{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":8,"n_cols":19,"rows_kept":8,"cut":false,"hidden":false,"merged":[[1,16,1,20],[2,17,2,18]]}
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Posession Indicator Tool"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Year","Week"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2025,1]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with RED = total closure on the section"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with YELLOW = reduced capacity on the section"]

{"sheet":"Schedule","index":1,"n_rows":4221,"n_cols":36,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,34,2,34],[1,30,2,30],[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof Day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID","Date of first publication","Date of last change","Lately announced","Re-routing possibilities"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"DB InfraGO","64C2-001","Rostock - Berlin","< >","Schönfließ West","Hennigsd N (Hdw)",2025,2025,43,46,"2025-10-24","22:00:00","2025-11-14","22:00:00","21d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-30"]
[null,"DB InfraGO","64C2-003","Rostock - Berlin","< >","Hohen Neuendorf West","Birkenwerder (b Berlin)",2025,2025,43,46,"2025-10-24","22:00:00","2025-11-14","22:00:00","21d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","64C2-004","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2025,2025,43,46,"2025-10-24","22:00:00","2025-11-14","22:00:00","21d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","650A-004","Hannover - Magdeburg",">","Braunschweig Hbf","Wolfenbüttel",2025,2025,28,30,"2025-07-07","23:40:00","2025-07-25","05:15:00","17d, 5h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","650A-007","Hannover - Magdeburg",">","Braunschweig Hbf","Wolfenbüttel",2025,2025,28,29,"2025-07-12","00:10:00","2025-07-19","05:15:00","7d, 5h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","650A-008","Hannover - Magdeburg",">","Braunschweig Hbf","Wolfenbüttel",2025,2025,28,29,"2025-07-13","00:10:00","2025-07-20","07:15:00","7d, 7h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","666B-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,35,35,"2025-08-26","09:00:00","2025-08-26","15:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N"]
[null,"DB InfraGO","666B-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,35,35,"2025-08-26","09:00:00","2025-08-26","15:00:00","0d, 6h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2",null,"N"]
[null,"DB InfraGO","6685-001","Hannover - Magdeburg",">","Hoheneggelsen","Groß Gleidingen",2025,2025,33,34,"2025-08-15","22:20:00","2025-08-23","02:05:00","7d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","6685-002","Hannover - Magdeburg","< >","Groß Gleidingen","Hoheneggelsen",2025,2025,33,34,"2025-08-15","22:20:00","2025-08-23","02:05:00","7d, 3h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","6685-003","Hannover - Magdeburg","< >","Groß Gleidingen","Hoheneggelsen",2025,2025,33,34,"2025-08-15","22:20:00","2025-08-23","02:05:00","7d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","6685-004","Hannover - Magdeburg","< >","Groß Gleidingen","Hoheneggelsen",2025,2025,33,33,"2025-08-16","02:30:00","2025-08-16","04:30:00","0d, 2h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","6685-008","Hannover - Magdeburg","< >","Groß Gleidingen","Hildesheim Hbf",2025,2025,34,34,"2025-08-23","02:05:00","2025-08-23","05:50:00","0d, 3h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","669D-001","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2025,2025,36,36,"2025-09-01","01:00:00","2025-09-01","03:00:00","0d, 2h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2023-06-21"]
[null,"DB InfraGO","669D-003","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,36,"2025-09-01","01:00:00","2025-09-01","03:00:00","0d, 2h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-11-24"]
[null,"DB InfraGO","669D-004","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,36,"2025-09-01","03:00:00","2025-09-01","05:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO","669D-005","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,36,"2025-09-01","03:00:00","2025-09-01","05:00:00","0d, 2h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO","669D-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,37,"2025-09-01","06:00:00","2025-09-08","04:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","669D-007","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2025,2025,36,36,"2025-09-01","06:00:00","2025-09-02","07:00:00","1d, 1h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2023-06-21"]
[null,"DB InfraGO","669D-008","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,37,"2025-09-01","06:00:00","2025-09-08","04:00:00","6d, 22h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","669D-009","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,36,"2025-09-02","01:00:00","2025-09-02","05:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N"]
[null,"DB InfraGO","669D-010","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,41,"2025-09-02","07:00:00","2025-10-09","22:00:00","37d, 15h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","669D-011","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,41,"2025-09-02","07:00:00","2025-10-09","22:00:00","37d, 15h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","68E7-003","Berlin - Dresden","< >","Hennersdorf West","Doberlug-Kh Nord",2025,2025,38,39,"2025-09-15","20:00:00","2025-09-22","05:00:00","6d, 9h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-14"]
[null,"DB InfraGO","669D-012","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2025,2025,36,36,"2025-09-02","12:00:00","2025-09-04","07:00:00","1d, 19h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4",null,"N",null,"2023-06-21"]
[null,"DB InfraGO","669D-013","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2025,2025,36,37,"2025-09-04","12:00:00","2025-09-08","04:00:00","3d, 16h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,4,5,6,7",null,"N",null,"2023-06-21"]
[null,"DB InfraGO","691C-002","Berlin - Dresden","< >","Doberlug-Kirchhain unt Bf","Doberlug-K ob Bf",2025,2025,42,42,"2025-10-18","20:00:00","2025-10-19","06:00:00","0d, 10h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-05-17"]
[null,"DB InfraGO","691C-003","Berlin - Dresden","< >","Doberlug-Kh Nord","Hennersdorf West",2025,2025,42,42,"2025-10-18","20:00:00","2025-10-19","06:00:00","0d, 10h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-05-17"]
[null,"DB InfraGO","669D-014","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2025,2025,36,36,"2025-09-06","01:00:00","2025-09-06","03:00:00","0d, 2h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2023-06-21"]
[null,"DB InfraGO","669D-015","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,36,36,"2025-09-06","01:00:00","2025-09-06","03:00:00","0d, 2h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-11-24"]
[null,"DB InfraGO","669D-016","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,37,37,"2025-09-08","01:00:00","2025-09-08","03:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO","669D-017","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,37,37,"2025-09-08","01:00:00","2025-09-08","03:00:00","0d, 2h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO","697B-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,37,38,"2025-09-09","22:00:00","2025-09-15","06:00:00","5d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","697B-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,37,38,"2025-09-09","22:00:00","2025-09-15","06:00:00","5d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","68E7-006","Berlin - Dresden","< >","Doberlug-Kirchhain unt Bf","Doberlug-K ob Bf",2025,2025,35,39,"2025-08-25","22:00:00","2025-09-22","22:00:00","28d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-14"]
[null,"DB InfraGO","6C64-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,38,39,"2025-09-15","06:00:00","2025-09-22","18:00:00","7d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-01"]
[null,"DB InfraGO","6AFF-001","Rostock - Berlin","< >","Berlin-Karow Ost","Schönfließ",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","6AFF-002","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","6AFF-003","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","6AFF-004","Rostock - Berlin","< >","Berlin-Karow West","Berlin-Karow West",2025,2025,15,16,"2025-04-11","21:00:00","2025-04-14","10:00:00","2d, 13h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","6C64-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,38,39,"2025-09-15","06:00:00","2025-09-22","18:00:00","7d, 12h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-24"]
[null,"DB InfraGO","6B00-001","Rostock - Berlin","< >","Berlin-Karow Ost","Schönfließ",2025,2025,34,34,"2025-08-19","22:20:00","2025-08-22","06:00:00","2d, 7h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4",null,"N",null,"2023-04-21"]
[null,"DB InfraGO","6B00-002","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,34,34,"2025-08-19","22:20:00","2025-08-22","06:00:00","2d, 7h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4",null,"N",null,"2023-04-21"]
[null,"DB InfraGO","6B00-003","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2025,2025,34,34,"2025-08-19","22:20:00","2025-08-22","06:00:00","2d, 7h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4",null,"N",null,"2023-04-21"]
[null,"DB InfraGO","6C64-003","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,38,38,"2025-09-19","00:00:00","2025-09-19","10:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C64-004","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,38,38,"2025-09-20","00:00:00","2025-09-20","08:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C64-005","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,38,38,"2025-09-20","18:00:00","2025-09-21","08:00:00","0d, 14h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,39,39,"2025-09-22","06:00:00","2025-09-27","13:00:00","5d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,39,41,"2025-09-22","06:00:00","2025-10-09","22:00:00","17d, 16h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-003","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,39,39,"2025-09-22","18:00:00","2025-09-27","13:00:00","4d, 19h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-004","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,40,40,"2025-09-29","16:00:00","2025-10-02","05:00:00","2d, 13h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-005","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,40,40,"2025-10-02","09:00:00","2025-10-02","15:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,40,40,"2025-10-02","22:00:00","2025-10-03","00:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6C67-007","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,41,41,"2025-10-06","09:00:00","2025-10-06","12:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6662-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,41,43,"2025-10-09","22:00:00","2025-10-25","09:00:00","15d, 11h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6662-007","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,41,43,"2025-10-09","22:00:00","2025-10-25","09:00:00","15d, 11h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6662-008","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,41,42,"2025-10-10","07:00:00","2025-10-15","07:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6662-009","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,42,42,"2025-10-15","03:00:00","2025-10-15","07:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6662-010","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,43,43,"2025-10-25","03:00:00","2025-10-25","07:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6662-011","Bremen - Hannover","<","Nienburg (Weser)","Nienburg (Weser)",2025,2025,43,43,"2025-10-25","05:00:00","2025-10-25","09:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-11-03"]
[null,"DB InfraGO","6F78-007","Hannover - Magdeburg","<","Hannover-Wülfel","Waldhausen",2025,2025,39,40,"2025-09-28","23:30:00","2025-09-29","05:15:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-06-05"]
[null,"DB InfraGO","6F78-013","Hannover - Magdeburg",">","Waldhausen","Hannover-Wülfel",2025,2025,40,40,"2025-09-30","05:00:00","2025-10-01","13:00:00","1d, 8h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-06-05"]
[null,"DB InfraGO","702F-001","Berlin - Dresden","< >","Rangsdorf","Wünsdorf-Waldstadt",2025,2025,22,23,"2025-05-30","21:00:00","2025-06-02","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-02-05"]
[null,"DB InfraGO","7223-001","Hannover - Magdeburg",">","Magdeburg-Sudenburg","Helmstedt",2024,2025,50,50,"2024-12-15","23:00:00","2025-12-08","05:00:00","357d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"Y",null,"2022-11-09"]
[null,"DB InfraGO","7703-001","Bremen - Hannover","< >","Ahlem","Seelze Ost",2025,2025,9,10,"2025-02-28","23:00:00","2025-03-04","05:00:00","3d, 6h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-002","Bremen - Hannover","<","Hannover-Linden Hafen","Seelze West",2025,2025,9,10,"2025-02-28","23:00:00","2025-03-04","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-003","Bremen - Hannover","< >","Hannover Kurve","Ahlem",2025,2025,9,10,"2025-02-28","23:00:00","2025-03-04","05:00:00","3d, 6h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-004","Bremen - Hannover",">","Seelze West","Hannover-Linden Hafen",2025,2025,10,10,"2025-03-04","23:00:00","2025-03-09","05:00:00","4d, 6h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-005","Bremen - Hannover","< >","Seelze Ost","Ahlem",2025,2025,10,10,"2025-03-04","23:00:00","2025-03-09","05:00:00","4d, 6h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-006","Bremen - Hannover","< >","Ahlem","Seelze Ost",2025,2025,10,11,"2025-03-09","22:00:00","2025-03-10","06:00:00","0d, 8h","Continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-007","Bremen - Hannover","<","Hannover-Linden Hafen","Seelze West",2025,2025,10,11,"2025-03-09","22:00:00","2025-03-10","06:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-008","Bremen - Hannover","< >","Hannover Kurve","Ahlem",2025,2025,10,11,"2025-03-09","22:00:00","2025-03-10","06:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-009","Bremen - Hannover",">","Seelze West","Hannover-Linden Hafen",2025,2025,11,11,"2025-03-10","22:00:00","2025-03-11","06:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-010","Bremen - Hannover","< >","Seelze Ost","Ahlem",2025,2025,11,11,"2025-03-10","22:00:00","2025-03-11","06:00:00","0d, 8h","Continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-011","Bremen - Hannover",">","Seelze West","Hannover-Linden Hafen",2025,2025,11,11,"2025-03-11","23:00:00","2025-03-14","05:00:00","2d, 6h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7703-012","Bremen - Hannover","< >","Seelze Ost","Hannover-Linden Hafen",2025,2025,11,11,"2025-03-11","23:00:00","2025-03-14","05:00:00","2d, 6h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7705-001","Bremen - Hannover",">","Seelze West","Hannover-Linden Hafen",2025,2025,15,15,"2025-04-12","22:05:00","2025-04-13","06:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7705-002","Bremen - Hannover","< >","Seelze Ost","Ahlem",2025,2025,15,15,"2025-04-12","22:05:00","2025-04-13","06:00:00","0d, 7h","Continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7705-003","Bremen - Hannover","< >","Ahlem","Seelze Ost",2025,2025,15,16,"2025-04-13","22:05:00","2025-04-14","06:00:00","0d, 7h","Continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7705-004","Bremen - Hannover","<","Hannover-Linden Hafen","Seelze West",2025,2025,15,16,"2025-04-13","22:05:00","2025-04-14","06:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7705-005","Bremen - Hannover","< >","Hannover Kurve","Ahlem",2025,2025,15,16,"2025-04-13","22:05:00","2025-04-14","06:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-11-16"]
[null,"DB InfraGO","7789-001","Bremen - Hannover","< >","Hannover-Linden","Hannover-Linden",2024,2025,51,2,"2024-12-16","06:00:00","2025-01-12","20:00:00","27d, 14h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","7789-002","Bremen - Hannover","< >","Hannover-Linden","Hannover-Linden",2024,2025,51,2,"2024-12-16","06:00:00","2025-01-12","20:00:00","27d, 14h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","7789-003","Bremen - Hannover","< >","Seelze Ost","Hannover-Linden Hafen",2025,2025,1,2,"2025-01-04","21:00:00","2025-01-10","21:00:00","6d, 0h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","7789-004","Bremen - Hannover","< >","Ahlem","Hannover Kurve",2025,2025,1,2,"2025-01-04","21:00:00","2025-01-10","21:00:00","6d, 0h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","7789-005","Bremen - Hannover","< >","Ahlem","Ahlem",2025,2025,2,2,"2025-01-10","21:00:00","2025-01-12","21:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","7789-006","Bremen - Hannover","< >","Ahlem","Hannover-Linden Hafen",2025,2025,2,2,"2025-01-10","21:00:00","2025-01-12","21:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","77B6-001","Bremen - Hannover",">","Seelze West","Hannover-Linden Hafen",2025,2025,13,13,"2025-03-25","23:00:00","2025-03-27","01:00:00","1d, 2h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","77B6-002","Bremen - Hannover","< >","Seelze Ost","Hannover-Linden Hafen",2025,2025,13,13,"2025-03-26","01:00:00","2025-03-27","03:00:00","1d, 2h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","77B6-003","Bremen - Hannover","<","Hannover-Linden Hafen","Seelze West",2025,2025,13,13,"2025-03-26","03:00:00","2025-03-27","06:00:00","1d, 3h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","77B6-004","Bremen - Hannover","< >","Ahlem","Hannover Kurve",2025,2025,13,13,"2025-03-26","01:00:00","2025-03-27","06:00:00","1d, 5h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","780B-001","Hamburg - Magdeburg","< >","Jesteburg","Maschen Rbf (Msof)",2024,2024,50,50,"2024-12-15","04:30:00","2024-12-15","20:30:00","0d, 16h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","780B-002","Hamburg - Magdeburg","<","Maschen Rbf (Msof)","Jesteburg",2024,2024,50,51,"2024-12-15","00:01:00","2024-12-20","16:00:00","5d, 15h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","780B-003","Hamburg - Magdeburg",">","Jesteburg","Maschen Rbf (Msof)",2024,2024,50,51,"2024-12-15","00:01:00","2024-12-20","16:00:00","5d, 15h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","780B-004","Hamburg - Magdeburg",">","Jesteburg","Maschen Rbf (Msof)",2024,2024,51,51,"2024-12-19","10:00:00","2024-12-19","15:00:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2022-11-17"]
[null,"DB InfraGO","780B-005","Hamburg - Magdeburg","<","Maschen Rbf (Msof)","Jesteburg",2024,2024,51,51,"2024-12-20","10:00:00","2024-12-20","15:00:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","7938-001","Hannover - Magdeburg",">","Braunschweig Hbf","Helmstedt",2024,2025,50,50,"2024-12-15","23:05:00","2025-12-13","04:30:00","362d, 5h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","9BC0-001","Rostock - Berlin","< >","Berlin-Karow Ost","Hohen Neuendorf West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-002","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","9BC0-003","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","9BC0-004","Rostock - Berlin","< >","Hohen Neuend Sw","Bergfelde Ost",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","9BC0-005","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","9BC0-006","Rostock - Berlin","< >","Hohen Neuend Sw","Schönfließ West",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","9BC0-007","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2025,2025,13,15,"2025-03-24","21:00:00","2025-04-11","21:00:00","17d, 23h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","7ABE-001","Magdeburg - Falkenberg","< >","Magdeburg Hbf","Magdeburg-Hasselbachplatz",2025,2025,22,22,"2025-05-31","12:00:00","2025-06-01","04:00:00","0d, 16h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","7ABE-002","Hannover - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,22,22,"2025-05-31","12:00:00","2025-06-01","04:00:00","0d, 16h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-11-21"]
[null,"DB InfraGO","9BC0-008","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","01:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","9BC0-009","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuendorf West",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","01:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-010","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","01:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-011","Rostock - Berlin","< >","Bln-Hohenschhsn","Berlin-Karow West",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-012","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-013","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Blankenburg",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-014","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","9BC0-015","Rostock - Berlin","< >","Hohen Neuend Sw","Oranienburg",2025,2025,14,15,"2025-04-06","22:00:00","2025-04-07","05:00:00","0d, 7h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","9BC0-016","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuendorf West",2025,2025,14,15,"2025-04-06","22:00:00","2025-04-07","05:00:00","0d, 7h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","9BC0-017","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,14,15,"2025-04-06","22:00:00","2025-04-07","05:00:00","0d, 7h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","9BC0-018","Rostock - Berlin","< >","Birkenwerder Nord","Birkenwerder (b Berlin)",2025,2025,14,15,"2025-04-06","22:00:00","2025-04-07","05:00:00","0d, 7h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","7B81-001","Falkenberg - Dresden","< >","Riesa","Weißig (b Großenhain)",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","7B81-002","Falkenberg - Dresden","< >","Riesa","Röderau",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","7B81-003","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","7B81-004","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Röderau",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-22"]
[null,"DB InfraGO","7D03-001","Bremen - Hannover",">","Seelze West","Waldhausen",2024,2025,50,50,"2024-12-15","05:40:00","2025-12-13","11:40:00","363d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","7D06-001","Bremen - Hannover",">","Hannover-Waldheim","Lehrte Bahnhofsteil Ahlten",2024,2025,50,50,"2024-12-15","05:00:00","2025-12-13","11:00:00","363d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"Y",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-019","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2025,2025,15,15,"2025-04-10","22:00:00","2025-04-11","02:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-020","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuendorf West",2025,2025,15,15,"2025-04-10","22:00:00","2025-04-11","02:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-021","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,15,15,"2025-04-10","22:00:00","2025-04-11","02:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-022","Rostock - Berlin","< >","Bln-Hohenschhsn","Berlin-Karow West",2025,2025,15,15,"2025-04-11","02:00:00","2025-04-11","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-023","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,15,15,"2025-04-11","02:00:00","2025-04-11","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-024","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,15,15,"2025-04-11","02:00:00","2025-04-11","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC0-025","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Blankenburg",2025,2025,15,15,"2025-04-11","02:00:00","2025-04-11","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2022-11-23"]
[null,"DB InfraGO","9BC1-001","Rostock - Berlin","< >","Schönfließ","Schönfließ",2025,2025,34,39,"2025-08-22","22:00:00","2025-09-22","04:00:00","30d, 6h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-02-23"]
[null,"DB InfraGO","7694-063","Rostock - Berlin","< >","Berlin-Karow Ost","Hohen Neuendorf West",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7694-064","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7694-065","Rostock - Berlin","< >","Berlin-Karow West","Berlin-Blankenburg",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7694-066","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7694-067","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7694-068","Rostock - Berlin","< >","Hohen Neuend Sw","Schönfließ West",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7694-069","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuend Sw",2025,2025,25,26,"2025-06-20","22:00:00","2025-06-23","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-04-20"]
[null,"DB InfraGO","7D6E-001","Magdeburg - Falkenberg","<","Meinsdorf","Medewitz (Mark)",2025,2025,39,40,"2025-09-22","21:00:00","2025-09-29","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","7DF3-001","Magdeburg - Falkenberg",">","Lutherstadt Wittenberg Hbf","Bitterfeld",2025,2025,45,46,"2025-11-07","21:00:00","2025-11-14","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-24"]
[null,"DB InfraGO","7E90-001","Magdeburg - Falkenberg",">","Jüterbog","Lutherstadt Wittenberg Hbf",2025,2025,46,47,"2025-11-14","21:00:00","2025-11-21","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-25"]
[null,"DB InfraGO","7FCD-001","Falkenberg - Dresden",">","Zeithain Bogendreieck","Leckwitz",2024,2025,50,30,"2024-12-15","00:00:00","2025-07-25","21:00:00","222d, 20h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","7FCD-002","Falkenberg - Dresden",">","Weißig (b Großenhain)","Weißig (b Großenhain)",2024,2025,50,30,"2024-12-15","00:00:00","2025-07-25","21:00:00","222d, 20h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","7FCD-004","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Zeithain Bogendreieck",2024,2025,50,30,"2024-12-15","00:00:00","2025-07-25","21:00:00","222d, 20h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","7FCD-005","Falkenberg - Dresden","< >","Leckwitz","Weißig (b Großenhain)",2024,2025,50,30,"2024-12-15","22:00:00","2025-07-25","21:00:00","221d, 22h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","7FCD-006","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Leckwitz",2024,2025,50,30,"2024-12-15","00:00:00","2025-07-25","21:00:00","222d, 20h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8028-001","Magdeburg - Falkenberg","< >","Magdeburg Hbf","Magdeburg Südseite",2025,2025,26,26,"2025-06-28","07:00:00","2025-06-28","19:00:00","0d, 12h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8051-001","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück Stw Gkn",2025,2025,39,46,"2025-09-26","08:00:00","2025-11-12","12:00:00","47d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-03-27"]
[null,"DB InfraGO","8053-001","Magdeburg - Falkenberg",">","Roßlau (Elbe)","Bitterfeld",2025,2025,15,16,"2025-04-07","21:00:00","2025-04-14","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-12-19"]
[null,"DB InfraGO","8051-002","Magdeburg - Falkenberg","< >","Gommern","Gommern",2025,2025,39,46,"2025-09-26","08:00:00","2025-11-12","12:00:00","47d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-03-27"]
[null,"DB InfraGO","8051-004","Magdeburg - Falkenberg","<","Rodleben","Güterglück",2025,2025,40,44,"2025-10-04","21:00:00","2025-11-02","05:00:00","28d, 9h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-04-03"]
[null,"DB InfraGO","8017-001","Falkenberg - Dresden","< >","Röderau","Röderau",2024,2025,50,43,"2024-12-15","00:00:00","2025-10-26","23:59:00","315d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","8051-005","Magdeburg - Falkenberg","< >","Güterglück","Güterglück",2025,2025,40,44,"2025-10-04","21:00:00","2025-11-02","05:00:00","28d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-006","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Rodleben",2025,2025,40,44,"2025-10-04","21:00:00","2025-11-02","05:00:00","28d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8017-003","Falkenberg - Dresden","< >","Röderau","Zeithain Bogendreieck",2024,2024,51,51,"2024-12-16","00:40:00","2024-12-21","01:40:00","5d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-004","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2024,2024,51,51,"2024-12-16","00:40:00","2024-12-21","01:40:00","5d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-005","Falkenberg - Dresden","< >","Röderau Bogendreieck","Weißig (b Großenhain)",2024,2024,51,51,"2024-12-16","00:40:00","2024-12-21","01:40:00","5d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-006","Falkenberg - Dresden",">","Leckwitz","Priestewitz",2024,2024,51,51,"2024-12-16","00:40:00","2024-12-21","01:40:00","5d, 1h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-007","Falkenberg - Dresden","< >","Röderau","Zeithain Bogendreieck",2024,2024,51,51,"2024-12-16","03:40:00","2024-12-21","04:40:00","5d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-008","Falkenberg - Dresden","< >","Zeithain Rohrwerk","Zeithain Bogendreieck",2024,2024,51,51,"2024-12-16","03:40:00","2024-12-21","04:40:00","5d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-009","Falkenberg - Dresden","< >","Röderau Bogendreieck","Weißig (b Großenhain)",2024,2024,51,51,"2024-12-16","03:40:00","2024-12-21","04:40:00","5d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-010","Falkenberg - Dresden",">","Leckwitz","Priestewitz",2024,2024,51,51,"2024-12-16","03:40:00","2024-12-21","04:40:00","5d, 1h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8017-011","Falkenberg - Dresden","< >","Röderau","Zeithain Bogendreieck",2025,2025,2,11,"2025-01-06","00:40:00","2025-03-15","01:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","8017-012","Falkenberg - Dresden","< >","Zeithain Rohrwerk","Zeithain Bogendreieck",2025,2025,2,11,"2025-01-06","00:40:00","2025-03-15","01:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-29"]
[null,"DB InfraGO","8017-013","Falkenberg - Dresden","< >","Röderau Bogendreieck","Weißig (b Großenhain)",2025,2025,2,11,"2025-01-06","00:40:00","2025-03-15","01:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","8017-014","Falkenberg - Dresden",">","Leckwitz","Priestewitz",2025,2025,2,11,"2025-01-06","00:40:00","2025-03-15","01:40:00","68d, 1h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","8017-015","Falkenberg - Dresden","< >","Röderau","Zeithain Bogendreieck",2025,2025,2,11,"2025-01-06","03:40:00","2025-03-15","04:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","8017-016","Falkenberg - Dresden","< >","Zeithain Rohrwerk","Zeithain Bogendreieck",2025,2025,2,11,"2025-01-06","03:40:00","2025-03-15","04:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","8017-017","Falkenberg - Dresden","< >","Röderau Bogendreieck","Weißig (b Großenhain)",2025,2025,2,11,"2025-01-06","03:40:00","2025-03-15","04:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","8017-018","Falkenberg - Dresden",">","Leckwitz","Priestewitz",2025,2025,2,11,"2025-01-06","03:40:00","2025-03-15","04:40:00","68d, 1h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2022-11-28"]
[null,"DB InfraGO","80B1-001","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Priestewitz",2025,2025,14,15,"2025-04-05","07:00:00","2025-04-12","19:00:00","7d, 12h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","80B1-002","Berlin - Dresden","< >","Leckwitz","Kottewitz",2025,2025,14,15,"2025-04-05","07:00:00","2025-04-12","19:00:00","7d, 12h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","80B1-003","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,14,15,"2025-04-05","07:00:00","2025-04-12","19:00:00","7d, 12h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","80C1-001","Magdeburg - Falkenberg",">","Falkenberg (Elster) unt Bf Stw W 26","Lutherstadt Wittenberg Hbf",2025,2025,16,16,"2025-04-18","21:00:00","2025-04-20","05:00:00","1d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","80C1-003","Magdeburg - Falkenberg",">","Falkenberg (Elster) unt Bf Stw W 26","Lutherstadt Wittenberg Hbf",2025,2025,17,18,"2025-04-25","21:00:00","2025-05-02","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","80C1-004","Magdeburg - Falkenberg",">","Falkenberg (Elster) unt Bf Stw W 26","Lutherstadt Wittenberg Hbf",2025,2025,18,19,"2025-05-02","21:00:00","2025-05-09","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","80C1-005","Magdeburg - Falkenberg",">","Falkenberg (Elster) unt Bf Stw W 26","Lutherstadt Wittenberg Hbf",2025,2025,19,20,"2025-05-09","21:00:00","2025-05-16","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","8051-007","Magdeburg - Falkenberg","< >","Güterglück","Rodleben",2025,2025,40,41,"2025-10-05","23:50:00","2025-10-09","01:30:00","3d, 1h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-008","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Rodleben",2025,2025,42,44,"2025-10-18","23:00:00","2025-11-02","05:00:00","14d, 7h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-009","Magdeburg - Falkenberg",">","Güterglück Stw Gkn","Rodleben",2025,2025,39,40,"2025-09-27","21:00:00","2025-10-04","21:00:00","7d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-03-27"]
[null,"DB InfraGO","8051-010","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück",2025,2025,39,40,"2025-09-27","21:00:00","2025-10-04","21:00:00","7d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-013","Magdeburg - Falkenberg","<","Güterglück","Gommern",2025,2025,40,40,"2025-10-04","21:00:00","2025-10-05","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","810B-001","Falkenberg - Dresden","< >","Röderau Bogendreieck","Priestewitz",2025,2025,29,29,"2025-07-20","00:00:00","2025-07-20","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810B-002","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Röderau",2025,2025,29,29,"2025-07-20","00:00:00","2025-07-20","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","810B-003","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,29,29,"2025-07-20","00:00:00","2025-07-20","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","810B-004","Berlin - Dresden","< >","Leckwitz","Kottewitz",2025,2025,29,29,"2025-07-20","00:00:00","2025-07-20","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","810C-001","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Priestewitz",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810C-002","Berlin - Dresden","< >","Leckwitz","Kottewitz",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","810C-003","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,30,31,"2025-07-25","21:00:00","2025-07-28","21:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810C-005","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Bogendreieck",2025,2025,30,30,"2025-07-25","21:00:00","2025-07-26","21:00:00","1d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810C-006","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Röderau",2025,2025,30,30,"2025-07-25","21:00:00","2025-07-26","21:00:00","1d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810C-007","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,30,30,"2025-07-25","21:00:00","2025-07-26","21:00:00","1d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810C-008","Berlin - Dresden","< >","Großenhain Cottb Bf","Priestewitz",2025,2025,30,30,"2025-07-25","21:00:00","2025-07-26","07:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","810C-009","Falkenberg - Dresden","< >","Priestewitz","Coswig (bei Dresden) Stw 1",2025,2025,30,30,"2025-07-25","21:00:00","2025-07-26","07:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-11-28"]
[null,"DB InfraGO","812B-001","Falkenberg - Dresden",">","Röderau Bogendreieck","Zeithain Bogendreieck",2025,2025,31,31,"2025-07-28","21:00:00","2025-07-29","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","812B-002","Falkenberg - Dresden",">","Zeithain Bogendreieck","Weißig (b Großenhain)",2025,2025,31,31,"2025-07-28","21:00:00","2025-07-29","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","812B-003","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,31,31,"2025-07-29","21:00:00","2025-07-30","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","8141-005","Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2025,2025,27,27,"2025-07-03","07:00:00","2025-07-05","19:00:00","2d, 12h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5,6",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","812B-004","Falkenberg - Dresden","<","Weißig (b Großenhain)","Zeithain Bogendreieck",2025,2025,31,31,"2025-07-29","21:00:00","2025-07-30","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","812B-005","Falkenberg - Dresden","<","Zeithain Bogendreieck","Riesa",2025,2025,31,31,"2025-07-29","21:00:00","2025-07-30","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","812B-006","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Röderau",2025,2025,31,31,"2025-07-29","21:00:00","2025-07-30","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","8141-007","Hannover - Magdeburg","< >","Magdeburg-Sudenburg","Magdeburg-Buckau",2025,2025,27,27,"2025-07-03","07:00:00","2025-07-05","19:00:00","2d, 12h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5,6",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","8141-008","Hannover - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,27,27,"2025-07-03","07:00:00","2025-07-05","19:00:00","2d, 12h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8188-001","Falkenberg - Dresden",">","Weißig (b Großenhain)","Leckwitz",2025,2025,31,31,"2025-07-28","21:00:00","2025-07-30","21:00:00","2d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","8188-002","Falkenberg - Dresden",">","Zeithain Bogendreieck","Weißig (b Großenhain)",2025,2025,31,31,"2025-07-28","21:00:00","2025-07-30","21:00:00","2d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81B5-001","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,31,43,"2025-07-28","21:00:00","2025-10-24","16:00:00","87d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81B5-003","Falkenberg - Dresden","<","Weißig (b Großenhain)","Zeithain Bogendreieck",2025,2025,33,35,"2025-08-11","08:00:00","2025-08-29","16:00:00","18d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-001","Falkenberg - Dresden",">","Zeithain Bogendreieck","Leckwitz",2025,2025,40,40,"2025-10-01","20:00:00","2025-10-03","05:00:00","1d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-002","Falkenberg - Dresden",">","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,40,40,"2025-10-01","20:00:00","2025-10-03","05:00:00","1d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-004","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Röderau",2025,2025,40,40,"2025-10-01","20:00:00","2025-10-02","20:45:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-005","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,40,40,"2025-10-01","20:00:00","2025-10-02","20:45:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-006","Falkenberg - Dresden","< >","Röderau Bogendreieck","Weißig (b Großenhain)",2025,2025,40,40,"2025-10-01","20:00:00","2025-10-02","20:45:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-007","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Röderau",2025,2025,40,40,"2025-10-02","04:15:00","2025-10-03","05:00:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-008","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,40,40,"2025-10-02","04:15:00","2025-10-03","05:00:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-009","Falkenberg - Dresden","< >","Röderau Bogendreieck","Weißig (b Großenhain)",2025,2025,40,40,"2025-10-02","04:15:00","2025-10-03","05:00:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-010","Falkenberg - Dresden",">","Zeithain Bogendreieck","Leckwitz",2025,2025,41,41,"2025-10-06","20:00:00","2025-10-10","05:00:00","3d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-011","Falkenberg - Dresden",">","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,41,41,"2025-10-06","20:00:00","2025-10-10","05:00:00","3d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81EC-001","Falkenberg - Dresden",">","Zeithain Bogendreieck","Weißig (b Großenhain)",2025,2025,41,41,"2025-10-10","21:00:00","2025-10-11","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81EC-002","Falkenberg - Dresden",">","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,41,41,"2025-10-10","21:00:00","2025-10-11","05:00:00","0d, 8h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","81C2-013","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Weißig (b Großenhain)",2025,2025,41,41,"2025-10-09","20:00:00","2025-10-10","05:00:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","8224-001","Hamburg - Magdeburg","< >","Lehrte","Lehrte",2025,2025,46,47,"2025-11-10","08:00:00","2025-11-17","04:00:00","6d, 20h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","8224-002","Bremen - Hannover","< >","Lehrte West","Lehrte West",2025,2025,46,47,"2025-11-12","08:00:00","2025-11-19","08:00:00","7d, 0h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","822A-001","Falkenberg - Dresden","< >","Weinböhla","Großenhain Berl Bf",2025,2025,37,50,"2025-09-12","00:00:00","2025-12-12","23:59:00","92d, 0h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-29"]
[null,"DB InfraGO","822A-002","Berlin - Dresden","< >","Kottewitz","Leckwitz",2025,2025,37,50,"2025-09-12","00:00:00","2025-12-12","23:59:00","92d, 0h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-29"]
[null,"DB InfraGO","822A-003","Falkenberg - Dresden","< >","Weinböhla","Weinböhla",2025,2025,37,50,"2025-09-12","00:00:00","2025-12-12","23:59:00","92d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-29"]
[null,"DB InfraGO","822A-004","Falkenberg - Dresden","< >","Großenhain Berl Bf","Großenhain Berl Bf",2025,2025,37,50,"2025-09-12","00:00:00","2025-12-12","23:59:00","92d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-29"]
[null,"DB InfraGO","822A-005","Falkenberg - Dresden","< >","Weinböhla","Kottewitz",2025,2025,50,50,"2025-12-12","23:59:00","2025-12-13","23:59:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-11-29"]
[null,"DB InfraGO","8249-001","Falkenberg - Dresden","<","Radebeul Nord","Radebeul Abzw Az",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-30"]
[null,"DB InfraGO","8249-002","Falkenberg - Dresden",">","Radebeul-Naundorf","Weinböhla",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-30"]
[null,"DB InfraGO","8249-003","Falkenberg - Dresden",">","Radebeul Abzw Az","Weinböhla",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8249-004","Falkenberg - Dresden",">","Weinböhla","Weinböhla",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8249-005","Falkenberg - Dresden","< >","Radebeul Abzw Az","Weinböhla",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8249-006","Falkenberg - Dresden","< >","Radebeul Abzw Az","Weinböhla",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8249-007","Falkenberg - Dresden","< >","Radebeul Abzw Az","Weinböhla",2025,2025,37,50,"2025-09-12","08:00:00","2025-12-12","18:00:00","91d, 11h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-11-30"]
[null,"DB InfraGO","8051-015","Magdeburg - Falkenberg","< >","Güterglück","Rodleben",2025,2025,40,44,"2025-10-04","21:00:00","2025-11-02","05:00:00","28d, 9h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-016","Magdeburg - Falkenberg","<","Güterglück","Gommern",2025,2025,44,44,"2025-11-01","21:00:00","2025-11-02","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-017","Magdeburg - Falkenberg","< >","Güterglück","Rodleben",2025,2025,39,40,"2025-09-27","22:00:00","2025-10-04","21:00:00","6d, 23h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","64C2-008","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,43,46,"2025-10-23","08:00:00","2025-11-14","16:00:00","22d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8051-020","Magdeburg - Falkenberg","<","Trebnitz Strw","Güterglück",2025,2025,44,45,"2025-11-02","05:00:00","2025-11-08","05:00:00","6d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-04-03"]
[null,"DB InfraGO","82C6-001","Falkenberg - Dresden","<","Radebeul Nord","Radebeul Abzw Az",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","16:20:00","34d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-002","Falkenberg - Dresden",">","Radebeul Abzw Az","Kottewitz",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","16:20:00","34d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","8224-003","Bremen - Hannover",">","Lehrte West","Lehrte Nord",2025,2025,46,47,"2025-11-14","20:05:00","2025-11-17","06:50:00","2d, 10h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","82C6-003","Falkenberg - Dresden",">","Weinböhla","Weinböhla",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","16:20:00","34d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-004","Falkenberg - Dresden",">","Radebeul Abzw Az","Weinböhla",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","16:20:00","34d, 8h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-005","Falkenberg - Dresden","<","Weinböhla","Radebeul Abzw Az",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","16:20:00","34d, 8h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","82C6-006","Falkenberg - Dresden","< >","Radebeul Abzw Az","Weinböhla",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","16:20:00","34d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-007","Falkenberg - Dresden",">","Cossebaude","Radebeul-Naundorf",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","08:20:00","34d, 0h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-008","Falkenberg - Dresden","< >","Radebeul-Naundorf","Radebeul Abzw Az",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","08:20:00","34d, 0h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-009","Falkenberg - Dresden","< >","Radebeul Nord","Radebeul Abzw Az",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","08:20:00","34d, 0h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-010","Falkenberg - Dresden",">","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2025,2025,32,37,"2025-08-08","07:35:00","2025-09-11","08:20:00","34d, 0h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-011","Falkenberg - Dresden",">","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2025,2025,32,37,"2025-08-08","15:35:00","2025-09-11","16:20:00","34d, 0h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-012","Falkenberg - Dresden",">","Cossebaude","Radebeul-Naundorf",2025,2025,32,37,"2025-08-08","15:35:00","2025-09-11","16:20:00","34d, 0h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","8224-004","Hamburg - Magdeburg","< >","Lehrte","Lehrte",2025,2025,46,47,"2025-11-14","20:05:00","2025-11-17","06:50:00","2d, 10h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","82C6-013","Falkenberg - Dresden","< >","Radebeul-Naundorf","Radebeul Abzw Az",2025,2025,32,37,"2025-08-08","15:35:00","2025-09-11","16:20:00","34d, 0h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","82C6-014","Falkenberg - Dresden","< >","Radebeul Nord","Radebeul Abzw Az",2025,2025,32,37,"2025-08-08","15:35:00","2025-09-11","16:20:00","34d, 0h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-21"]
[null,"DB InfraGO","8224-005","Bremen - Hannover","< >","Lehrte West","Lehrte West",2025,2025,46,46,"2025-11-14","20:05:00","2025-11-14","23:00:00","0d, 2h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8224-006","Bremen - Hannover","< >","Lehrte West","Lehrte West",2025,2025,47,47,"2025-11-17","04:00:00","2025-11-17","06:50:00","0d, 2h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8224-007","Bremen - Hannover","< >","Lehrte West","Lehrte Nord",2025,2025,46,47,"2025-11-14","20:05:00","2025-11-17","06:50:00","2d, 10h","Continuous","Others",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8224-008","Bremen - Hannover","< >","Lehrte Nord","Lehrte West",2025,2025,46,46,"2025-11-14","23:00:00","2025-11-15","04:00:00","0d, 5h","Continuous","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8224-009","Bremen - Hannover","< >","Lehrte Nord","Lehrte West",2025,2025,46,47,"2025-11-16","23:00:00","2025-11-17","04:00:00","0d, 5h","Continuous","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-11-30"]
[null,"DB InfraGO","8051-021","Magdeburg - Falkenberg","<","Rodleben","Güterglück",2025,2025,44,46,"2025-11-02","23:00:00","2025-11-14","05:00:00","11d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-022","Magdeburg - Falkenberg","< >","Rodleben","Rodleben",2025,2025,44,46,"2025-11-02","23:00:00","2025-11-14","05:00:00","11d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-023","Magdeburg - Falkenberg","< >","Güterglück","Güterglück",2025,2025,44,46,"2025-11-02","23:00:00","2025-11-14","05:00:00","11d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-024","Magdeburg - Falkenberg","< >","Güterglück","Trebnitz Strw",2025,2025,39,40,"2025-09-27","22:00:00","2025-10-04","21:00:00","6d, 23h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-04-03"]
[null,"DB InfraGO","8051-025","Magdeburg - Falkenberg","< >","Güterglück","Trebnitz Strw",2025,2025,40,44,"2025-10-04","21:00:00","2025-11-02","05:00:00","28d, 9h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","8051-026","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück",2025,2025,43,43,"2025-10-20","23:00:00","2025-10-22","05:00:00","1d, 6h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","80D3-001","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück Stw Gkn",2025,2025,36,37,"2025-09-06","08:00:00","2025-09-10","12:00:00","4d, 4h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,6,7",null,"N",null,"2023-04-28"]
[null,"DB InfraGO","80D3-002","Magdeburg - Falkenberg",">","Güterglück Stw Gkn","Rodleben",2025,2025,36,37,"2025-09-06","21:00:00","2025-09-10","05:00:00","3d, 8h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,6",null,"N",null,"2023-04-28"]
[null,"DB InfraGO","80D3-003","Magdeburg - Falkenberg","<","Rodleben","Güterglück",2025,2025,36,37,"2025-09-07","21:00:00","2025-09-09","05:00:00","1d, 8h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-04-28"]
[null,"DB InfraGO","80D3-004","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe)",2025,2025,36,37,"2025-09-07","21:00:00","2025-09-09","05:00:00","1d, 8h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-04-28"]
[null,"DB InfraGO","80D3-005","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück",2025,2025,36,37,"2025-09-06","21:00:00","2025-09-10","05:00:00","3d, 8h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,6",null,"N",null,"2023-04-28"]
[null,"DB InfraGO","84A6-001","Hannover - Magdeburg",">","Magdeburg Hbf","Helmstedt",2025,2025,18,20,"2025-05-02","21:00:00","2025-05-16","05:00:00","13d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","84B8-001","Hannover - Magdeburg",">","Magdeburg Hbf","Helmstedt",2025,2025,21,22,"2025-05-23","21:00:00","2025-05-30","05:00:00","6d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","84C6-001","Hannover - Magdeburg",">","Magdeburg-Sudenburg","Eilsleben (b Magdeburg)",2025,2025,20,21,"2025-05-16","21:00:00","2025-05-23","05:00:00","6d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","68BC-004","Berlin - Dresden","< >","Doberlug-Kirchhain unt Bf","Doberlug-K ob Bf",2025,2025,34,39,"2025-08-23","08:00:00","2025-09-24","16:00:00","32d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","8521-001","Rostock - Berlin","< >","Bln-Hohenschhsn","Karower Kr Strw",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-12","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","8521-002","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-12","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","8521-003","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Blankenburg",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-12","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","8521-004","Rostock - Berlin","< >","Bln-Hohenschhsn","Karower Kr Strw",2025,2025,32,32,"2025-08-04","22:00:00","2025-08-09","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-03-23"]
[null,"DB InfraGO","8521-005","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,32,32,"2025-08-04","22:00:00","2025-08-09","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-03-23"]
[null,"DB InfraGO","8521-006","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Blankenburg",2025,2025,32,32,"2025-08-04","22:00:00","2025-08-09","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-03-23"]
[null,"DB InfraGO","8521-007","Rostock - Berlin","< >","Bln-Hohenschhsn","Karower Kr Strw",2025,2025,35,36,"2025-08-31","22:00:00","2025-09-05","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","8521-008","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,35,36,"2025-08-31","22:00:00","2025-09-05","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","8521-009","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Blankenburg",2025,2025,35,36,"2025-08-31","22:00:00","2025-09-05","04:00:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","850A-002","Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2025,2025,32,32,"2025-08-08","23:30:00","2025-08-09","12:30:00","0d, 13h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-12-02"]
[null,"DB InfraGO","87CC-001","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2025,2025,10,10,"2025-03-08","22:25:00","2025-03-09","08:25:00","0d, 10h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87CC-002","Hannover - Magdeburg","<","Helmstedt","Frellstedt",2025,2025,10,11,"2025-03-09","20:35:00","2025-03-10","06:10:00","0d, 9h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87CF-001","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2025,2025,11,11,"2025-03-14","21:35:00","2025-03-15","07:20:00","0d, 9h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87CF-002","Hannover - Magdeburg","< >","Helmstedt","Schandelah",2025,2025,11,11,"2025-03-15","21:35:00","2025-03-16","11:10:00","0d, 13h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-004","Hannover - Magdeburg","< >","Magdeburg-Neustadt","Niederndodeleben",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-005","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Neustadt",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87CF-003","Hannover - Magdeburg","< >","Helmstedt","Harbke",2025,2025,11,11,"2025-03-15","21:35:00","2025-03-16","11:10:00","0d, 13h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87CF-004","Hannover - Magdeburg","<","Helmstedt","Frellstedt",2025,2025,11,12,"2025-03-16","20:35:00","2025-03-17","06:10:00","0d, 9h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-006","Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-007","Magdeburg - Falkenberg","< >","Magdeburg Hbf","Dodendorf",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-008","Hannover - Magdeburg","< >","Magdeburg-Neustadt","Magdeburg-Buckau",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-009","Magdeburg - Falkenberg","< >","Magdeburg Hbf","Magdeburg Südseite",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-010","Hannover - Magdeburg","< >","Magdeburg-Buckau","Magdeburg-Sudenburg",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","850A-011","Hannover - Magdeburg","< >","Tornitz Seehof","Magdeburg Hbf",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","864C-001","Hamburg - Magdeburg","< >","Hamburg-Wilhelmsburg","Hamburg-Harburg",2025,2025,19,23,"2025-05-10","00:00:00","2025-06-08","16:00:00","29d, 16h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","864C-002","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,20,23,"2025-05-12","00:00:00","2025-06-08","16:00:00","27d, 16h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","864C-003","Hamburg - Magdeburg","< >","Süderelbbrücke","Hmb H Schaar Süd",2025,2025,19,23,"2025-05-10","00:00:00","2025-06-08","16:00:00","29d, 16h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","850A-014","Hannover - Magdeburg","< >","Helmstedt","Magdeburg-Sudenburg",2025,2025,32,32,"2025-08-10","02:30:00","2025-08-10","06:30:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86A7-002","Bremen - Hannover","< >","Bremen Gabelung","Bremen Hbf",2025,2025,13,14,"2025-03-28","21:00:00","2025-03-31","14:00:00","2d, 16h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86C2-001","Magdeburg - Falkenberg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86C2-002","Hannover - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86C2-003","Magdeburg - Falkenberg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86C2-004","Hannover - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86C2-005","Magdeburg - Falkenberg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,32,33,"2025-08-10","06:30:00","2025-08-17","23:59:00","7d, 17h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","86D1-001","Hamburg - Magdeburg","< >","Süderelbbrücke","Hmb H Schaar Süd",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","16:00:00","0d, 16h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","86C2-006","Hannover - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2025,32,33,"2025-08-10","06:30:00","2025-08-17","23:59:00","7d, 17h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-13"]
[null,"DB InfraGO","86C2-007","Hannover - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-05"]
[null,"DB InfraGO","86C2-008","Magdeburg - Falkenberg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-05"]
[null,"DB InfraGO","87D2-001","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2025,2025,32,32,"2025-08-09","22:20:00","2025-08-10","02:00:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87D2-002","Hannover - Magdeburg","<","Helmstedt","Frellstedt",2025,2025,32,32,"2025-08-10","02:00:00","2025-08-10","06:00:00","0d, 4h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87D2-003","Hannover - Magdeburg","< >","Frellstedt","Helmstedt",2025,2025,32,32,"2025-08-10","05:00:00","2025-08-10","06:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-05"]
[null,"DB InfraGO","87D2-004","Hannover - Magdeburg",">","Schandelah","Königslutter",2025,2025,32,33,"2025-08-10","23:05:00","2025-08-11","02:20:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-05-23"]
[null,"DB InfraGO","87D2-005","Hannover - Magdeburg",">","Königslutter","Schandelah",2025,2025,33,33,"2025-08-11","02:20:00","2025-08-11","05:20:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-05-23"]
[null,"DB InfraGO","86D1-002","Hamburg - Magdeburg","< >","Hmb H Schaar Süd","Hamburg-Wilhelmsburg",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","16:00:00","0d, 16h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","86D1-003","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hmb Süd DB-Gr",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","16:00:00","0d, 16h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","86D1-004","Hamburg - Magdeburg","< >","Hmb Süd DB-Gr","Hamburg Süd",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","16:00:00","0d, 16h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","86D1-005","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hamburg Oberhafen",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","07:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","86D1-006","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hamburg Hbf",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","07:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","8817-001","Magdeburg - Falkenberg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,35,35,"2025-08-25","03:00:00","2025-08-25","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2022-12-16"]
[null,"DB InfraGO","8817-002","Hannover - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2025,35,35,"2025-08-25","03:00:00","2025-08-25","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2022-12-16"]
[null,"DB InfraGO","8817-003","Magdeburg - Falkenberg","<","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,35,38,"2025-08-25","08:00:00","2025-09-19","16:00:00","25d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","8817-004","Hannover - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2025,35,38,"2025-08-25","08:00:00","2025-09-19","16:00:00","25d, 8h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-001","Hannover - Magdeburg","<","Helmstedt","Königslutter",2025,2025,17,18,"2025-04-27","00:30:00","2025-04-28","05:10:00","1d, 4h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-002","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,18,23,"2025-04-28","06:00:00","2025-06-08","18:00:00","41d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-003","Hannover - Magdeburg","< >","Schandelah","Schandelah",2025,2025,18,23,"2025-04-28","06:00:00","2025-06-06","21:00:00","39d, 15h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-004","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2025,2025,18,23,"2025-04-28","06:00:00","2025-06-08","18:00:00","41d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-005","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2025,2025,18,23,"2025-04-28","06:00:00","2025-06-08","18:00:00","41d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-007","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,18,18,"2025-04-28","22:00:00","2025-05-02","06:00:00","3d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-008","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,18,20,"2025-05-02","21:00:00","2025-05-16","21:00:00","14d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-009","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,18,20,"2025-05-02","21:00:00","2025-05-16","21:00:00","14d, 0h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-010","Hannover - Magdeburg","<","Helmstedt","Königslutter",2025,2025,18,19,"2025-05-02","21:00:00","2025-05-05","06:10:00","2d, 9h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-011","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,18,19,"2025-05-02","21:00:00","2025-05-05","06:30:00","2d, 9h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-012","Hannover - Magdeburg",">","Braunschweig Hbf","Schandelah",2025,2025,18,20,"2025-05-02","23:10:00","2025-05-12","05:00:00","9d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-013","Hannover - Magdeburg","< >","Braunschweig-Buchhorst","Braunschweig Rbf",2025,2025,18,20,"2025-05-02","23:10:00","2025-05-12","05:00:00","9d, 5h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-014","Hannover - Magdeburg","< >","Schandelah","Braunschweig Schmiedekamp",2025,2025,18,20,"2025-05-02","23:10:00","2025-05-12","05:00:00","9d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-015","Hannover - Magdeburg","< >","Schandelah","Braunschweig Schmiedekamp",2025,2025,18,20,"2025-05-02","23:10:00","2025-05-16","21:00:00","13d, 21h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-016","Hannover - Magdeburg","< >","Schandelah","Braunschweig Schmiedekamp",2025,2025,18,19,"2025-05-02","23:40:00","2025-05-07","05:20:00","4d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO",0.88400000000000001,"Magdeburg - Falkenberg","< >","Magdeburg Hbf","Magdeburg-Buckau",2025,2025,38,38,"2025-09-20","08:00:00","2025-09-21","16:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO",8.8400000000000006E-2,"Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2025,2025,38,38,"2025-09-20","08:00:00","2025-09-21","16:00:00","1d, 8h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-017","Hannover - Magdeburg",">","Braunschweig-Buchhorst","Schandelah",2025,2025,20,20,"2025-05-12","05:00:00","2025-05-16","21:00:00","4d, 16h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-018","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2025,2025,20,20,"2025-05-12","05:00:00","2025-05-16","21:00:00","4d, 16h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-019","Hannover - Magdeburg","< >","Braunschweig Schmiedekamp","Braunschweig-Buchhorst",2025,2025,20,21,"2025-05-12","05:00:00","2025-05-19","06:00:00","7d, 1h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-020","Hannover - Magdeburg","< >","Braunschweig-Buchhorst","Weddel (Braunschw)",2025,2025,20,21,"2025-05-16","21:00:00","2025-05-23","21:00:00","7d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-021","Hannover - Magdeburg","< >","Königslutter","Königslutter",2025,2025,20,23,"2025-05-13","06:00:00","2025-06-06","21:00:00","24d, 15h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-022","Hannover - Magdeburg","< >","Helmstedt","Schandelah",2025,2025,20,23,"2025-05-16","22:00:00","2025-06-06","18:00:00","20d, 20h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-03-21"]
[null,"DB InfraGO","87F2-023","Hannover - Magdeburg","< >","Schandelah","Braunschweig Schmiedekamp",2025,2025,20,21,"2025-05-16","23:40:00","2025-05-20","05:20:00","3d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-024","Hannover - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2025,2025,20,21,"2025-05-16","23:40:00","2025-05-20","05:20:00","3d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-025","Hannover - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2025,2025,18,19,"2025-05-02","23:40:00","2025-05-07","05:20:00","4d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","87F2-026","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-08","21:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-03-21"]
[null,"DB InfraGO","87F2-027","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-08","21:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-03-21"]
[null,"DB InfraGO","87F2-028","Hannover - Magdeburg","< >","Königslutter","Königslutter",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-08","21:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-03-21"]
[null,"DB InfraGO","87F2-029","Hannover - Magdeburg","< >","Frellstedt","Königslutter",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-08","21:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-03-21"]
[null,"DB InfraGO","87F2-030","Hannover - Magdeburg","< >","Weddel (Braunschw)","Schandelah",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-08","21:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-03-21"]
[null,"DB InfraGO","887A-001","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,32,34,"2025-08-08","08:00:00","2025-08-18","20:00:00","10d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-002","Hannover - Magdeburg",">","Königslutter","Frellstedt",2025,2025,32,32,"2025-08-09","00:10:00","2025-08-09","05:55:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-003","Hannover - Magdeburg","< >","Königslutter","Frellstedt",2025,2025,32,32,"2025-08-09","00:10:00","2025-08-09","05:55:00","0d, 5h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-004","Hannover - Magdeburg","<","Frellstedt","Schandelah",2025,2025,32,32,"2025-08-09","23:25:00","2025-08-10","07:15:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-005","Hannover - Magdeburg","< >","Königslutter","Frellstedt",2025,2025,32,32,"2025-08-09","23:25:00","2025-08-10","07:15:00","0d, 7h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-006","Hannover - Magdeburg","< >","Schandelah","Braunschweig Schmiedekamp",2025,2025,32,33,"2025-08-10","21:25:00","2025-08-11","05:20:00","0d, 7h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-007","Hannover - Magdeburg",">","Braunschweig Hbf","Schandelah",2025,2025,32,33,"2025-08-10","21:25:00","2025-08-11","05:20:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-008","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig-Buchhorst",2025,2025,32,33,"2025-08-10","21:25:00","2025-08-11","05:20:00","0d, 7h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-009","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,33,33,"2025-08-15","22:00:00","2025-08-16","08:00:00","0d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-010","Hannover - Magdeburg","< >","Königslutter","Frellstedt",2025,2025,33,33,"2025-08-15","22:00:00","2025-08-16","08:00:00","0d, 10h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-011","Hannover - Magdeburg","<","Helmstedt","Königslutter",2025,2025,33,33,"2025-08-16","02:25:00","2025-08-16","04:25:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-012","Hannover - Magdeburg","< >","Königslutter","Frellstedt",2025,2025,33,33,"2025-08-16","02:25:00","2025-08-16","04:25:00","0d, 2h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-013","Hannover - Magdeburg","<","Helmstedt","Königslutter",2025,2025,33,33,"2025-08-16","23:55:00","2025-08-17","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-014","Hannover - Magdeburg","< >","Königslutter","Helmstedt",2025,2025,33,33,"2025-08-17","05:00:00","2025-08-17","06:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-015","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2025,2025,33,33,"2025-08-17","06:00:00","2025-08-17","08:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-016","Hannover - Magdeburg","< >","Frellstedt","Helmstedt",2025,2025,33,33,"2025-08-16","23:55:00","2025-08-17","06:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","887A-017","Hannover - Magdeburg","< >","Frellstedt","Helmstedt",2025,2025,33,33,"2025-08-17","05:00:00","2025-08-17","08:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2022-12-06"]
[null,"DB InfraGO","88A3-005","Dresden - Děčín","< >","Heidenau","Heidenau",2025,2025,22,33,"2025-06-01","23:30:00","2025-08-11","03:30:00","70d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-07"]
[null,"DB InfraGO","88D7-001","Hamburg - Magdeburg","<","Hmb H Schaar Süd","Süderelbbrücke",2025,2025,23,50,"2025-06-08","16:00:00","2025-12-13","23:59:00","188d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-03-11"]
[null,"DB InfraGO","887A-018","Hannover - Magdeburg","<","Frellstedt","Schandelah",2025,2025,33,34,"2025-08-17","21:45:00","2025-08-18","02:45:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO",8.8400000000000001E-6,"Magdeburg - Falkenberg","< >","Magdeburg Hbf","Magdeburg-Buckau",2025,2025,42,42,"2025-10-18","08:00:00","2025-10-19","16:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO",8.8400000000000003E-7,"Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2025,2025,42,42,"2025-10-18","08:00:00","2025-10-19","16:00:00","1d, 8h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","887A-019","Hannover - Magdeburg","< >","Königslutter","Frellstedt",2025,2025,34,34,"2025-08-18","02:45:00","2025-08-18","03:45:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","887A-020","Hannover - Magdeburg","< >","Königslutter","Frellstedt",2025,2025,33,34,"2025-08-17","21:45:00","2025-08-18","03:45:00","0d, 6h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88EB-001","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,33,36,"2025-08-16","01:00:00","2025-09-04","04:00:00","19d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88EB-002","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw S-B",2025,2025,32,33,"2025-08-04","01:00:00","2025-08-16","01:00:00","12d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","887A-021","Hannover - Magdeburg",">","Königslutter","Frellstedt",2025,2025,34,34,"2025-08-18","03:45:00","2025-08-18","05:45:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","887A-022","Hannover - Magdeburg","< >","Frellstedt","Königslutter",2025,2025,34,34,"2025-08-18","02:45:00","2025-08-18","05:45:00","0d, 3h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88F5-001","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,42,44,"2025-10-18","01:00:00","2025-10-27","04:00:00","9d, 4h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88F0-001","Bremen - Hannover","<","Bremen Hbf","Bremen Gabelung",2025,2025,14,14,"2025-03-31","23:59:00","2025-04-01","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88F5-002","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,45,46,"2025-11-07","22:00:00","2025-11-12","05:00:00","4d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88F5-003","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,45,46,"2025-11-07","22:00:00","2025-11-12","05:00:00","4d, 7h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","895C-001","Hannover - Magdeburg","< >","Schandelah","Schandelah",2025,2025,10,11,"2025-03-08","22:00:00","2025-03-10","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","895C-002","Hannover - Magdeburg",">","Braunschweig-Buchhorst","Schandelah",2025,2025,10,11,"2025-03-08","23:20:00","2025-03-10","05:20:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","895C-003","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2025,2025,10,11,"2025-03-08","23:20:00","2025-03-10","05:20:00","1d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8960-001","Hannover - Magdeburg","< >","Schandelah","Schandelah",2025,2025,11,12,"2025-03-15","22:00:00","2025-03-17","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8960-002","Hannover - Magdeburg","< >","Braunschweig-Buchhorst","Schandelah",2025,2025,11,12,"2025-03-15","23:35:00","2025-03-17","05:25:00","1d, 5h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8960-003","Hannover - Magdeburg","<","Schandelah","Braunschweig Schmiedekamp",2025,2025,11,12,"2025-03-15","23:35:00","2025-03-17","05:25:00","1d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8960-004","Hannover - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2025,2025,11,12,"2025-03-15","23:35:00","2025-03-17","05:25:00","1d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-008","Hannover - Magdeburg","< >","Braunschweig Schmiedekamp","Schandelah",2025,2025,20,21,"2025-05-16","23:40:00","2025-05-20","05:20:00","3d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-009","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2025,2025,20,21,"2025-05-16","23:40:00","2025-05-20","05:20:00","3d, 5h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-010","Hannover - Magdeburg","< >","Braunschweig-Buchhorst","Schandelah",2025,2025,22,22,"2025-05-26","23:35:00","2025-05-29","05:25:00","2d, 5h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-011","Hannover - Magdeburg","<","Schandelah","Braunschweig Schmiedekamp",2025,2025,22,22,"2025-05-26","23:35:00","2025-05-29","05:25:00","2d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-012","Hannover - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2025,2025,22,22,"2025-05-26","23:35:00","2025-05-29","05:25:00","2d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-013","Hannover - Magdeburg","< >","Braunschweig-Buchhorst","Schandelah",2025,2025,23,23,"2025-06-02","23:35:00","2025-06-06","05:25:00","3d, 5h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-014","Hannover - Magdeburg","<","Schandelah","Braunschweig Schmiedekamp",2025,2025,23,23,"2025-06-02","23:35:00","2025-06-06","05:25:00","3d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-015","Hannover - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2025,2025,23,23,"2025-06-02","23:35:00","2025-06-06","05:25:00","3d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8905-016","Hannover - Magdeburg","< >","Schandelah","Schandelah",2025,2025,23,23,"2025-06-05","22:00:00","2025-06-06","06:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88F5-004","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,46,50,"2025-11-12","05:00:00","2025-12-13","23:59:00","31d, 18h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88F5-005","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,46,50,"2025-11-12","05:00:00","2025-12-13","23:59:00","31d, 18h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88F0-005","Bremen - Hannover","<","Bremen Hbf","Bremen Gabelung",2025,2025,15,15,"2025-04-11","00:01:00","2025-04-11","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","8964-001","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,47,48,"2025-11-21","22:00:00","2025-11-26","09:00:00","4d, 11h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","8964-002","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,47,48,"2025-11-21","22:00:00","2025-11-26","09:00:00","4d, 11h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","8964-003","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,48,50,"2025-11-26","09:00:00","2025-12-13","23:59:00","17d, 14h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","8964-004","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,48,50,"2025-11-26","09:00:00","2025-12-13","23:59:00","17d, 14h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","898F-001","Hamburg - Magdeburg","< >","Hamburg-Wilhelmsburg","Hamburg-Harburg",2025,2025,50,50,"2025-12-12","22:00:00","2025-12-13","23:59:00","1d, 1h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","898F-002","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,50,50,"2025-12-12","22:00:00","2025-12-13","23:59:00","1d, 1h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88F0-008","Bremen - Hannover",">","Bremen Gabelung","Bremen Hbf",2025,2025,15,15,"2025-04-11","23:59:00","2025-04-12","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","898F-003","Hamburg - Magdeburg","< >","Süderelbbrücke","Hmb H Schaar Süd",2025,2025,50,50,"2025-12-12","22:00:00","2025-12-13","23:59:00","1d, 1h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","88F0-013","Bremen - Hannover",">","Bremen Gabelung","Bremen Hbf",2025,2025,17,17,"2025-04-22","00:01:00","2025-04-22","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-001","Hannover - Magdeburg","<","Peine Gbf","Hämelerwald",2025,2025,18,18,"2025-05-02","23:40:00","2025-05-03","05:30:00","0d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-002","Hannover - Magdeburg","< >","Peine","Peine",2025,2025,18,18,"2025-05-02","23:40:00","2025-05-03","05:30:00","0d, 5h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-003","Hannover - Magdeburg","<","Peine Gbf","Peine",2025,2025,18,21,"2025-05-03","21:10:00","2025-05-21","05:10:00","17d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-004","Hannover - Magdeburg","< >","Peine","Peine",2025,2025,18,21,"2025-05-03","21:10:00","2025-05-21","05:10:00","17d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-005","Hannover - Magdeburg","< >","Peine","Peine",2025,2025,18,21,"2025-05-03","21:10:00","2025-05-21","05:10:00","17d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-006","Hannover - Magdeburg","<","Peine Gbf","Hämelerwald",2025,2025,21,21,"2025-05-21","23:10:00","2025-05-22","05:10:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-007","Hannover - Magdeburg","< >","Peine","Peine",2025,2025,21,21,"2025-05-21","23:10:00","2025-05-22","05:10:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-008","Hannover - Magdeburg",">","Hämelerwald","Peine",2025,2025,21,23,"2025-05-22","21:45:00","2025-06-06","05:10:00","14d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-009","Hannover - Magdeburg","< >","Peine","Peine",2025,2025,21,23,"2025-05-22","21:45:00","2025-06-06","05:10:00","14d, 7h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89BB-010","Hannover - Magdeburg","< >","Peine","Peine",2025,2025,21,23,"2025-05-22","21:45:00","2025-06-06","05:10:00","14d, 7h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-07"]
[null,"DB InfraGO","89D3-010","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Geestgottberg",2025,2025,22,22,"2025-06-01","02:00:00","2025-06-01","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-04-05"]
[null,"DB InfraGO","89D3-011","Hamburg - Magdeburg","< >","Tangerhütte","Stendal Hauptbahnhof",2025,2025,22,22,"2025-06-01","02:00:00","2025-06-01","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-04-05"]
[null,"DB InfraGO","89D3-014","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Kläden (Kr Stendal) Hp",2025,2025,22,22,"2025-06-01","02:00:00","2025-06-01","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-04-05"]
[null,"DB InfraGO","89D3-015","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangermünde",2025,2025,22,22,"2025-06-01","02:00:00","2025-06-01","06:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-04-05"]
[null,"DB InfraGO","8A3E-001","Hannover - Magdeburg","< >","Peine","Hämelerwald",2025,2025,20,20,"2025-05-12","23:25:00","2025-05-14","05:10:00","1d, 5h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8A3E-002","Hannover - Magdeburg",">","Hämelerwald","Peine",2025,2025,20,20,"2025-05-12","23:25:00","2025-05-14","05:10:00","1d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8A3E-003","Hannover - Magdeburg","<","Peine Gbf","Hämelerwald",2025,2025,20,20,"2025-05-14","23:15:00","2025-05-16","05:10:00","1d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8A3E-004","Hannover - Magdeburg","< >","Hämelerwald","Peine",2025,2025,20,20,"2025-05-14","23:15:00","2025-05-16","05:10:00","1d, 5h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8A3E-005","Hannover - Magdeburg","< >","Hämelerwald","Peine",2025,2025,20,20,"2025-05-15","02:35:00","2025-05-16","04:35:00","1d, 2h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8A71-001","Rostock - Berlin","<","Neustrelitz Hbf","Oranienburg",2025,2025,16,18,"2025-04-18","23:00:00","2025-05-02","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","8A71-003","Rostock - Berlin","< >","Oranienburg","Neustrelitz Hbf",2025,2025,16,18,"2025-04-18","23:00:00","2025-05-02","05:00:00","13d, 6h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","8AF1-001","Hannover - Magdeburg",">","Brandenburg Hbf","Biederitz",2025,2025,18,18,"2025-04-28","21:00:00","2025-05-02","05:00:00","3d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2022-12-08"]
[null,"DB InfraGO","8BE9-001","Hannover - Magdeburg",">","Brandenburg Hbf","Biederitz",2025,2025,7,8,"2025-02-14","21:00:00","2025-02-21","05:00:00","6d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-09"]
[null,"DB InfraGO","8C00-001","Bremen - Hannover","<","Haste","Wunstorf",2025,2025,24,25,"2025-06-13","16:55:00","2025-06-18","04:55:00","4d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"Y",null,"2022-12-12"]
[null,"DB InfraGO","8C00-002","Bremen - Hannover","< >","Haste","Wunstorf",2025,2025,25,28,"2025-06-18","04:55:00","2025-07-10","08:55:00","22d, 4h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-12"]
[null,"DB InfraGO","8C00-004","Bremen - Hannover","<","Haste","Wunstorf",2025,2025,28,28,"2025-07-10","08:55:00","2025-07-12","21:00:00","2d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"Y",null,"2022-12-12"]
[null,"DB InfraGO","8C00-005","Bremen - Hannover","< >","Wunstorf","Haste",2025,2025,28,29,"2025-07-12","21:00:00","2025-07-14","04:55:00","1d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,6,7",null,"N",null,"2022-12-12"]
[null,"DB InfraGO","8C00-006","Bremen - Hannover","<","Haste","Wunstorf",2025,2025,29,31,"2025-07-14","04:55:00","2025-08-03","05:00:00","20d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-12"]
[null,"DB InfraGO","8A73-002","Rostock - Berlin","<","Neustrelitz Hbf","Oranienburg",2025,2025,40,42,"2025-10-03","21:00:00","2025-10-17","05:00:00","13d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","8A73-003","Rostock - Berlin","< >","Oranienburg","Neustrelitz Hbf",2025,2025,40,42,"2025-10-03","21:00:00","2025-10-17","05:00:00","13d, 8h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","8C00-007","Bremen - Hannover","< >","Wunstorf","Haste",2025,2025,29,31,"2025-07-14","04:55:00","2025-08-03","05:00:00","20d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-12"]
[null,"DB InfraGO","8C00-008","Bremen - Hannover","< >","Wunstorf","Haste",2025,2025,31,32,"2025-08-03","00:30:00","2025-08-04","04:25:00","1d, 3h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"Y",null,"2022-12-12"]
[null,"DB InfraGO","8CFE-001","Hamburg - Magdeburg",">","Glindenberg","Tangerhütte",2025,2025,39,40,"2025-09-25","21:30:00","2025-10-02","05:30:00","6d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","864C-004","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,19,23,"2025-05-10","00:00:00","2025-06-08","16:00:00","29d, 16h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88EB-003","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw S-B",2025,2025,33,36,"2025-08-16","01:00:00","2025-09-04","04:00:00","19d, 3h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88EB-004","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,32,33,"2025-08-04","01:00:00","2025-08-16","01:00:00","12d, 0h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88EB-005","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,32,33,"2025-08-04","01:00:00","2025-08-16","01:00:00","12d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88F5-008","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw",2025,2025,45,46,"2025-11-07","22:00:00","2025-11-12","05:00:00","4d, 7h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","8964-007","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,47,48,"2025-11-21","22:00:00","2025-11-26","09:00:00","4d, 11h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","8964-008","Hamburg - Magdeburg",">","Süderelbbrücke","Hamburg-Wilhelmsburg",2025,2025,47,48,"2025-11-21","22:00:00","2025-11-26","09:00:00","4d, 11h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-03-11"]
[null,"DB InfraGO","88F5-010","Hamburg - Magdeburg",">","Hamburg-Harburg","Hmb-Wlb Abzw S-B",2025,2025,42,44,"2025-10-18","01:00:00","2025-10-27","04:00:00","9d, 4h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-12"]
[null,"DB InfraGO","898F-004","Hamburg - Magdeburg","<","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,50,50,"2025-12-12","22:00:00","2025-12-13","23:59:00","1d, 1h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-12"]
[null,"DB InfraGO","8DFD-001","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2025,2025,28,29,"2025-07-11","22:00:00","2025-07-14","06:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2022-12-13"]
[null,"DB InfraGO","8E0B-001","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2025,2025,29,30,"2025-07-18","22:00:00","2025-07-21","06:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2022-12-13"]
[null,"DB InfraGO","8E0D-001","Berlin - Dresden","< >","Rangsdorf","Wünsdorf-Waldstadt",2025,2025,33,34,"2025-08-15","21:00:00","2025-08-18","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-02-16"]
[null,"DB InfraGO","8E86-001","Hannover - Magdeburg",">","Hannover Hbf","Braunschweig Hbf",2024,2025,51,50,"2024-12-16","23:00:00","2025-12-13","05:00:00","361d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"Y",null,"2022-12-13"]
[null,"DB InfraGO","8D93-001","Magdeburg - Falkenberg",">","Biederitz","Rodleben",2025,2025,17,19,"2025-04-25","21:00:00","2025-05-09","05:00:00","13d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-07-27"]
[null,"DB InfraGO","8E4C-001","Magdeburg - Falkenberg",">","Biederitz","Rodleben",2025,2025,45,46,"2025-11-07","21:00:00","2025-11-14","05:00:00","6d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","8D92-001","Magdeburg - Falkenberg",">","Biederitz","Rodleben",2025,2025,19,20,"2025-05-09","21:00:00","2025-05-16","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-13"]
[null,"DB InfraGO","8D92-002","Magdeburg - Falkenberg","< >","Biederitz","Rodleben",2025,2025,19,20,"2025-05-09","21:00:00","2025-05-16","05:00:00","6d, 8h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-13"]
[null,"DB InfraGO","9006-001","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,13,23,"2025-03-26","21:00:00","2025-06-06","05:00:00","71d, 7h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-16"]
[null,"DB InfraGO","8F99-002","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,16,17,"2025-04-16","21:00:00","2025-04-24","21:00:00","8d, 0h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","8F99-004","Rostock - Berlin","<","Nassenheide","Oranienburg",2025,2025,16,16,"2025-04-16","21:00:00","2025-04-17","01:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","8F99-005","Rostock - Berlin","< >","Nassenheide","Nassenheide",2025,2025,16,16,"2025-04-16","21:00:00","2025-04-17","01:00:00","0d, 4h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","8F99-006","Rostock - Berlin","<","Oranienburg","Birkenwerder Nord",2025,2025,16,16,"2025-04-17","01:00:00","2025-04-17","05:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","8F99-007","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,16,16,"2025-04-17","01:00:00","2025-04-17","05:00:00","0d, 4h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","8F99-008","Rostock - Berlin","< >","Nassenheide","Nassenheide",2025,2025,18,19,"2025-05-02","22:00:00","2025-05-10","05:30:00","7d, 7h","Periodical","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","8F99-009","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,18,19,"2025-05-02","22:00:00","2025-05-10","05:30:00","7d, 7h","Periodical","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","8F99-010","Rostock - Berlin","<","Nassenheide","Oranienburg",2025,2025,18,19,"2025-05-02","22:00:00","2025-05-10","05:30:00","7d, 7h","Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-04-26"]
[null,"DB InfraGO","8F99-011","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,19,23,"2025-05-10","21:00:00","2025-06-06","05:00:00","26d, 8h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","9007-001","Rostock - Berlin","< >","Nassenheide","Nassenheide",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","01:00:00","0d, 4h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","9007-002","Rostock - Berlin","<","Nassenheide","Oranienburg",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","01:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","9007-003","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,23,23,"2025-06-06","01:00:00","2025-06-06","05:00:00","0d, 4h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","9007-004","Rostock - Berlin","<","Oranienburg","Birkenwerder Nord",2025,2025,23,23,"2025-06-06","01:00:00","2025-06-06","05:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","9007-005","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,23,50,"2025-06-06","05:00:00","2025-12-13","23:59:00","190d, 19h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-14"]
[null,"DB InfraGO","8FE9-002","Rostock - Berlin","< >","Gransee","Fürstenberg (Havel)",2025,2025,20,22,"2025-05-16","23:00:00","2025-05-26","05:00:00","9d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","904A-001","Hamburg - Magdeburg","<","Glindenberg","Mg-Eichenw Üst",2025,2025,41,41,"2025-10-09","21:00:00","2025-10-12","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2022-12-14"]
[null,"DB InfraGO","904A-002","Hamburg - Magdeburg",">","Mg-Eichenw Üst","Glindenberg",2025,2025,41,41,"2025-10-06","21:00:00","2025-10-09","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-01-09"]
[null,"DB InfraGO","90E7-003","Hamburg - Magdeburg","< >","Buchholz (Nordheide)","Hamburg-Harburg",2025,2025,28,28,"2025-07-07","23:30:00","2025-07-10","04:30:00","2d, 5h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2023-09-05"]
[null,"DB InfraGO","9147-001","Rostock - Berlin","< >","Eichgestell Nord","Berlin Wendenheide",2025,2025,6,6,"2025-02-03","21:30:00","2025-02-04","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","9147-002","Rostock - Berlin","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,6,6,"2025-02-03","21:30:00","2025-02-04","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","9147-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,6,6,"2025-02-03","21:30:00","2025-02-04","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","9167-001","Rostock - Berlin","< >","Eichgestell Nord","Berlin Wendenheide",2025,2025,21,21,"2025-05-21","21:30:00","2025-05-22","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","9167-002","Rostock - Berlin","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,21,21,"2025-05-21","21:30:00","2025-05-22","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","9167-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,21,21,"2025-05-21","21:30:00","2025-05-22","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-04-13"]
[null,"DB InfraGO","9169-001","Rostock - Berlin","< >","Eichgestell Nord","Berlin Wendenheide",2025,2025,23,23,"2025-06-02","21:30:00","2025-06-03","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","9169-002","Rostock - Berlin","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,23,23,"2025-06-02","21:30:00","2025-06-03","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","9169-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,23,23,"2025-06-02","21:30:00","2025-06-03","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","916A-001","Rostock - Berlin","< >","Eichgestell Nord","Berlin Wendenheide",2025,2025,33,33,"2025-08-11","21:30:00","2025-08-12","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","916A-002","Rostock - Berlin","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,33,33,"2025-08-11","21:30:00","2025-08-12","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","916A-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,33,33,"2025-08-11","21:30:00","2025-08-12","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","916D-001","Rostock - Berlin","< >","Eichgestell Nord","Berlin Wendenheide",2025,2025,49,49,"2025-12-01","21:30:00","2025-12-02","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","916D-002","Rostock - Berlin","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,49,49,"2025-12-01","21:30:00","2025-12-02","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","916D-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,49,49,"2025-12-01","21:30:00","2025-12-02","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2022-12-15"]
[null,"DB InfraGO","8817-005","Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg Hbf",2025,2025,35,35,"2025-08-25","03:00:00","2025-08-25","04:00:00","0d, 1h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-12-16"]
[null,"DB InfraGO","92C6-003","Magdeburg - Falkenberg",">","Zahna","Lutherstadt Wittenberg Hbf",2025,2025,13,14,"2025-03-28","21:00:00","2025-04-02","05:00:00","4d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2022-12-17"]
[null,"DB InfraGO","92C6-005","Magdeburg - Falkenberg","<","Lutherstadt Wittenberg Hbf","Lutherstadt Wittenberg Hbf",2025,2025,13,14,"2025-03-28","21:00:00","2025-04-02","05:00:00","4d, 7h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2022-12-17"]
[null,"DB InfraGO","92C6-008","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Lutherstadt Wittenberg Hbf",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-28","05:00:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-12-17"]
[null,"DB InfraGO","92C6-009","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Lutherstadt Wittenberg Hbf",2025,2025,14,14,"2025-04-02","21:00:00","2025-04-04","05:00:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2022-12-17"]
[null,"DB InfraGO","94E9-002","Bremen - Hannover","< >","Hannover-Linden","Hannover-Linden",2025,2025,45,49,"2025-11-07","06:00:00","2025-12-05","20:00:00","28d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-001","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,17,18,"2025-04-25","23:00:00","2025-04-28","04:00:00","2d, 5h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-002","Bremen - Hannover","<","Langwedel","Verden (Aller)",2025,2025,18,18,"2025-04-28","04:00:00","2025-05-02","23:00:00","4d, 19h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-003","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,18,18,"2025-04-28","04:00:00","2025-05-02","23:00:00","4d, 19h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-004","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,18,18,"2025-04-28","04:00:00","2025-05-02","23:00:00","4d, 19h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-005","Bremen - Hannover","< >","Verden (Aller)","Walle (Kr Verden)",2025,2025,18,23,"2025-04-30","22:00:00","2025-06-02","04:00:00","32d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-20"]
[null,"DB InfraGO","94C7-006","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,18,19,"2025-05-02","23:00:00","2025-05-05","04:00:00","2d, 5h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-007","Bremen - Hannover",">","Verden (Aller)","Langwedel",2025,2025,19,19,"2025-05-05","04:00:00","2025-05-09","04:00:00","4d, 0h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-008","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,19,19,"2025-05-05","04:00:00","2025-05-09","04:00:00","4d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94C7-009","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,19,19,"2025-05-05","04:00:00","2025-05-09","04:00:00","4d, 0h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-20"]
[null,"DB InfraGO","94E3-001","Bremen - Hannover","<","Langwedel","Verden (Aller)",2025,2025,21,21,"2025-05-20","23:00:00","2025-05-23","23:00:00","3d, 0h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-002","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,21,21,"2025-05-20","23:00:00","2025-05-23","23:00:00","3d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-003","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,21,21,"2025-05-20","23:00:00","2025-05-23","23:00:00","3d, 0h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-004","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,21,21,"2025-05-23","00:00:00","2025-05-23","06:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-005","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,21,50,"2025-05-23","23:00:00","2025-12-13","23:59:00","204d, 1h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-006","Bremen - Hannover",">","Verden (Aller)","Langwedel",2025,2025,21,22,"2025-05-23","23:00:00","2025-05-27","05:00:00","3d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-007","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,21,22,"2025-05-23","23:00:00","2025-05-27","05:00:00","3d, 6h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-008","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,21,22,"2025-05-23","23:00:00","2025-05-27","05:00:00","3d, 6h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-009","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,22,22,"2025-05-26","00:00:00","2025-05-26","06:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","94E3-010","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,22,50,"2025-05-27","05:00:00","2025-12-12","23:59:00","199d, 19h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","9708-001","Bremen - Hannover","<","Empelde                           (Abzw)","Hannover-Linden",2025,2025,32,34,"2025-08-09","00:00:00","2025-08-22","21:40:00","13d, 21h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","9708-002","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,32,34,"2025-08-09","00:00:00","2025-08-22","21:40:00","13d, 21h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","970A-001","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,34,39,"2025-08-22","22:50:00","2025-09-26","04:40:00","34d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-004","Bremen - Hannover","< >","Hannover-Linden","Ronnenberg",2025,2025,43,44,"2025-10-26","22:50:00","2025-10-27","04:40:00","0d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-005","Bremen - Hannover","< >","Hannover-Linden Hafen","Empelde                           (Abzw)",2025,2025,43,44,"2025-10-26","22:50:00","2025-10-27","04:40:00","0d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-006","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,44,44,"2025-10-27","22:50:00","2025-10-30","04:40:00","2d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-007","Bremen - Hannover","<","Ronnenberg","Hannover-Linden",2025,2025,44,44,"2025-10-31","00:20:00","2025-10-31","03:20:00","0d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-008","Bremen - Hannover","<","Empelde                           (Abzw)","Hannover-Linden",2025,2025,44,46,"2025-10-31","00:20:00","2025-11-10","04:50:00","10d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-009","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,44,46,"2025-10-31","00:20:00","2025-11-10","04:50:00","10d, 4h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-010","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,44,46,"2025-10-31","00:20:00","2025-11-10","04:50:00","10d, 4h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-011","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,44,45,"2025-10-31","23:20:00","2025-11-03","04:40:00","2d, 5h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-012","Bremen - Hannover","< >","Wunstorf","Wunstorf",2025,2025,45,45,"2025-11-03","05:00:00","2025-11-07","19:00:00","4d, 14h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-013","Bremen - Hannover","<","Ronnenberg","Hannover-Linden",2025,2025,45,45,"2025-11-03","07:30:00","2025-11-03","19:30:00","0d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-014","Bremen - Hannover","<","Ronnenberg","Hannover-Linden",2025,2025,45,45,"2025-11-07","07:30:00","2025-11-07","15:30:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-015","Bremen - Hannover","<","Ronnenberg","Hannover-Linden",2025,2025,45,45,"2025-11-07","23:15:00","2025-11-08","05:10:00","0d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-016","Bremen - Hannover","< >","Hannover-Linden","Ronnenberg",2025,2025,45,46,"2025-11-09","22:50:00","2025-11-10","04:40:00","0d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-017","Bremen - Hannover","<","Ronnenberg","Hannover-Linden",2025,2025,46,46,"2025-11-10","01:40:00","2025-11-10","04:40:00","0d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-018","Bremen - Hannover","< >","Hannover-Linden Hafen","Empelde                           (Abzw)",2025,2025,45,46,"2025-11-09","22:50:00","2025-11-10","04:40:00","0d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-019","Bremen - Hannover","< >","Empelde","Hannover-Linden",2025,2025,46,46,"2025-11-10","04:50:00","2025-11-12","08:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","96B6-020","Bremen - Hannover","< >","Hannover-Linden","Empelde                           (Abzw)",2025,2025,46,46,"2025-11-10","22:50:00","2025-11-13","04:40:00","2d, 5h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2022-12-21"]
[null,"DB InfraGO","9817-001","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2024,2025,50,20,"2024-12-15","00:00:00","2025-05-12","04:25:00","148d, 3h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-22"]
[null,"DB InfraGO","9817-002","Bremen - Hannover","< >","Wunstorf","Poggenhagen",2024,2025,50,21,"2024-12-15","00:00:00","2025-05-19","04:30:00","155d, 3h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-22"]
[null,"DB InfraGO","9820-001","Bremen - Hannover","< >","Wunstorf","Neustadt a Rübenberge",2025,2025,17,21,"2025-04-24","22:00:00","2025-05-19","06:00:00","24d, 8h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-002","Bremen - Hannover","< >","Poggenhagen","Neustadt a Rübenberge",2025,2025,17,18,"2025-04-25","22:40:00","2025-04-28","04:25:00","2d, 5h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-003","Bremen - Hannover","<","Neustadt a Rübenberge","Wunstorf",2025,2025,17,18,"2025-04-25","22:40:00","2025-04-28","04:25:00","2d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-004","Bremen - Hannover","< >","Wunstorf","Neustadt a Rübenberge",2025,2025,17,17,"2025-04-26","21:05:00","2025-04-27","06:55:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-005","Bremen - Hannover","< >","Wunstorf","Neustadt a Rübenberge",2025,2025,17,18,"2025-04-27","23:05:00","2025-04-28","04:25:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-006","Bremen - Hannover","< >","Neustadt a Rübenberge","Poggenhagen",2025,2025,18,19,"2025-05-02","22:40:00","2025-05-05","04:30:00","2d, 5h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-007","Bremen - Hannover",">","Wunstorf","Neustadt a Rübenberge",2025,2025,18,19,"2025-05-02","22:40:00","2025-05-05","04:30:00","2d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-008","Bremen - Hannover","< >","Neustadt a Rübenberge","Wunstorf",2025,2025,18,18,"2025-05-03","21:05:00","2025-05-04","06:55:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-009","Bremen - Hannover","< >","Neustadt a Rübenberge","Wunstorf",2025,2025,18,19,"2025-05-04","23:05:00","2025-05-05","04:25:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-010","Bremen - Hannover","< >","Poggenhagen","Neustadt a Rübenberge",2025,2025,19,20,"2025-05-09","22:40:00","2025-05-12","04:25:00","2d, 5h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-011","Bremen - Hannover","< >","Wunstorf","Poggenhagen",2025,2025,19,20,"2025-05-09","22:40:00","2025-05-12","04:25:00","2d, 5h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-012","Bremen - Hannover","<","Neustadt a Rübenberge","Wunstorf",2025,2025,19,20,"2025-05-09","22:40:00","2025-05-12","04:25:00","2d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-013","Bremen - Hannover","< >","Wunstorf","Neustadt a Rübenberge",2025,2025,19,19,"2025-05-10","21:05:00","2025-05-11","06:55:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-014","Bremen - Hannover","< >","Wunstorf","Neustadt a Rübenberge",2025,2025,19,20,"2025-05-11","23:05:00","2025-05-12","04:25:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-015","Bremen - Hannover","< >","Neustadt a Rübenberge","Poggenhagen",2025,2025,20,21,"2025-05-16","22:40:00","2025-05-19","04:30:00","2d, 5h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-016","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2025,2025,20,21,"2025-05-16","22:40:00","2025-05-19","04:30:00","2d, 5h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-017","Bremen - Hannover",">","Wunstorf","Neustadt a Rübenberge",2025,2025,20,21,"2025-05-16","22:40:00","2025-05-19","04:30:00","2d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-018","Bremen - Hannover","< >","Neustadt a Rübenberge","Wunstorf",2025,2025,20,20,"2025-05-17","21:05:00","2025-05-18","06:55:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9820-019","Bremen - Hannover","< >","Neustadt a Rübenberge","Wunstorf",2025,2025,20,21,"2025-05-18","23:05:00","2025-05-19","04:25:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-12-23"]
[null,"DB InfraGO","9A1F-012","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2025,2025,26,27,"2025-06-29","22:00:00","2025-06-30","05:00:00","0d, 7h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2022-12-28"]
[null,"DB InfraGO","9A1F-013","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2025,2025,26,27,"2025-06-29","22:00:00","2025-06-30","05:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9A8B-001","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,17,17,"2025-04-22","21:15:00","2025-04-23","04:15:00","0d, 7h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9A8B-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,17,17,"2025-04-22","21:15:00","2025-04-23","04:15:00","0d, 7h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2022-12-29"]
[null,"DB InfraGO","9A8B-003","Dresden - Děčín","< >","Bad Schandau Gr","Schöna",2025,2025,17,21,"2025-04-23","04:15:00","2025-05-22","20:15:00","29d, 16h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9A8B-004","Dresden - Děčín",">","Bad Schandau Gr","Schöna",2025,2025,17,21,"2025-04-23","04:15:00","2025-05-22","20:15:00","29d, 16h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9A8B-005","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,17,21,"2025-04-26","00:15:00","2025-05-20","04:15:00","24d, 4h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,6,7",null,"N",null,"2022-12-29"]
[null,"DB InfraGO","9A8B-006","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,17,21,"2025-04-26","00:15:00","2025-05-20","04:15:00","24d, 4h","Periodical","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,6,7",null,"N",null,"2022-12-29"]
[null,"DB InfraGO","9A8B-007","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Gr",2025,2025,21,21,"2025-05-22","20:15:00","2025-05-25","04:15:00","2d, 8h","Periodical","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9A8B-008","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,21,21,"2025-05-22","20:15:00","2025-05-25","04:15:00","2d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5,6",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9A8B-009","Dresden - Děčín",">","Bad Schandau Gr","Schöna",2025,2025,21,21,"2025-05-23","04:15:00","2025-05-25","04:15:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2022-12-29"]
[null,"DB InfraGO","9A8B-010","Dresden - Děčín","<","Schöna","Bad Schandau Gr",2025,2025,21,21,"2025-05-23","04:15:00","2025-05-25","04:15:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2022-12-29"]
[null,"DB InfraGO","9ADD-003","Dresden - Děčín",">","Bad Schandau","Königst (Sä) Üst",2025,2025,21,22,"2025-05-25","21:00:00","2025-05-30","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9ADD-004","Dresden - Děčín","< >","Bad Schandau","Königst (Sä) Üst",2025,2025,21,24,"2025-05-25","21:00:00","2025-06-13","05:00:00","18d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9ADD-005","Dresden - Děčín","< >","Bad Schandau","Königst (Sä) Üst",2025,2025,21,24,"2025-05-25","21:00:00","2025-06-13","05:00:00","18d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9ADD-006","Dresden - Děčín",">","Bad Schandau","Königst (Sä) Üst",2025,2025,22,24,"2025-05-30","21:00:00","2025-06-10","05:00:00","10d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9ADD-007","Dresden - Děčín",">","Bad Schandau","Königst (Sä) Üst",2025,2025,24,24,"2025-06-10","21:00:00","2025-06-13","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9AF2-001","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9AF2-002","Dresden - Děčín","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9AF2-004","Dresden - Děčín","< >","Dolni Zleb","Bad Schandau Gr",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9AF2-005","Dresden - Děčín","< >","Pirna Gbf","Dürrröhrsdorf",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9AF2-006","Dresden - Děčín","< >","Dresden Hbf","Pirna",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9AF2-007","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9AF2-008","Dresden - Děčín","< >","Bad Schandau","Rathmannsdorf(P)",2025,2025,26,26,"2025-06-28","22:00:00","2025-06-29","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9B01-001","Dresden - Děčín",">","Schöna","Bad Schandau Ost",2025,2025,26,39,"2025-06-29","04:00:00","2025-09-24","22:00:00","87d, 18h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2022-12-30"]
[null,"DB InfraGO","9B01-002","Dresden - Děčín","< >","Schöna","Bad Schandau Ost",2025,2025,26,39,"2025-06-29","04:00:00","2025-09-24","22:00:00","87d, 18h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2022-12-30"]
[null,"DB InfraGO","9B01-003","Dresden - Děčín",">","Bad Schandau Ost","Bad Schandau",2025,2025,27,39,"2025-06-30","06:30:00","2025-09-24","07:30:00","86d, 1h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"Y",null,"2023-06-07"]
[null,"DB InfraGO","9B01-004","Dresden - Děčín",">","Bad Schandau Ost","Bad Schandau Ost",2025,2025,27,39,"2025-06-30","06:30:00","2025-09-24","07:30:00","86d, 1h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9B01-005","Dresden - Děčín",">","Bad Schandau Ost","Bad Schandau",2025,2025,27,39,"2025-06-30","16:30:00","2025-09-24","17:30:00","86d, 1h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"Y",null,"2023-06-07"]
[null,"DB InfraGO","9B01-006","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Ost",2025,2025,27,39,"2025-06-30","16:30:00","2025-09-24","17:30:00","86d, 1h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9B0D-001","Dresden - Děčín","< >","Bad Schandau","Schöna",2025,2025,26,27,"2025-06-29","08:50:00","2025-07-04","18:50:00","5d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9B0D-002","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,26,27,"2025-06-29","08:50:00","2025-07-04","18:50:00","5d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9B14-001","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,38,39,"2025-09-19","08:50:00","2025-09-24","18:50:00","5d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9B14-002","Dresden - Děčín","< >","Bad Schandau","Schöna",2025,2025,38,39,"2025-09-19","08:50:00","2025-09-24","18:50:00","5d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9BB6-001","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9BB6-002","Dresden - Děčín","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9BB6-004","Dresden - Děčín","< >","Bad Schandau Gr","Dolni Zleb",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9BB6-005","Dresden - Děčín","< >","Pirna Gbf","Dürrröhrsdorf",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9BB6-006","Dresden - Děčín","< >","Dresden Hbf","Pirna",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9BB6-007","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9BB6-008","Dresden - Děčín","< >","Bad Schandau","Rathmannsdorf(P)",2025,2025,39,39,"2025-09-24","22:00:00","2025-09-25","04:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-01-02"]
[null,"DB InfraGO","9BDB-001","Dresden - Děčín","<","Bad Schandau Ost","Schöna",2025,2025,39,45,"2025-09-25","04:00:00","2025-11-06","21:00:00","42d, 18h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-03"]
[null,"DB InfraGO","9BDB-002","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Ost",2025,2025,39,45,"2025-09-25","04:00:00","2025-11-06","21:00:00","42d, 18h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9BDB-003","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,39,45,"2025-09-25","04:00:00","2025-11-06","21:00:00","42d, 18h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-25"]
[null,"DB InfraGO","9BDB-004","Dresden - Děčín","<","Bad Schandau Ost","Schöna",2025,2025,39,45,"2025-09-25","04:00:00","2025-11-06","21:00:00","42d, 18h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9BDB-005","Dresden - Děčín","< >","Schöna","Bad Schandau Ost",2025,2025,39,45,"2025-09-25","04:00:00","2025-11-06","21:00:00","42d, 18h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9BDB-006","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,39,39,"2025-09-25","08:50:00","2025-09-26","18:50:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9BDB-007","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,39,39,"2025-09-25","08:50:00","2025-09-26","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9BDB-008","Dresden - Děčín","<","Bad Schandau","Bad Schandau Ost",2025,2025,39,44,"2025-09-25","06:30:00","2025-10-27","07:30:00","32d, 2h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"Y",null,"2023-01-02"]
[null,"DB InfraGO","9BDB-009","Dresden - Děčín","<","Bad Schandau","Bad Schandau Ost",2025,2025,39,44,"2025-09-25","16:30:00","2025-10-27","17:30:00","32d, 2h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"Y",null,"2023-01-02"]
[null,"DB InfraGO","9BF7-001","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,43,44,"2025-10-26","08:50:00","2025-10-27","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9BF7-002","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,43,44,"2025-10-26","08:50:00","2025-10-27","18:50:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9C41-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2025,2025,44,44,"2025-10-27","21:00:00","2025-11-01","21:00:00","5d, 0h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9C41-002","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,44,44,"2025-10-27","21:00:00","2025-11-01","21:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-04-19"]
[null,"DB InfraGO","9C41-003","Dresden - Děčín",">","Schöna","Schöna",2025,2025,44,44,"2025-10-27","21:00:00","2025-11-01","21:00:00","5d, 0h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C41-004","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,44,44,"2025-10-27","21:00:00","2025-11-01","21:00:00","5d, 0h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C41-005","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,44,45,"2025-11-02","04:00:00","2025-11-06","21:00:00","4d, 17h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C41-006","Dresden - Děčín","< >","Schöna","Bad Schandau",2025,2025,44,45,"2025-11-02","04:00:00","2025-11-06","21:00:00","4d, 17h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9C41-007","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,44,45,"2025-11-02","04:00:00","2025-11-06","21:00:00","4d, 17h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C41-008","Dresden - Děčín",">","Schöna","Schöna",2025,2025,44,45,"2025-11-02","04:00:00","2025-11-06","21:00:00","4d, 17h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C41-009","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,44,44,"2025-11-01","21:00:00","2025-11-02","04:00:00","0d, 7h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-04-19"]
[null,"DB InfraGO","9C41-011","Dresden - Děčín","< >","Bad Schandau Gr","Dolni Zleb",2025,2025,44,44,"2025-11-01","21:00:00","2025-11-02","04:00:00","0d, 7h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9C56-001","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C56-002","Dresden - Děčín","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C56-004","Dresden - Děčín","< >","Dolni Zleb","Bad Schandau Gr",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9C56-005","Dresden - Děčín","< >","Pirna Gbf","Dürrröhrsdorf",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C56-006","Dresden - Děčín","< >","Dresden Hbf","Pirna",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C56-007","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C56-008","Dresden - Děčín","< >","Bad Schandau","Rathmannsdorf(P)",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C67-001","Dresden - Děčín","<","Bad Schandau Ost","Schöna",2025,2025,45,46,"2025-11-07","04:00:00","2025-11-14","21:00:00","7d, 17h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-04-19"]
[null,"DB InfraGO","9C67-002","Dresden - Děčín","< >","Schöna","Bad Schandau Ost",2025,2025,45,46,"2025-11-07","04:00:00","2025-11-14","21:00:00","7d, 17h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-04-19"]
[null,"DB InfraGO","9C67-007","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,45,45,"2025-11-07","08:50:00","2025-11-08","18:50:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-04-19"]
[null,"DB InfraGO","9C67-008","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,45,45,"2025-11-07","08:50:00","2025-11-08","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9C67-009","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,46,46,"2025-11-13","08:50:00","2025-11-14","18:50:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-04-19"]
[null,"DB InfraGO","9C67-010","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,46,46,"2025-11-13","08:50:00","2025-11-14","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9C86-001","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C86-002","Dresden - Děčín","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C86-004","Dresden - Děčín","< >","Dolni Zleb","Bad Schandau Gr",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9C86-005","Dresden - Děčín","< >","Pirna Gbf","Dürrröhrsdorf",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C86-006","Dresden - Děčín","< >","Dresden Hbf","Pirna",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C86-007","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9C86-008","Dresden - Děčín","< >","Bad Schandau","Rathmannsdorf(P)",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CA3-001","Dresden - Děčín",">","Bad Schandau Ost","Schöna",2025,2025,46,49,"2025-11-15","04:00:00","2025-12-02","22:00:00","17d, 18h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-04-19"]
[null,"DB InfraGO","9CA3-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,46,49,"2025-11-15","04:00:00","2025-12-02","22:00:00","17d, 18h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9CA3-007","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,46,46,"2025-11-15","08:50:00","2025-11-16","18:50:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","94C1-001","Bremen - Hannover","<","Langwedel","Verden (Aller)",2025,2025,22,22,"2025-05-31","23:00:00","2025-06-01","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94C1-002","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,22,22,"2025-05-31","23:00:00","2025-06-01","05:00:00","0d, 6h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CA3-008","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,46,46,"2025-11-15","08:50:00","2025-11-16","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9CA3-009","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,49,49,"2025-12-01","08:50:00","2025-12-02","18:50:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9CA3-010","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,49,49,"2025-12-01","08:50:00","2025-12-02","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","9CE5-001","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-002","Dresden - Děčín","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-004","Dresden - Děčín","< >","Dolni Zleb","Bad Schandau Gr",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9CE5-005","Dresden - Děčín","< >","Pirna Gbf","Dürrröhrsdorf",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-006","Dresden - Děčín","< >","Dresden Hbf","Pirna",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-007","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-008","Dresden - Děčín","< >","Bad Schandau","Rathmannsdorf(P)",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-009","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,49,50,"2025-12-03","04:00:00","2025-12-10","14:00:00","7d, 10h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-010","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,49,50,"2025-12-03","04:00:00","2025-12-10","14:00:00","7d, 10h","Continuous","Signal",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94C1-003","Bremen - Hannover",">","Verden (Aller)","Langwedel",2025,2025,22,23,"2025-06-01","23:00:00","2025-06-02","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-011","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-012","Dresden - Děčín","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94C1-004","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,22,23,"2025-06-01","23:00:00","2025-06-02","05:00:00","0d, 6h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-014","Dresden - Děčín","< >","Dolni Zleb","Bad Schandau Gr",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","9CE5-015","Dresden - Děčín","< >","Pirna Gbf","Dürrröhrsdorf",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-016","Dresden - Děčín","< >","Dresden Hbf","Pirna",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-017","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94C1-005","Bremen - Hannover","< >","Verden (Aller)","Walle (Kr Verden)",2025,2025,23,23,"2025-06-02","23:00:00","2025-06-03","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9CE5-018","Dresden - Děčín","< >","Bad Schandau","Rathmannsdorf(P)",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94E5-001","Bremen - Hannover","<","Langwedel","Verden (Aller)",2025,2025,32,32,"2025-08-08","23:00:00","2025-08-09","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94E5-002","Bremen - Hannover","< >","Verden (Aller)","Langwedel",2025,2025,32,32,"2025-08-08","23:00:00","2025-08-09","05:00:00","0d, 6h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94E5-003","Bremen - Hannover",">","Verden (Aller)","Langwedel",2025,2025,32,32,"2025-08-09","23:00:00","2025-08-10","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94E5-004","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,32,32,"2025-08-09","23:00:00","2025-08-10","05:00:00","0d, 6h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","94E5-005","Bremen - Hannover","< >","Verden (Aller)","Walle (Kr Verden)",2025,2025,32,33,"2025-08-10","23:00:00","2025-08-11","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-01-03"]
[null,"DB InfraGO","9DDC-001","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,36,36,"2025-09-01","16:00:00","2025-09-03","04:00:00","1d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-003","Dresden - Děčín",">","Bad Schandau Gr","Schöna",2025,2025,36,36,"2025-09-01","20:00:00","2025-09-02","00:01:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-004","Dresden - Děčín",">","Schöna","Schöna",2025,2025,36,36,"2025-09-01","20:00:00","2025-09-02","00:01:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-005","Dresden - Děčín",">","Bad Schandau Gr","Schöna",2025,2025,36,36,"2025-09-01","20:00:00","2025-09-02","00:01:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-006","Dresden - Děčín","<","Schöna","Bad Schandau Gr",2025,2025,36,36,"2025-09-02","00:01:00","2025-09-02","04:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-007","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,36,36,"2025-09-02","00:01:00","2025-09-02","04:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-008","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,36,36,"2025-09-02","00:01:00","2025-09-02","04:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-009","Dresden - Děčín",">","Bad Schandau Gr","Schöna",2025,2025,36,36,"2025-09-02","20:00:00","2025-09-03","00:01:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-010","Dresden - Děčín",">","Schöna","Schöna",2025,2025,36,36,"2025-09-02","20:00:00","2025-09-03","00:01:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-011","Dresden - Děčín",">","Bad Schandau Gr","Schöna",2025,2025,36,36,"2025-09-02","20:00:00","2025-09-03","00:01:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-012","Dresden - Děčín","<","Schöna","Bad Schandau Gr",2025,2025,36,36,"2025-09-03","00:01:00","2025-09-03","04:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-013","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,36,36,"2025-09-03","00:01:00","2025-09-03","04:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DDC-014","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau Ost",2025,2025,36,36,"2025-09-03","00:01:00","2025-09-03","04:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-001","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,33,34,"2025-08-15","09:00:00","2025-08-24","10:00:00","9d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-003","Dresden - Děčín","< >","Rathmannsdorf(P)","Bad Schandau",2025,2025,34,34,"2025-08-18","01:00:00","2025-08-18","04:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-004","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-18","01:00:00","2025-08-18","04:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-005","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-18","01:00:00","2025-08-18","04:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-006","Dresden - Děčín","< >","Rathmannsdorf(P)","Bad Schandau",2025,2025,34,34,"2025-08-24","01:00:00","2025-08-24","04:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-007","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-24","01:00:00","2025-08-24","04:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-008","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-24","01:00:00","2025-08-24","04:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-009","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-18","04:00:00","2025-08-24","01:00:00","5d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-010","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-18","04:00:00","2025-08-24","01:00:00","5d, 21h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9DEC-011","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,34,34,"2025-08-18","04:00:00","2025-08-24","01:00:00","5d, 21h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9E34-001","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2024,2025,50,50,"2024-12-15","00:01:00","2025-12-13","23:59:00","363d, 23h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9E34-003","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2024,2025,50,50,"2024-12-15","00:01:00","2025-12-13","23:59:00","363d, 23h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-25"]
[null,"DB InfraGO","9E6A-001","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,17,17,"2025-04-21","06:00:00","2025-04-24","18:00:00","3d, 12h","Periodical","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9E6A-002","Bremen - Hannover","<","Bremen-Sebaldsbrück","Bremen-Mahndorf",2025,2025,17,17,"2025-04-25","00:00:00","2025-04-25","05:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9E6A-003","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,17,17,"2025-04-25","00:00:00","2025-04-25","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9E6A-004","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,17,17,"2025-04-25","00:00:00","2025-04-25","05:00:00","0d, 5h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9E6A-005","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,17,24,"2025-04-25","05:00:00","2025-06-14","00:00:00","49d, 19h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-04"]
[null,"DB InfraGO","9EEC-001","Dresden - Děčín",">","Pirna","Dresden Hbf",2024,2025,51,43,"2024-12-17","22:00:00","2025-10-22","04:00:00","308d, 5h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"Y",null,"2023-02-01"]
[null,"DB InfraGO","9EFB-001","Dresden - Děčín",">","Pirna Gbf","Dresden Hbf",2024,2025,51,43,"2024-12-16","22:00:00","2025-10-21","04:00:00","308d, 5h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"Y",null,"2023-02-01"]
[null,"DB InfraGO","9E6A-006","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,17,24,"2025-04-25","08:00:00","2025-06-13","20:00:00","49d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9E6A-007","Bremen - Hannover","<","Bremen-Sebaldsbrück","Bremen-Mahndorf",2025,2025,17,18,"2025-04-25","23:30:00","2025-05-03","05:30:00","7d, 6h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9E6A-008","Bremen - Hannover","<","Bremen-Sebaldsbrück","Bremen-Mahndorf",2025,2025,21,21,"2025-05-19","23:30:00","2025-05-23","05:30:00","3d, 6h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F5B-001","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,24,24,"2025-06-14","00:00:00","2025-06-14","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F5B-002","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,24,24,"2025-06-14","00:00:00","2025-06-14","05:00:00","0d, 5h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F5B-003","Bremen - Hannover","<","Bremen-Sebaldsbrück","Bremen-Mahndorf",2025,2025,24,24,"2025-06-14","00:00:00","2025-06-14","05:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F5B-004","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,25,25,"2025-06-16","06:00:00","2025-06-18","18:00:00","2d, 12h","Periodical","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F71-001","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,37,37,"2025-09-08","06:00:00","2025-09-10","18:00:00","2d, 12h","Periodical","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F71-002","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,38,38,"2025-09-16","07:00:00","2025-09-17","21:00:00","1d, 14h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F71-003","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,38,38,"2025-09-16","07:00:00","2025-09-17","21:00:00","1d, 14h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F71-004","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,38,38,"2025-09-18","07:00:00","2025-09-19","19:00:00","1d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9F71-005","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,38,38,"2025-09-18","07:00:00","2025-09-19","19:00:00","1d, 12h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","9FE0-001","Berlin - Dresden",">","Elsterwerda","Dresden-Friedrichstadt",2024,2025,51,37,"2024-12-17","23:30:00","2025-09-10","05:30:00","266d, 5h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"Y",null,"2023-02-02"]
[null,"DB InfraGO","A016-001","Falkenberg - Dresden",">","Leckwitz","Coswig (bei Dresden)",2024,2025,51,37,"2024-12-18","23:00:00","2025-09-11","05:00:00","266d, 5h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"Y",null,"2023-02-02"]
[null,"DB InfraGO","A027-001","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,28,38,"2025-07-10","22:00:00","2025-09-20","06:00:00","71d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"Y",null,"2023-01-05"]
[null,"DB InfraGO","A027-002","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,28,38,"2025-07-10","22:00:00","2025-09-20","06:00:00","71d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","A027-004","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,28,38,"2025-07-10","14:00:00","2025-09-20","05:00:00","71d, 15h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"Y",null,"2023-01-05"]
[null,"DB InfraGO","A027-005","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,28,38,"2025-07-10","14:00:00","2025-09-20","05:00:00","71d, 15h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-05"]
[null,"DB InfraGO","A1F0-001","Bremen - Hannover",">","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,22,23,"2025-05-27","23:30:00","2025-06-07","04:30:00","10d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A1F0-002","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,22,23,"2025-05-27","23:30:00","2025-06-07","04:30:00","10d, 5h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A1F0-003","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,23,23,"2025-06-02","06:00:00","2025-06-06","18:00:00","4d, 12h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A1F0-004","Bremen - Hannover",">","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,23,23,"2025-06-02","06:00:00","2025-06-06","18:00:00","4d, 12h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-005","Bremen - Hannover","< >","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2025,2025,23,25,"2025-06-07","18:00:00","2025-06-21","12:00:00","13d, 18h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-006","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,23,25,"2025-06-07","23:00:00","2025-06-21","05:30:00","13d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-007","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,23,25,"2025-06-07","23:00:00","2025-06-21","05:30:00","13d, 6h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-008","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,23,24,"2025-06-07","23:00:00","2025-06-10","00:00:00","2d, 1h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-009","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","02:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-010","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,23,23,"2025-06-08","03:00:00","2025-06-08","04:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-011","Bremen - Hannover","<","Lübberstedt","Bremen-Burg",2025,2025,23,23,"2025-06-08","02:00:00","2025-06-08","03:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-012","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,23,23,"2025-06-08","13:30:00","2025-06-08","14:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-013","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,24,24,"2025-06-09","00:00:00","2025-06-09","03:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-014","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,24,24,"2025-06-10","00:00:00","2025-06-10","04:30:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-015","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,24,24,"2025-06-10","00:00:00","2025-06-13","04:30:00","3d, 4h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-016","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,24,24,"2025-06-13","03:00:00","2025-06-13","04:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-017","Bremen - Hannover","<","Lübberstedt","Bremen-Burg",2025,2025,24,24,"2025-06-13","00:00:00","2025-06-13","03:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-018","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,24,25,"2025-06-13","04:30:00","2025-06-19","01:00:00","5d, 20h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-019","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,24,24,"2025-06-14","00:00:00","2025-06-14","04:30:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-020","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,24,24,"2025-06-15","00:00:00","2025-06-15","04:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-021","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,25,25,"2025-06-16","00:00:00","2025-06-16","04:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-022","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-17","04:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-023","Bremen - Hannover","<","Lübberstedt","Bremen-Burg",2025,2025,25,25,"2025-06-18","00:00:00","2025-06-18","02:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-024","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,25,25,"2025-06-18","02:00:00","2025-06-18","04:30:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-025","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,25,25,"2025-06-18","13:00:00","2025-06-18","14:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-026","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,25,25,"2025-06-18","22:00:00","2025-06-19","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-027","Bremen - Hannover","< >","Bremen-Burg","Oldenbüttel",2025,2025,25,25,"2025-06-19","01:00:00","2025-06-19","04:30:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-028","Bremen - Hannover","< >","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,25,25,"2025-06-19","04:30:00","2025-06-19","23:00:00","0d, 18h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2023-01-10"]
[null,"DB InfraGO","A00F-029","Bremen - Hannover","< >","Osterholz-Scharmbeck","Lübberstedt",2025,2025,25,25,"2025-06-19","23:00:00","2025-06-20","02:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-030","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,25,25,"2025-06-20","03:00:00","2025-06-20","05:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-031","Bremen - Hannover","<","Lübberstedt","Bremen-Burg",2025,2025,25,25,"2025-06-20","02:00:00","2025-06-20","03:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-032","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,25,25,"2025-06-20","02:00:00","2025-06-21","05:30:00","1d, 3h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-10"]
[null,"DB InfraGO","A00F-033","Bremen - Hannover","<","Lübberstedt","Bremen-Burg",2025,2025,25,25,"2025-06-21","00:00:00","2025-06-21","02:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A00F-034","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,25,25,"2025-06-21","02:00:00","2025-06-21","03:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-035","Bremen - Hannover","< >","Bremen-Burg","Lübberstedt",2025,2025,25,25,"2025-06-21","03:30:00","2025-06-21","05:30:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-036","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,25,25,"2025-06-21","05:30:00","2025-06-22","18:00:00","1d, 12h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A00F-037","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,25,26,"2025-06-22","18:00:00","2025-06-24","18:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","A1F1-001","Bremen - Hannover",">","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,25,27,"2025-06-21","23:30:00","2025-07-02","04:30:00","10d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A1F1-002","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,26,27,"2025-06-24","23:30:00","2025-07-02","04:30:00","7d, 5h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A1F1-003","Bremen - Hannover",">","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,26,26,"2025-06-23","06:00:00","2025-06-27","18:00:00","4d, 12h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A1F1-004","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,26,26,"2025-06-25","06:00:00","2025-06-27","18:00:00","2d, 12h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-07"]
[null,"DB InfraGO","A022-001","Bremen - Hannover",">","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,41,41,"2025-10-06","06:00:00","2025-10-10","18:00:00","4d, 12h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-002","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,41,41,"2025-10-06","06:00:00","2025-10-10","18:00:00","4d, 12h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-003","Bremen - Hannover","< >","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2025,2025,41,42,"2025-10-11","12:00:00","2025-10-13","12:00:00","2d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-004","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,41,41,"2025-10-11","22:30:00","2025-10-11","23:00:00","0d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-005","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,41,41,"2025-10-11","22:30:00","2025-10-12","07:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-006","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,41,41,"2025-10-11","23:00:00","2025-10-12","01:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-007","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,41,41,"2025-10-12","01:00:00","2025-10-12","07:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-10"]
[null,"DB InfraGO","A022-008","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,41,42,"2025-10-12","22:30:00","2025-10-13","02:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-009","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,42,42,"2025-10-13","04:00:00","2025-10-13","05:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-010","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,42,42,"2025-10-13","02:00:00","2025-10-13","04:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-011","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,41,42,"2025-10-12","22:30:00","2025-10-13","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-012","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,42,42,"2025-10-18","22:30:00","2025-10-18","23:00:00","0d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-013","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,42,42,"2025-10-18","23:00:00","2025-10-19","01:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-014","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,42,42,"2025-10-19","01:00:00","2025-10-19","07:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-015","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,42,42,"2025-10-18","22:30:00","2025-10-19","07:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-016","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,42,43,"2025-10-19","22:30:00","2025-10-20","02:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-017","Bremen - Hannover","<","Lübberstedt","Osterholz-Scharmbeck",2025,2025,43,43,"2025-10-20","02:00:00","2025-10-20","04:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-018","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2025,2025,43,43,"2025-10-20","04:00:00","2025-10-20","05:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A022-019","Bremen - Hannover","< >","Osterholz-Scharmbeck","Oldenbüttel",2025,2025,42,43,"2025-10-19","22:30:00","2025-10-20","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-08"]
[null,"DB InfraGO","A27E-001","Bremen - Hannover",">","Wunstorf","Bremen Hbf",2025,2025,18,22,"2025-04-28","23:00:00","2025-05-30","05:00:00","31d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-09"]
[null,"DB InfraGO","A38A-001","Hamburg - Magdeburg",">","Celle","Hamburg-Harburg",2025,2025,7,9,"2025-02-14","23:00:00","2025-02-28","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-10"]
[null,"DB InfraGO","A38B-001","Hamburg - Magdeburg",">","Hamburg-Harburg","Stade",2025,2025,31,33,"2025-08-01","23:00:00","2025-08-15","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-10"]
[null,"DB InfraGO","A38A-002","Hamburg - Magdeburg",">","Lehrte Nord","Celle",2025,2025,7,9,"2025-02-14","23:00:00","2025-02-28","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-10"]
[null,"DB InfraGO","A633-001","Bremen - Hannover","<","Misburg","Misburg",2025,2025,18,19,"2025-04-30","09:00:00","2025-05-07","16:55:00","7d, 7h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-002","Bremen - Hannover","< >","Misburg","Misburg",2025,2025,18,19,"2025-04-30","09:00:00","2025-05-07","16:55:00","7d, 7h","Periodical","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-003","Bremen - Hannover","<","Misburg","Hannover-Waldheim",2025,2025,18,18,"2025-04-30","09:00:00","2025-04-30","15:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-004","Bremen - Hannover","<","Misburg","Misburg",2025,2025,20,21,"2025-05-15","09:00:00","2025-05-21","16:55:00","6d, 7h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-005","Bremen - Hannover","< >","Misburg","Misburg",2025,2025,20,21,"2025-05-15","09:00:00","2025-05-21","16:55:00","6d, 7h","Periodical","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-006","Bremen - Hannover","<","Misburg","Misburg",2025,2025,22,23,"2025-05-29","09:00:00","2025-06-06","16:55:00","8d, 7h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-007","Bremen - Hannover","< >","Misburg","Misburg",2025,2025,22,23,"2025-05-29","09:00:00","2025-06-06","16:55:00","8d, 7h","Periodical","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A633-008","Bremen - Hannover","<","Misburg","Hannover-Waldheim",2025,2025,23,23,"2025-06-06","11:00:00","2025-06-06","16:55:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-02-24"]
[null,"DB InfraGO","A4CE-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2025,2025,22,22,"2025-06-01","14:00:00","2025-06-01","18:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2025,2025,22,24,"2025-06-01","14:00:00","2025-06-13","15:00:00","12d, 1h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2025,2025,22,24,"2025-06-01","14:00:00","2025-06-13","15:00:00","12d, 1h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-004","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,23,23,"2025-06-05","00:00:00","2025-06-05","04:00:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-005","Bremen - Hannover","< >","Bremen Hbf ehem Bwn","Bremen Hbf",2025,2025,23,23,"2025-06-05","00:00:00","2025-06-05","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-006","Bremen - Hannover","< >","Bremen Hbf ehem Bwn","Bremen Hbf",2025,2025,23,24,"2025-06-06","00:00:00","2025-06-13","15:00:00","7d, 15h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-007","Wilhelmshaven - Bremen","< >","Bremen Hbf ehem Bwn","Bremen Hbf",2025,2025,23,24,"2025-06-06","00:00:00","2025-06-13","15:00:00","7d, 15h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-008","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,23,23,"2025-06-07","00:00:00","2025-06-07","04:00:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-009","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,24,24,"2025-06-10","00:00:00","2025-06-11","04:00:00","1d, 4h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-010","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,24,24,"2025-06-11","15:00:00","2025-06-11","16:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-011","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,24,24,"2025-06-11","20:00:00","2025-06-11","21:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-11"]
[null,"DB InfraGO","A4CE-012","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Bremen Hbf",2025,2025,24,24,"2025-06-12","00:00:00","2025-06-12","03:00:00","0d, 3h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-013","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,24,24,"2025-06-12","03:00:00","2025-06-12","05:30:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-014","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,24,24,"2025-06-13","00:00:00","2025-06-13","04:00:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-015","Bremen - Hannover","< >","Bremen Hbf ehem Bwn","Bremen Hbf",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-17","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4CE-016","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-17","04:00:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4C7-001","Bremen - Hannover","< >","Bremen Hbf ehem Bwn","Bremen Hbf",2025,2025,32,32,"2025-08-09","21:00:00","2025-08-10","05:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4C7-002","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,32,32,"2025-08-10","02:00:00","2025-08-10","04:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4C7-003","Bremen - Hannover","< >","Bremen Hbf ehem Bwn","Bremen Hbf",2025,2025,32,33,"2025-08-10","22:30:00","2025-08-11","05:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A4C7-004","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,32,33,"2025-08-10","23:00:00","2025-08-11","01:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A726-002","Bremen - Hannover","< >","Lehrte West","Lehrte West",2025,2025,26,32,"2025-06-27","06:00:00","2025-08-08","06:00:00","42d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A822-004","Hannover - Magdeburg",">","Hildesheim Hbf","Groß Gleidingen",2025,2025,32,32,"2025-08-08","23:30:00","2025-08-09","02:30:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-12"]
[null,"DB InfraGO","A87B-001","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,23,"2025-04-28","05:00:00","2025-06-02","05:00:00","35d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-002","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,23,"2025-04-28","05:00:00","2025-06-02","05:00:00","35d, 0h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,23,"2025-04-28","05:00:00","2025-06-02","05:00:00","35d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-004","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,23,"2025-04-28","05:00:00","2025-06-02","05:00:00","35d, 0h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-005","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-04","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-007","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-04","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-008","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-04","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-009","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-04","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-010","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,18,"2025-05-01","23:30:00","2025-05-04","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-012","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,18,18,"2025-05-01","23:30:00","2025-05-04","04:30:00","2d, 5h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-013","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,20,"2025-05-08","21:00:00","2025-05-17","05:00:00","8d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-015","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,20,"2025-05-08","21:00:00","2025-05-17","05:00:00","8d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-016","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,20,"2025-05-08","21:00:00","2025-05-17","05:00:00","8d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-017","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,20,"2025-05-08","21:00:00","2025-05-17","05:00:00","8d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-018","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-24","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-020","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-24","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-021","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-24","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-022","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-24","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-023","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,21,"2025-05-21","23:30:00","2025-05-24","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-025","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,21,"2025-05-21","23:30:00","2025-05-24","04:30:00","2d, 5h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-026","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,22,"2025-05-24","07:00:00","2025-05-28","20:00:00","4d, 13h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A87B-027","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,21,22,"2025-05-24","07:00:00","2025-05-28","20:00:00","4d, 13h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-001","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,22,22,"2025-05-29","07:00:00","2025-06-01","20:00:00","3d, 13h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-003","Dresden - Děčín",">","Dresden Hbf","Dresden Hbf",2025,2025,22,22,"2025-05-29","07:00:00","2025-06-01","20:00:00","3d, 13h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-004","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,28,"2025-06-02","05:00:00","2025-07-07","05:00:00","35d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A89D-006","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,28,"2025-06-02","05:00:00","2025-07-07","05:00:00","35d, 0h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-007","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,28,"2025-06-02","05:00:00","2025-07-07","05:00:00","35d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-008","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,28,"2025-06-02","05:00:00","2025-07-07","05:00:00","35d, 0h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-009","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","20:00:00","2025-06-07","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-011","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","20:00:00","2025-06-07","04:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-012","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","20:00:00","2025-06-07","04:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-014","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","20:00:00","2025-06-07","04:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-015","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","23:00:00","2025-06-07","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-017","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","23:00:00","2025-06-07","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-019","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,23,23,"2025-06-04","23:00:00","2025-06-07","04:30:00","2d, 5h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-020","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,24,26,"2025-06-11","20:00:00","2025-06-27","04:00:00","15d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-022","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,24,26,"2025-06-11","20:00:00","2025-06-27","04:00:00","15d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-023","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,24,26,"2025-06-11","20:00:00","2025-06-27","04:00:00","15d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-03-08"]
[null,"DB InfraGO","A89D-025","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,24,26,"2025-06-11","20:00:00","2025-06-27","04:00:00","15d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-03-08"]
[null,"DB InfraGO","A89D-026","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","20:00:00","2025-07-05","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-028","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","20:00:00","2025-07-05","04:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-029","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","20:00:00","2025-07-05","04:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-03-08"]
[null,"DB InfraGO","A89D-031","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","20:00:00","2025-07-05","04:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-03-08"]
[null,"DB InfraGO","A89D-032","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","23:00:00","2025-07-05","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-034","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","23:00:00","2025-07-05","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A89D-036","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,27,27,"2025-07-02","23:00:00","2025-07-05","04:30:00","2d, 5h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-001","Dresden - Děčín",">","Dresden Hbf","Dresden Hbf",2025,2025,28,39,"2025-07-07","04:00:00","2025-09-22","04:00:00","77d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-003","Dresden - Děčín",">","Dresden Hbf","Dresden Hbf",2025,2025,28,39,"2025-07-07","04:00:00","2025-09-22","04:00:00","77d, 0h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DB-001","Hannover - Magdeburg",">","Hannover Hbf","Braunschweig Hbf",2025,2025,18,20,"2025-05-02","23:00:00","2025-05-16","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-004","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,28,30,"2025-07-09","20:00:00","2025-07-26","04:00:00","16d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-006","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,28,30,"2025-07-09","20:00:00","2025-07-26","04:00:00","16d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-007","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,28,30,"2025-07-09","20:00:00","2025-07-26","04:00:00","16d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-009","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,28,30,"2025-07-09","20:00:00","2025-07-26","04:00:00","16d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-010","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,28,30,"2025-07-09","20:00:00","2025-07-26","04:00:00","16d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-011","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,28,30,"2025-07-09","20:00:00","2025-07-26","04:00:00","16d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A8DF-015","Dresden - Děčín","<","Dresden Hbf","Dresden Hbf",2025,2025,40,40,"2025-09-29","20:00:00","2025-10-04","04:00:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-017","Dresden - Děčín","<","Dresden Hbf","Dresden Hbf",2025,2025,40,40,"2025-09-29","20:00:00","2025-10-04","04:00:00","4d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-018","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,40,40,"2025-09-29","20:00:00","2025-10-04","04:00:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-019","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,40,40,"2025-09-29","20:00:00","2025-10-04","04:00:00","4d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-020","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,40,41,"2025-10-04","20:30:00","2025-10-07","04:30:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-022","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,40,41,"2025-10-04","20:30:00","2025-10-07","04:30:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-023","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,41,"2025-10-07","20:30:00","2025-10-12","04:30:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-025","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,41,"2025-10-07","20:30:00","2025-10-12","04:30:00","4d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-026","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,41,"2025-10-07","20:30:00","2025-10-12","04:30:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-027","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,41,"2025-10-07","20:30:00","2025-10-12","04:30:00","4d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-028","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,42,"2025-10-12","20:30:00","2025-10-15","04:30:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-030","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,42,"2025-10-12","20:30:00","2025-10-15","04:30:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-031","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,42,"2025-10-12","20:30:00","2025-10-15","04:30:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-032","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,42,"2025-10-15","20:30:00","2025-10-18","04:30:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-034","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,42,"2025-10-15","20:30:00","2025-10-18","04:30:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-035","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,42,"2025-10-15","20:30:00","2025-10-18","04:30:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-036","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,44,"2025-10-18","20:30:00","2025-10-28","04:30:00","9d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-038","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,44,"2025-10-18","20:30:00","2025-10-28","04:30:00","9d, 9h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-039","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,44,44,"2025-10-28","20:30:00","2025-11-02","04:30:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-040","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,44,44,"2025-10-28","20:30:00","2025-11-02","04:30:00","4d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-041","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,44,44,"2025-10-28","20:30:00","2025-11-02","04:30:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A8DF-042","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,44,44,"2025-10-28","20:30:00","2025-11-02","04:30:00","4d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-19"]
[null,"DB InfraGO","A978-001","Hannover - Magdeburg",">","Oebisfelde","Lehrte",2025,2025,8,10,"2025-02-21","23:00:00","2025-03-07","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A993-001","Hamburg - Magdeburg",">","Buchholz (Nordheide)","Meckelfeld",2025,2025,6,7,"2025-02-07","23:00:00","2025-02-14","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-13"]
[null,"DB InfraGO","A9E0-001","Bremen - Hannover",">","Hannover-Waldheim","Lehrte Bahnhofsteil Ahlten",2025,2025,7,8,"2025-02-14","23:00:00","2025-02-21","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A9E4-001","Bremen - Hannover",">","Hannover-Waldheim","Lehrte Bahnhofsteil Ahlten",2025,2025,47,48,"2025-11-21","23:00:00","2025-11-28","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A9E7-001","Bremen - Hannover",">","Seelze Ost","Hannover-Waldheim",2025,2025,9,11,"2025-02-28","23:00:00","2025-03-14","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AA1E-001","Berlin - Dresden",">","Luckau-Uckro","Luckau-Uckro",2025,2025,10,12,"2025-03-07","22:00:00","2025-03-21","22:00:00","14d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-25"]
[null,"DB InfraGO","AA1E-002","Berlin - Dresden",">","Golßen (Niederlausitz)","Walddrehna",2025,2025,10,10,"2025-03-07","22:00:00","2025-03-08","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A864-001","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,44,50,"2025-11-01","00:00:00","2025-12-13","23:59:00","42d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-16"]
[null,"DB InfraGO","A864-002","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,44,50,"2025-11-01","00:00:00","2025-12-13","23:59:00","42d, 23h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A864-003","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,44,50,"2025-11-01","00:00:00","2025-12-13","23:59:00","42d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AA1E-003","Berlin - Dresden","< >","Luckau-Uckro","Luckau-Uckro",2025,2025,10,12,"2025-03-08","05:00:00","2025-03-21","22:00:00","13d, 17h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AA1E-004","Berlin - Dresden",">","Golßen (Niederlausitz)","Walddrehna",2025,2025,10,12,"2025-03-08","21:00:00","2025-03-21","05:00:00","12d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AA7F-001","Hannover - Magdeburg",">","Braunschweig Hbf","Helmstedt",2025,2025,18,20,"2025-05-02","23:00:00","2025-05-16","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A8E5-001","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2025,2025,46,50,"2025-11-16","08:00:00","2025-12-12","16:00:00","26d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A8E5-002","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2025,2025,46,50,"2025-11-16","08:00:00","2025-12-12","16:00:00","26d, 8h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A8E5-003","Wilhelmshaven - Bremen","<","Delmenhorst Df","Delmenhorst",2025,2025,47,48,"2025-11-17","00:01:00","2025-11-29","05:00:00","12d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A864-009","Magdeburg - Falkenberg",">","Medewitz (Mark)","Meinsdorf",2025,2025,45,45,"2025-11-03","21:00:00","2025-11-05","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A864-010","Magdeburg - Falkenberg","<","Meinsdorf","Medewitz (Mark)",2025,2025,45,45,"2025-11-05","21:00:00","2025-11-07","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AB3F-001","Berlin - Dresden",">","Luckau-Uckro","Luckau-Uckro",2025,2025,12,14,"2025-03-21","22:00:00","2025-04-04","22:00:00","13d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AB3F-002","Berlin - Dresden","<","Walddrehna","Golßen (Niederlausitz)",2025,2025,12,12,"2025-03-21","22:00:00","2025-03-22","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AB3F-003","Berlin - Dresden","< >","Luckau-Uckro","Luckau-Uckro",2025,2025,12,14,"2025-03-22","05:00:00","2025-04-04","22:00:00","13d, 16h","Periodical","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","AB3F-004","Berlin - Dresden","<","Walddrehna","Golßen (Niederlausitz)",2025,2025,12,14,"2025-03-22","21:00:00","2025-04-04","05:00:00","12d, 7h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-16"]
[null,"DB InfraGO","A861-001","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,27,37,"2025-07-01","00:00:00","2025-09-08","23:59:00","69d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-17"]
[null,"DB InfraGO","A861-002","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,27,37,"2025-07-01","00:00:00","2025-09-08","23:59:00","69d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-003","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,27,37,"2025-07-01","00:00:00","2025-09-08","23:59:00","69d, 23h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-005","Wilhelmshaven - Bremen","<","Delmenhorst Df","Delmenhorst",2025,2025,47,48,"2025-11-17","00:01:00","2025-11-29","05:00:00","12d, 4h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-006","Wilhelmshaven - Bremen","< >","Delmenhorst","Delmenhorst Df",2025,2025,47,48,"2025-11-17","00:01:00","2025-11-29","05:00:00","12d, 4h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-007","Wilhelmshaven - Bremen","< >","Delmenhorst","Delmenhorst Df",2025,2025,47,48,"2025-11-17","00:01:00","2025-11-29","05:00:00","12d, 4h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-007","Magdeburg - Falkenberg","<","Meinsdorf","Medewitz (Mark)",2025,2025,28,28,"2025-07-07","21:00:00","2025-07-11","05:00:00","3d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-008","Magdeburg - Falkenberg",">","Medewitz (Mark)","Meinsdorf",2025,2025,28,32,"2025-07-12","06:00:00","2025-08-08","21:00:00","27d, 15h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-17"]
[null,"DB InfraGO","A861-009","Magdeburg - Falkenberg","<","Meinsdorf","Medewitz (Mark)",2025,2025,28,32,"2025-07-12","06:00:00","2025-08-08","21:00:00","27d, 15h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-010","Magdeburg - Falkenberg","<","Meinsdorf","Medewitz (Mark)",2025,2025,28,32,"2025-07-12","06:00:00","2025-08-08","21:00:00","27d, 15h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-17"]
[null,"DB InfraGO","A861-011","Magdeburg - Falkenberg","<","Meinsdorf","Medewitz (Mark)",2025,2025,32,36,"2025-08-09","06:00:00","2025-09-05","21:00:00","27d, 15h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-17"]
[null,"DB InfraGO","A861-012","Magdeburg - Falkenberg",">","Medewitz (Mark)","Meinsdorf",2025,2025,32,36,"2025-08-09","06:00:00","2025-09-05","21:00:00","27d, 15h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-17"]
[null,"DB InfraGO","A861-013","Magdeburg - Falkenberg",">","Medewitz (Mark)","Meinsdorf",2025,2025,32,36,"2025-08-09","06:00:00","2025-09-05","21:00:00","27d, 15h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-014","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2025,2025,37,39,"2025-09-09","00:00:00","2025-09-22","23:59:00","13d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-008","Wilhelmshaven - Bremen","<","Bremen-Neustadt","Bookholzberg",2025,2025,47,48,"2025-11-17","00:01:00","2025-11-29","05:00:00","12d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","AC6F-001","Wilhelmshaven - Bremen",">","Oldenburg (Oldb) Hbf","Bremen Hbf ehem Bwn",2025,2025,17,19,"2025-04-25","23:00:00","2025-05-09","05:00:00","13d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","AC85-001","Wilhelmshaven - Bremen",">","Oldenburg (Oldb) Hbf","Bremen Hbf ehem Bwn",2025,2025,46,47,"2025-11-14","23:00:00","2025-11-21","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","AC8A-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Leer (Ostfriesl)",2025,2025,19,20,"2025-05-09","23:00:00","2025-05-16","05:00:00","6d, 6h","Periodical","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","AC95-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Leer (Ostfriesl)",2025,2025,48,49,"2025-11-24","23:00:00","2025-12-05","05:00:00","10d, 6h","Periodical","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2023-03-31"]
[null,"DB InfraGO","A861-015","Magdeburg - Falkenberg",">","Jeber-Bergfrieden","Meinsdorf",2025,2025,38,38,"2025-09-19","21:00:00","2025-09-21","21:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A8E5-009","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Bookholzberg",2025,2025,47,47,"2025-11-17","03:00:00","2025-11-17","05:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-010","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Bookholzberg",2025,2025,47,48,"2025-11-21","23:00:00","2025-11-24","04:00:00","2d, 5h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-011","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Bookholzberg",2025,2025,48,48,"2025-11-29","00:01:00","2025-11-29","02:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-018","Magdeburg - Falkenberg","<","Meinsdorf","Jeber-Bergfrieden",2025,2025,38,38,"2025-09-19","21:00:00","2025-09-21","21:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A8D2-001","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst",2025,2025,48,50,"2025-11-29","05:00:00","2025-12-12","05:00:00","13d, 0h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-019","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,28,29,"2025-07-12","06:00:00","2025-07-14","05:00:00","1d, 23h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-002","Wilhelmshaven - Bremen",">","Delmenhorst","Delmenhorst Df",2025,2025,48,50,"2025-11-30","00:01:00","2025-12-12","05:00:00","12d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-003","Wilhelmshaven - Bremen","< >","Delmenhorst","Delmenhorst Df",2025,2025,48,50,"2025-11-30","00:01:00","2025-12-12","05:00:00","12d, 4h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-004","Wilhelmshaven - Bremen","< >","Delmenhorst","Delmenhorst Df",2025,2025,48,50,"2025-11-30","00:01:00","2025-12-12","05:00:00","12d, 4h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-020","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,29,32,"2025-07-18","21:00:00","2025-08-04","05:00:00","16d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-005","Wilhelmshaven - Bremen","< >","Delmenhorst","Wildeshausen",2025,2025,48,50,"2025-11-30","00:01:00","2025-12-12","05:00:00","12d, 4h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-15"]
[null,"DB InfraGO","A8D2-006","Wilhelmshaven - Bremen",">","Bookholzberg","Bremen-Neustadt",2025,2025,48,50,"2025-11-30","00:01:00","2025-12-12","05:00:00","12d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-021","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,32,33,"2025-08-09","06:00:00","2025-08-11","05:00:00","1d, 23h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-022","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,33,36,"2025-08-15","21:00:00","2025-09-01","05:00:00","16d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A861-023","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,36,38,"2025-09-05","21:00:00","2025-09-19","15:00:00","13d, 18h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-007","Wilhelmshaven - Bremen","< >","Bookholzberg","Bremen-Neustadt",2025,2025,48,48,"2025-11-30","03:00:00","2025-11-30","05:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-008","Wilhelmshaven - Bremen","< >","Bookholzberg","Bremen-Neustadt",2025,2025,50,50,"2025-12-12","00:01:00","2025-12-12","02:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-009","Wilhelmshaven - Bremen","< >","Bookholzberg","Bremen-Neustadt",2025,2025,49,50,"2025-12-05","23:00:00","2025-12-08","04:00:00","2d, 5h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-010","Wilhelmshaven - Bremen","< >","Delmenhorst","Delmenhorst Heidkrug",2025,2025,50,50,"2025-12-12","05:00:00","2025-12-13","08:00:00","1d, 3h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8D2-011","Wilhelmshaven - Bremen","< >","Delmenhorst","Delmenhorst Heidkrug",2025,2025,50,50,"2025-12-13","08:00:00","2025-12-13","23:59:00","0d, 15h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-17"]
[null,"DB InfraGO","A8E5-013","Wilhelmshaven - Bremen","< >","Delmenhorst Heidkrug","Delmenhorst",2025,2025,47,48,"2025-11-17","00:01:00","2025-11-29","05:00:00","12d, 4h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","AED4-001","Rostock - Berlin","<","Waren (Müritz)","Kargow",2025,2025,16,16,"2025-04-14","06:00:00","2025-04-18","22:00:00","4d, 16h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","AED4-002","Rostock - Berlin",">","Kargow","Waren (Müritz)",2025,2025,18,18,"2025-04-28","06:00:00","2025-05-02","22:00:00","4d, 16h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","AED4-003","Rostock - Berlin","<","Waren (Müritz)","Kargow",2025,2025,20,20,"2025-05-12","06:00:00","2025-05-16","22:00:00","4d, 16h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","AED4-004","Rostock - Berlin","<","Waren (Müritz)","Kargow",2025,2025,22,22,"2025-05-26","05:00:00","2025-05-30","23:00:00","4d, 18h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","AED4-005","Rostock - Berlin","< >","Kargow","Waren (Müritz)",2025,2025,22,22,"2025-05-26","23:00:00","2025-05-29","05:00:00","2d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2024-02-21"]
[null,"DB InfraGO","AF50-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2024,2025,50,33,"2024-12-15","00:00:00","2025-08-17","23:59:00","245d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-18"]
[null,"DB InfraGO","AF50-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2024,2025,50,33,"2024-12-15","00:00:00","2025-08-17","23:59:00","245d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2023-01-18"]
[null,"DB InfraGO","A861-026","Magdeburg - Falkenberg","< >","Güterglück","Bitterfeld",2025,2025,28,28,"2025-07-11","21:00:00","2025-07-12","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-027","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Roßlau (Elbe) Gbf",2025,2025,28,28,"2025-07-11","21:00:00","2025-07-12","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-028","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,28,28,"2025-07-11","21:00:00","2025-07-12","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-029","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe) Gbf",2025,2025,28,28,"2025-07-11","21:00:00","2025-07-12","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-032","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Roßlau (Elbe) Gbf",2025,2025,36,36,"2025-09-05","21:00:00","2025-09-06","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-033","Magdeburg - Falkenberg","< >","Güterglück","Bitterfeld",2025,2025,36,36,"2025-09-05","21:00:00","2025-09-06","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-034","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,36,36,"2025-09-05","21:00:00","2025-09-06","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-035","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe) Gbf",2025,2025,36,36,"2025-09-05","21:00:00","2025-09-06","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-038","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Roßlau (Elbe) Gbf",2025,2025,32,32,"2025-08-08","21:00:00","2025-08-09","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-039","Magdeburg - Falkenberg","< >","Güterglück","Bitterfeld",2025,2025,32,32,"2025-08-08","21:00:00","2025-08-09","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-040","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,32,32,"2025-08-08","21:00:00","2025-08-09","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-041","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe) Gbf",2025,2025,32,32,"2025-08-08","21:00:00","2025-08-09","03:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-045","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Roßlau (Elbe) Gbf",2025,2025,38,38,"2025-09-19","15:00:00","2025-09-19","21:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-046","Magdeburg - Falkenberg","< >","Güterglück","Bitterfeld",2025,2025,38,38,"2025-09-19","15:00:00","2025-09-19","21:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-047","Magdeburg - Falkenberg","< >","Medewitz (Mark)","Meinsdorf",2025,2025,38,38,"2025-09-19","15:00:00","2025-09-19","21:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","A861-048","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe) Gbf",2025,2025,38,38,"2025-09-19","15:00:00","2025-09-19","21:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-01-18"]
[null,"DB InfraGO","B037-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,27,30,"2025-06-30","08:00:00","2025-07-24","04:00:00","23d, 20h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-003","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,27,30,"2025-06-30","08:00:00","2025-07-24","04:00:00","23d, 20h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,27,30,"2025-06-30","08:00:00","2025-07-24","04:00:00","23d, 20h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-005","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,27,30,"2025-06-30","08:00:00","2025-07-24","04:00:00","23d, 20h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-006","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,28,30,"2025-07-08","08:00:00","2025-07-24","04:00:00","15d, 20h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-008","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,28,30,"2025-07-10","22:00:00","2025-07-24","04:00:00","13d, 6h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-009","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,28,30,"2025-07-10","22:00:00","2025-07-24","04:00:00","13d, 6h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-011","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,28,30,"2025-07-10","22:00:00","2025-07-24","04:00:00","13d, 6h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B037-013","Falkenberg - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2025,2025,30,30,"2025-07-21","19:00:00","2025-07-22","05:00:00","0d, 10h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-003","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,30,32,"2025-07-24","04:00:00","2025-08-04","04:00:00","11d, 0h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-006","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,30,32,"2025-07-24","04:00:00","2025-08-04","04:00:00","11d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-013","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,32,33,"2025-08-04","04:00:00","2025-08-11","04:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-017","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,32,33,"2025-08-04","04:00:00","2025-08-11","04:00:00","7d, 0h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-021","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,32,32,"2025-08-09","20:00:00","2025-08-10","04:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-022","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,33,33,"2025-08-11","04:00:00","2025-08-14","04:00:00","3d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-026","Falkenberg - Dresden","< >","Dresden-Cotta Bft","Dresden-Friedrichstadt",2025,2025,33,33,"2025-08-11","04:00:00","2025-08-14","04:00:00","3d, 0h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B0B6-031","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,33,34,"2025-08-11","04:00:00","2025-08-18","16:00:00","7d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B12B-005","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,35,37,"2025-08-25","08:00:00","2025-09-12","17:00:00","18d, 9h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B12B-009","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,35,37,"2025-08-25","08:00:00","2025-09-12","17:00:00","18d, 9h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-19"]
[null,"DB InfraGO","B277-001","Wilhelmshaven - Bremen",">","Oldenburg (Oldb) Hbf","Wilhelmshaven",2025,2025,21,22,"2025-05-19","23:00:00","2025-05-26","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,46,46,"2025-11-13","21:00:00","2025-11-14","16:00:00","0d, 19h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-008","Falkenberg - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2025,2025,46,46,"2025-11-13","21:00:00","2025-11-14","04:00:00","0d, 7h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-009","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,46,46,"2025-11-13","21:00:00","2025-11-14","04:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-013","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,46,47,"2025-11-16","19:00:00","2025-11-17","04:00:00","0d, 9h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-014","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,47,47,"2025-11-17","22:00:00","2025-11-19","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-017","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,47,47,"2025-11-17","22:00:00","2025-11-19","04:00:00","1d, 6h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-020","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,47,47,"2025-11-20","22:00:00","2025-11-21","12:00:00","0d, 14h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B2FB-001","Bremerhaven - Bremen","< >","Brh-Speckenbütt","Cuxhaven CF",2025,2025,47,48,"2025-11-17","23:00:00","2025-11-24","05:00:00","6d, 6h","Periodical","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B2AD-005","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg-Hemmelsberg",2025,2025,27,29,"2025-07-03","00:01:00","2025-07-16","05:00:00","13d, 4h","Periodical","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B2AD-006","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Großenkneten",2025,2025,33,36,"2025-08-14","05:00:00","2025-09-01","08:00:00","18d, 3h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-20"]
[null,"DB InfraGO","B20B-027","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,47,47,"2025-11-22","08:00:00","2025-11-23","06:00:00","0d, 22h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-23"]
[null,"DB InfraGO","B20B-031","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,48,50,"2025-11-24","16:00:00","2025-12-13","17:00:00","19d, 1h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-23"]
[null,"DB InfraGO","B20B-038","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,49,49,"2025-12-01","21:00:00","2025-12-03","05:00:00","1d, 8h","Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-01-23"]
[null,"DB InfraGO","B20B-042","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,49,49,"2025-12-03","21:00:00","2025-12-05","05:00:00","1d, 8h","Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-01-23"]
[null,"DB InfraGO","B20B-048","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,50,50,"2025-12-10","08:00:00","2025-12-13","16:00:00","3d, 8h","Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5,6",null,"N",null,"2023-01-23"]
[null,"DB InfraGO","B0AD-003","Magdeburg - Falkenberg","<","Roßlau (Elbe) Aw","Klieken",2025,2025,21,21,"2025-05-24","04:00:00","2025-05-25","04:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-01-31"]
[null,"DB InfraGO","B0AD-006","Magdeburg - Falkenberg","<","Meinsdorf","Coswig (Anh) Gbf",2025,2025,25,25,"2025-06-21","01:00:00","2025-06-21","05:00:00","0d, 4h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-24"]
[null,"DB InfraGO","B0AD-007","Magdeburg - Falkenberg",">","Coswig (Anh) Gbf","Meinsdorf",2025,2025,25,25,"2025-06-21","01:00:00","2025-06-21","05:00:00","0d, 4h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-24"]
[null,"DB InfraGO","B58E-006","Hamburg - Magdeburg",">","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2025,2025,8,10,"2025-02-17","07:30:00","2025-03-08","19:30:00","19d, 12h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-03-04"]
[null,"DB InfraGO","B0B1-003","Magdeburg - Falkenberg",">","Coswig (Anh)","Coswig (Anh)",2025,2025,21,21,"2025-05-24","04:00:00","2025-05-25","04:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-08-03"]
[null,"DB InfraGO","B0B1-007","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,27,27,"2025-07-06","01:00:00","2025-07-06","05:00:00","0d, 4h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-01-25"]
[null,"DB InfraGO","BA3D-001","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,16,16,"2025-04-18","22:00:00","2025-04-19","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-01-26"]
[null,"DB InfraGO","BA3D-004","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,19,20,"2025-05-07","04:00:00","2025-05-12","16:00:00","5d, 12h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,3,4,5,6,7",null,"N",null,"2023-01-31"]
[null,"DB InfraGO","BB67-002","Hamburg - Magdeburg","< >","Wieren","Veerßen",2025,2025,16,18,"2025-04-19","00:00:00","2025-05-02","04:00:00","13d, 4h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-27"]
[null,"DB InfraGO","BB67-005","Hamburg - Magdeburg","< >","Veerßen","Uelzen Gbf",2025,2025,10,14,"2025-03-08","00:00:00","2025-04-04","04:00:00","27d, 3h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-27"]
[null,"DB InfraGO","BB67-006","Hamburg - Magdeburg","< >","Wieren","Veerßen",2025,2025,10,18,"2025-03-07","23:00:00","2025-05-02","21:00:00","55d, 21h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-01-27"]
[null,"DB InfraGO","B87F-007","Hamburg - Magdeburg","< >","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2025,2025,17,18,"2025-04-22","06:30:00","2025-05-02","21:00:00","10d, 14h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-04"]
[null,"DB InfraGO","BA3D-007","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,16,17,"2025-04-19","06:00:00","2025-04-22","12:00:00","3d, 6h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,6,7",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","BA3D-011","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,21,21,"2025-05-20","06:00:00","2025-05-23","18:00:00","3d, 12h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","BA3D-014","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,24,24,"2025-06-12","22:00:00","2025-06-15","06:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","BA3D-019","Magdeburg - Falkenberg","<","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2025,2025,45,45,"2025-11-04","06:00:00","2025-11-04","14:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","BA3D-022","Magdeburg - Falkenberg","<","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2025,2025,46,46,"2025-11-12","08:00:00","2025-11-12","16:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","BA3D-025","Magdeburg - Falkenberg","<","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2025,2025,50,50,"2025-12-13","06:00:00","2025-12-13","10:00:00","0d, 4h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-31"]
[null,"DB InfraGO","BA3D-026","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,50,50,"2025-12-13","10:00:00","2025-12-13","14:00:00","0d, 4h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-01-30"]
[null,"DB InfraGO","BE16-003","Hamburg - Magdeburg","< >","Bad Bodenteich","Schnega",2025,2025,18,18,"2025-04-30","15:00:00","2025-05-02","21:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5",null,"N",null,"2023-01-31"]
[null,"DB InfraGO","BED5-001","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2024,2025,50,22,"2024-12-15","00:00:00","2025-05-31","23:59:00","167d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-27"]
[null,"DB InfraGO","C032-001","Hamburg - Magdeburg",">","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2025,2025,11,13,"2025-03-14","07:30:00","2025-03-28","19:30:00","14d, 12h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-02"]
[null,"DB InfraGO","C032-006","Hamburg - Magdeburg",">","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2025,2025,14,16,"2025-04-05","07:30:00","2025-04-18","19:30:00","13d, 12h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-02-02"]
[null,"DB InfraGO","C032-018","Hamburg - Magdeburg","< >","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2025,2025,13,14,"2025-03-29","06:30:00","2025-04-04","21:00:00","6d, 13h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-04"]
[null,"DB InfraGO","C404-001","Berlin - Dresden","< >","Zossen","Blankenfelde (Kr Teltow-Fläming)",2025,2025,17,18,"2025-04-21","22:00:00","2025-05-03","04:00:00","11d, 6h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-25"]
[null,"DB InfraGO","C408-003","Berlin - Dresden","< >","Glasower Damm West","Blankenfelde (Kr Teltow-Fläming)",2025,2025,22,23,"2025-05-30","21:00:00","2025-06-02","05:00:00","2d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-02-05"]
[null,"DB InfraGO","C408-004","Berlin - Dresden","< >","Glasower Damm Ost","Blankenfelde (Kr Teltow-Fläming)",2025,2025,22,23,"2025-05-30","21:00:00","2025-06-02","05:00:00","2d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-02-05"]
[null,"DB InfraGO","C408-006","Berlin - Dresden","< >","Glasower Damm Ost","Flughafen BER F-Bahn",2025,2025,22,23,"2025-05-30","21:00:00","2025-06-06","21:00:00","7d, 0h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-02-05"]
[null,"DB InfraGO","C436-002","Berlin - Dresden","< >","Glasower Damm West","Schönefeld (bei Berlin) F-Bahn",2025,2025,31,32,"2025-08-01","21:00:00","2025-08-04","05:00:00","2d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2023-02-07"]
[null,"DB InfraGO","C458-001","Berlin - Dresden","< >","Diedersdorf","Schönefeld (bei Berlin) F-Bahn",2025,2025,33,33,"2025-08-15","21:00:00","2025-08-16","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-02-07"]
[null,"DB InfraGO","C458-004","Berlin - Dresden","< >","Glasower Damm Ost","Bohnsdorf Süd",2025,2025,33,33,"2025-08-15","21:00:00","2025-08-16","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-02-07"]
[null,"DB InfraGO","C458-009","Berlin - Dresden","< >","Hennersdorf West","Doberlug-Kh Nord",2025,2025,33,33,"2025-08-15","21:00:00","2025-08-16","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-02-07"]
[null,"DB InfraGO","C488-003","Berlin - Dresden","< >","Blankenfelde (Kr Teltow-Fläming)","Glasower Damm West",2025,2025,34,34,"2025-08-18","05:00:00","2025-08-22","05:00:00","4d, 0h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-05-15"]
[null,"DB InfraGO","C496-003","Berlin - Dresden","< >","Glasower Damm Ost","Flughafen BER F-Bahn",2025,2025,33,34,"2025-08-13","21:00:00","2025-08-18","05:00:00","4d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,3,4,5,6,7",null,"N",null,"2023-02-07"]
[null,"DB InfraGO","C496-004","Berlin - Dresden","< >","Blankenfelde (Kr Teltow-Fläming)","Glasower Damm West",2025,2025,33,34,"2025-08-13","21:00:00","2025-08-18","05:00:00","4d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,3,4,5,6,7",null,"N",null,"2023-06-04"]
[null,"DB InfraGO","C488-005","Berlin - Dresden","< >","Glasower Damm Ost","Blankenfelde (Kr Teltow-Fläming)",2025,2025,34,35,"2025-08-22","05:00:00","2025-08-26","21:00:00","4d, 16h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2023-06-04"]
[null,"DB InfraGO","6F78-036","Hannover - Magdeburg",">","Waldhausen","Hannover-Wülfel",2025,2025,39,39,"2025-09-25","23:40:00","2025-09-26","05:15:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-06-05"]
[null,"DB InfraGO","6F78-048","Hannover - Magdeburg",">","Waldhausen","Hannover-Wülfel",2025,2025,39,40,"2025-09-27","01:00:00","2025-09-30","01:30:00","3d, 0h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,6,7",null,"N",null,"2023-06-05"]
[null,"DB InfraGO","6F78-057","Hannover - Magdeburg",">","Waldhausen","Hannover-Wülfel",2025,2025,39,40,"2025-09-27","14:55:00","2025-09-29","15:20:00","2d, 0h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2023-06-05"]
[null,"DB InfraGO","1543D-002","Hannover - Magdeburg","< >","Magdeburg-Buckau","Magdeburg-Sudenburg",2025,2025,19,19,"2025-05-10","22:00:00","2025-05-11","00:50:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-09-07"]
[null,"DB InfraGO","81C2-021","Falkenberg - Dresden",">","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,40,40,"2025-10-01","20:00:00","2025-10-03","05:00:00","1d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-05-30"]
[null,"DB InfraGO","81C2-023","Falkenberg - Dresden",">","Zeithain Bogendreieck","Leckwitz",2025,2025,41,41,"2025-10-06","20:00:00","2025-10-10","05:00:00","3d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-05-30"]
[null,"DB InfraGO","81C2-024","Falkenberg - Dresden",">","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,41,41,"2025-10-06","20:00:00","2025-10-10","05:00:00","3d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-05-30"]
[null,"DB InfraGO","14CD2-008","Hamburg - Magdeburg",">","Jesteburg","Maschen Rbf (Msof)",2025,2025,15,15,"2025-04-11","00:50:00","2025-04-11","05:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-06-09"]
[null,"DB InfraGO","15BA8-002","Hamburg - Magdeburg","< >","Wieren","Wieren",2025,2025,17,17,"2025-04-26","21:15:00","2025-04-27","00:00:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-06-09"]
[null,"DB InfraGO","15C60-001","Hamburg - Magdeburg","< >","Wieren","Veerßen",2025,2025,17,17,"2025-04-25","21:15:00","2025-04-26","00:00:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-06-09"]
[null,"DB InfraGO","15C60-004","Hamburg - Magdeburg","< >","Wieren","Wieren",2025,2025,17,17,"2025-04-25","21:15:00","2025-04-26","00:00:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-09"]
[null,"DB InfraGO","15D4E-002","Hannover - Magdeburg","<","Marienborn","Eilsleben (b Magdeburg)",2025,2025,19,19,"2025-05-05","23:35:00","2025-05-07","00:40:00","1d, 1h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","15D80-001","Hamburg - Magdeburg","< >","Ashausen Abzw","Maschen Rbf (Msof)",2025,2025,25,25,"2025-06-20","21:00:00","2025-06-20","22:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-06-13"]
[null,"DB InfraGO","15D4E-006","Hannover - Magdeburg","<","Wellen","Magdeburg-Sudenburg",2025,2025,19,19,"2025-05-06","03:00:00","2025-05-07","04:30:00","1d, 1h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","15D80-006","Hamburg - Magdeburg",">","Hmb-Wlb Abzw","Hamburg-Rothenburgsort Ro",2025,2025,25,25,"2025-06-21","01:50:00","2025-06-21","02:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-06-13"]
[null,"DB InfraGO","1600B-003","Hamburg - Magdeburg","<","Lehrte Nord","Lehrte Nord",2025,2025,14,14,"2025-04-05","22:35:00","2025-04-05","23:35:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N"]
[null,"DB InfraGO","1600B-010","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Hannover-Waldheim",2025,2025,14,14,"2025-04-06","03:35:00","2025-04-06","04:45:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N"]
[null,"DB InfraGO","1600B-013","Bremen - Hannover","< >","Hannover-Linden Hafen","Waldhausen",2025,2025,14,14,"2025-04-06","04:45:00","2025-04-06","06:05:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N"]
[null,"DB InfraGO","16010-007","Hamburg - Magdeburg","<","Hamburg-Veddel","Meckelfeld",2025,2025,25,25,"2025-06-21","22:50:00","2025-06-22","01:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-06-13"]
[null,"DB InfraGO","16071-001","Dresden - Děčín","<","Heidenau","Pirna Gbf",2025,2025,14,14,"2025-04-04","21:30:00","2025-04-05","04:30:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16071-006","Dresden - Děčín","<","Dresden-Niedersedlitz Güteranlage  (DHD)","Heidenau",2025,2025,14,14,"2025-04-05","21:30:00","2025-04-05","23:59:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16071-008","Dresden - Děčín","< >","Heidenau","Dresden-Niedersedlitz Güteranlage  (DHD)",2025,2025,14,14,"2025-04-05","21:30:00","2025-04-05","23:59:00","0d, 2h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16071-012","Dresden - Děčín","<","Dresden Hbf","Dresden-Reick Abstellbahnhof",2025,2025,14,15,"2025-04-06","21:30:00","2025-04-07","04:30:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16071-016","Dresden - Děčín",">","Pirna","Heidenau",2025,2025,15,15,"2025-04-07","21:30:00","2025-04-08","04:30:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",16.09,"Bremen - Hannover","< >","Ahlem","Ahlem",2025,2025,14,14,"2025-04-06","21:40:00","2025-04-06","23:25:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N"]
[null,"DB InfraGO",1.609E-2,"Bremen - Hannover","< >","Ahlem","Hannover Kurve",2025,2025,14,14,"2025-04-06","21:40:00","2025-04-06","23:25:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N"]
[null,"DB InfraGO",1.609E-5,"Bremen - Hannover","< >","Seelze Ost","Hannover-Linden Hafen",2025,2025,14,15,"2025-04-06","23:25:00","2025-04-07","00:25:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","16071-024","Dresden - Děčín","< >","Dresden-Niedersedlitz Güteranlage  (DHD)","Dresden-Reick Abstellbahnhof",2025,2025,15,15,"2025-04-09","00:30:00","2025-04-09","04:30:00","0d, 4h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16071-026","Dresden - Děčín",">","Dresden Hbf","Dresden Hbf",2025,2025,15,15,"2025-04-10","02:00:00","2025-04-10","04:30:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.6089999999999999E-12,"Bremen - Hannover","<","Gümmerwald","Wunstorf",2025,2025,15,15,"2025-04-07","01:10:00","2025-04-07","03:40:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO",1.6090000000000001E-14,"Bremen - Hannover","<","Wunstorf","Seelze West",2025,2025,15,15,"2025-04-07","01:10:00","2025-04-07","03:40:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO",1.609E-17,"Bremen - Hannover","< >","Wunstorf","Seelze West",2025,2025,15,15,"2025-04-07","03:40:00","2025-04-07","04:40:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N"]
[null,"DB InfraGO",16.21,"Hannover - Magdeburg","<","Schandelah","Braunschweig Schmiedekamp",2025,2025,16,16,"2025-04-14","22:05:00","2025-04-14","23:05:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","1622A-002","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2025,41,41,"2025-10-11","07:00:00","2025-10-11","13:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","163CE-001","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2025,2025,18,18,"2025-04-28","22:40:00","2025-04-29","00:40:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","163CE-004","Bremen - Hannover",">","Poggenhagen","Neustadt a Rübenberge",2025,2025,18,18,"2025-04-29","00:40:00","2025-04-29","01:40:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","163CE-007","Bremen - Hannover",">","Hagen (Han)","Linsburg",2025,2025,18,18,"2025-04-29","04:30:00","2025-04-29","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","163CE-008","Bremen - Hannover","< >","Linsburg","Hagen (Han)",2025,2025,18,18,"2025-04-29","04:30:00","2025-04-29","05:30:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","16449-004","Dresden - Děčín","<","Bad Schandau","Bad Schandau Ost",2025,2025,15,15,"2025-04-10","23:00:00","2025-04-11","01:30:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16457-002","Bremen - Hannover","< >","Neustadt a Rübenberge","Linsburg",2025,2025,18,18,"2025-04-29","21:50:00","2025-04-29","23:50:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","16457-005","Bremen - Hannover","<","Neustadt a Rübenberge","Wunstorf",2025,2025,18,18,"2025-04-30","02:20:00","2025-04-30","04:20:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2024-07-23"]
[null,"DB InfraGO","16468-003","Dresden - Děčín","< >","Schöna","Bad Schandau Ost",2025,2025,15,15,"2025-04-11","21:30:00","2025-04-13","04:30:00","1d, 7h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-08-04"]
[null,"DB InfraGO","16494-001","Dresden - Děčín",">","Bad Schandau","Königst (Sä) Üst",2025,2025,15,16,"2025-04-13","21:30:00","2025-04-15","04:30:00","1d, 7h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16494-005","Dresden - Děčín",">","Bad Schandau","Bad Schandau",2025,2025,15,15,"2025-04-13","21:30:00","2025-04-13","23:59:00","0d, 2h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16494-008","Dresden - Děčín","<","Königst (Sä) Üst","Bad Schandau",2025,2025,16,16,"2025-04-15","21:30:00","2025-04-17","04:30:00","1d, 7h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16494-010","Dresden - Děčín","< >","Bad Schandau","Königst (Sä) Üst",2025,2025,16,16,"2025-04-15","21:30:00","2025-04-17","04:30:00","1d, 7h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16494-013","Dresden - Děčín","<","Kurort Rathen (Kr Pirna)","Bad Schandau",2025,2025,16,16,"2025-04-17","01:30:00","2025-04-17","04:30:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","164D7-005","Dresden - Děčín",">","Dresden-Niedersedlitz Güteranlage  (DHD)","Dresden Hbf",2025,2025,17,17,"2025-04-24","00:00:00","2025-04-24","04:30:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","164D7-009","Dresden - Děčín",">","Dresden-Reick Abstellbahnhof","Dresden-Reick Abstellbahnhof",2025,2025,17,17,"2025-04-24","21:30:00","2025-04-25","04:30:00","0d, 7h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","164D7-013","Dresden - Děčín",">","Dresden Hbf","Dresden Hbf",2025,2025,17,17,"2025-04-25","02:00:00","2025-04-25","04:30:00","0d, 2h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-07-16"]
[null,"DB InfraGO","16540-002","Dresden - Děčín",">","Dresden Hbf","Dresden Mitte",2025,2025,17,17,"2025-04-26","21:30:00","2025-04-27","01:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16540-006","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,17,17,"2025-04-27","01:15:00","2025-04-27","04:30:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16594-002","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2025,2025,15,15,"2025-04-09","08:00:00","2025-04-13","20:00:00","4d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","16594-003","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2025,2025,15,15,"2025-04-11","20:00:00","2025-04-13","20:00:00","2d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","16594-006","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2025,2025,15,15,"2025-04-11","20:00:00","2025-04-13","20:00:00","2d, 0h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","165C9-002","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2025,2025,26,26,"2025-06-25","10:00:00","2025-06-25","12:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","165CA-004","Berlin - Dresden",">","Elsterwerda","Elsterwerda",2025,2025,18,18,"2025-04-28","22:30:00","2025-04-29","04:30:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","165CA-007","Falkenberg - Dresden","< >","Elsterwerda","Gröditz (b Riesa)",2025,2025,18,18,"2025-04-29","02:00:00","2025-04-29","04:30:00","0d, 2h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2024-01-03"]
[null,"DB InfraGO","1670D-001","Bremen - Hannover","< >","Wunstorf","Poggenhagen",2025,2025,19,20,"2025-05-09","22:40:00","2025-05-12","04:25:00","2d, 5h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-07-19"]
[null,"DB InfraGO","1670D-004","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2025,2025,20,21,"2025-05-16","22:40:00","2025-05-19","04:30:00","2d, 5h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-07-19"]
[null,"DB InfraGO","1670D-007","Bremen - Hannover","< >","Wunstorf","Poggenhagen",2025,2025,21,21,"2025-05-20","06:00:00","2025-05-22","18:00:00","2d, 12h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2024-07-19"]
[null,"DB InfraGO","1664C-002","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2025,2025,17,19,"2025-04-24","08:00:00","2025-05-07","16:00:00","13d, 8h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-31"]
[null,"DB InfraGO","1664C-005","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2025,2025,17,19,"2025-04-25","16:00:00","2025-05-05","16:00:00","10d, 0h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-10-27"]
[null,"DB InfraGO",167.8,"Falkenberg - Dresden","<","Coswig (bei Dresden) Stw 1","Coswig (bei Dresden) Stw 1",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-20","23:00:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",0.1678,"Falkenberg - Dresden",">","Coswig (bei Dresden) Stw 1","Coswig (bei Dresden)",2025,2025,21,21,"2025-05-20","23:00:00","2025-05-21","01:00:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.6780000000000001E-4,"Falkenberg - Dresden","< >","Niederau","Coswig (bei Dresden)",2025,2025,21,21,"2025-05-21","01:00:00","2025-05-21","04:30:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16857-011","Magdeburg - Falkenberg","<","Falkenberg (Elster) unt Bf Stw W 15","Bad Liebenwerda",2025,2025,22,22,"2025-05-26","00:00:00","2025-05-27","04:00:00","1d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16832-003","Falkenberg - Dresden","< >","Radebeul Ost","Dresden-Neustadt",2025,2025,21,21,"2025-05-22","01:00:00","2025-05-22","04:00:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","16832-004","Falkenberg - Dresden","< >","Radebeul Ost","Dresden-Neustadt",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","01:00:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","168AD-002","Falkenberg - Dresden","<","Dresden-Neustadt","Radebeul Nord",2025,2025,21,21,"2025-05-25","03:00:00","2025-05-25","04:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","168AD-005","Falkenberg - Dresden","< >","Radebeul Ost","Radebeul Ost",2025,2025,21,21,"2025-05-25","03:00:00","2025-05-25","04:30:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","168F2-002","Falkenberg - Dresden",">","Dresden-Pieschen                  (Abzw)","Dresden-Neustadt",2025,2025,27,27,"2025-07-02","02:00:00","2025-07-02","04:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","168F2-005","Falkenberg - Dresden","< >","Radebeul Nord","Dresden-Pieschen                  (Abzw)",2025,2025,27,27,"2025-07-01","21:30:00","2025-07-02","04:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","168F3-003","Hamburg - Magdeburg","< >","Zielitz","Angern-Rogätz",2025,2025,9,9,"2025-03-01","21:30:00","2025-03-02","05:30:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-08-08"]
[null,"DB InfraGO","168F2-008","Falkenberg - Dresden","< >","Radebeul Nord","Dresden-Neustadt",2025,2025,27,27,"2025-07-02","21:30:00","2025-07-03","04:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","168FE-008","Hannover - Magdeburg","< >","Magdeburg-Sudenburg","Magdeburg-Sudenburg",2025,2025,19,19,"2025-05-11","05:05:00","2025-05-11","06:30:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-09-07"]
[null,"DB InfraGO","16916-001","Hamburg - Magdeburg",">","Zielitz Stw B2","Angern-Rogätz",2025,2025,9,9,"2025-03-01","02:30:00","2025-03-01","05:30:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-01-03"]
[null,"DB InfraGO","169DC-003","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2025,2025,40,40,"2025-09-29","21:00:00","2025-10-01","04:30:00","1d, 7h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","169DC-010","Dresden - Děčín","< >","Dresden-Neustadt","Dresden-Neustadt",2025,2025,40,40,"2025-10-01","02:30:00","2025-10-03","04:30:00","2d, 2h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,5",null,"N",null,"2024-07-15"]
[null,"DB InfraGO","16B7F-001","Dresden - Děčín","< >","Schöna","Bad Schandau Ost",2025,2025,46,50,"2025-11-15","00:01:00","2025-12-13","23:59:00","28d, 23h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-15"]
[null,"DB InfraGO","16BE5-002","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,21,30,"2025-05-23","00:40:00","2025-07-25","01:40:00","63d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-06-14"]
[null,"DB InfraGO","16BE5-006","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Zeithain Rohrwerk",2025,2025,21,30,"2025-05-23","03:40:00","2025-07-25","04:40:00","63d, 1h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2023-06-14"]
[null,"DB InfraGO","16C74-001","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2025,2025,9,9,"2025-03-01","08:00:00","2025-03-02","16:00:00","1d, 8h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-08-14"]
[null,"DB InfraGO","16C74-004","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2025,2025,9,9,"2025-03-01","08:00:00","2025-03-02","16:00:00","1d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-08-14"]
[null,"DB InfraGO","16CCD-001","Falkenberg - Dresden",">","Cossebaude","Radebeul Abzw Az",2025,2025,14,14,"2025-04-03","22:00:00","2025-04-05","08:00:00","1d, 10h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16CCD-004","Falkenberg - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2025,2025,14,14,"2025-04-03","22:00:00","2025-04-05","08:00:00","1d, 10h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16CCD-007","Falkenberg - Dresden","< >","Radebeul Abzw Az","Cossebaude",2025,2025,15,15,"2025-04-08","22:00:00","2025-04-12","06:00:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16CF0-002","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2025,2025,15,15,"2025-04-12","22:00:00","2025-04-13","06:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16CF0-003","Falkenberg - Dresden","<","Radebeul Abzw Az","Radebeul-Naundorf",2025,2025,15,17,"2025-04-13","06:00:00","2025-04-26","22:00:00","13d, 16h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16CF0-007","Falkenberg - Dresden","< >","Radebeul-Naundorf","Cossebaude",2025,2025,17,17,"2025-04-25","21:00:00","2025-04-26","07:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16CF0-010","Falkenberg - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2025,2025,17,17,"2025-04-26","22:00:00","2025-04-27","06:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16E80-003","Falkenberg - Dresden",">","Radebeul-Naundorf","Radebeul Abzw Az",2025,2025,21,23,"2025-05-25","06:00:00","2025-06-07","22:00:00","13d, 16h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16E80-004","Falkenberg - Dresden",">","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2025,2025,21,23,"2025-05-25","06:00:00","2025-06-07","22:00:00","13d, 16h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16E80-007","Falkenberg - Dresden","< >","Cossebaude","Radebeul Abzw Az",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","07:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2023-08-12"]
[null,"DB InfraGO","16E80-010","Falkenberg - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2025,2025,23,23,"2025-06-07","22:00:00","2025-06-08","06:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2023-08-12"]
[null,"DB InfraGO",171.7,"Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,38,39,"2025-09-20","20:00:00","2025-09-25","04:30:00","4d, 8h","Periodical","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,6,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",0.17169999999999999,"Dresden - Děčín","<","Dresden Hbf","Dresden-Reick Abstellbahnhof",2025,2025,38,38,"2025-09-20","21:00:00","2025-09-20","23:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.717E-5,"Dresden - Děčín","<","Dresden Hbf","Dresden-Reick",2025,2025,38,38,"2025-09-21","01:00:00","2025-09-21","03:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.7170000000000001E-8,"Dresden - Děčín",">","Dresden Hbf","Dresden Hbf",2025,2025,38,38,"2025-09-21","03:00:00","2025-09-21","05:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.7170000000000001E-11,"Dresden - Děčín","< >","Dresden Hbf","Dresden-Reick",2025,2025,39,39,"2025-09-22","00:00:00","2025-09-22","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.7170000000000001E-12,"Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,39,39,"2025-09-22","00:00:00","2025-09-22","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","172A6-003","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hamburg-Rothenburgsort Ro",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","07:00:00","0d, 7h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N"]
[null,"DB InfraGO",1.717E-17,"Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,39,39,"2025-09-22","20:00:00","2025-09-22","22:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","172A6-007","Hamburg - Magdeburg","< >","Hmb-Wlb Abzw","Hamburg-Harburg",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","16:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-03-05"]
[null,"DB InfraGO",1.717E-21,"Dresden - Děčín",">","Dresden-Niedersedlitz Güteranlage  (DHD)","Dresden Hbf",2025,2025,39,39,"2025-09-22","22:00:00","2025-09-23","02:30:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.7170000000000001E-24,"Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,39,39,"2025-09-23","02:30:00","2025-09-23","04:00:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.717E-27,"Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,39,39,"2025-09-23","21:00:00","2025-09-24","04:30:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.717E-31,"Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,39,39,"2025-09-24","21:00:00","2025-09-25","04:30:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO",1.7170000000000001E-32,"Dresden - Děčín","< >","Dresden-Reick","Dresden Hbf",2025,2025,39,39,"2025-09-25","00:30:00","2025-09-25","04:30:00","0d, 4h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17173-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","17173-006","Dresden - Děčín","< >","Dresden Hbf","Klingenberg-Colmnitz",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","17173-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","17173-013","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","17173-017","Falkenberg - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","1746A-003","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2025,14,14,"2025-04-06","02:15:00","2025-04-06","04:50:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-21"]
[null,"DB InfraGO","1746A-006","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2025,14,15,"2025-04-06","22:40:00","2025-04-07","02:45:00","0d, 4h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-21"]
[null,"DB InfraGO","1746A-007","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2025,14,15,"2025-04-06","22:40:00","2025-04-07","02:45:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-21"]
[null,"DB InfraGO","1746A-009","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2025,15,15,"2025-04-07","02:45:00","2025-04-07","04:55:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2024-07-21"]
[null,"DB InfraGO","17173-020","Falkenberg - Dresden","< >","Elsterwerda","Gröditz (b Riesa)",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","17173-023","Berlin - Dresden","< >","Großenhain Cottb Bf","Priestewitz",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2023-07-17"]
[null,"DB InfraGO",17.940000000000001,"Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Stw W 17","Falkenberg (Elster) unt Bf Stw W 15",2025,2025,10,10,"2025-03-04","20:00:00","2025-03-05","04:00:00","0d, 8h","Continuous","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3",null,"N"]
[null,"DB InfraGO","17F66-002","Hannover - Magdeburg","< >","Biederitz","Magdeburg Hbf",2025,2025,18,18,"2025-05-02","22:00:00","2025-05-03","01:50:00","0d, 3h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","17F66-006","Hannover - Magdeburg","<","Magdeburg-Neustadt","Gerwisch",2025,2025,18,18,"2025-05-03","00:50:00","2025-05-03","01:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-12-19"]
[null,"DB InfraGO","17F66-007","Hannover - Magdeburg","< >","Magdeburg Hbf","Biederitz",2025,2025,18,18,"2025-05-03","02:00:00","2025-05-03","06:00:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-12-19"]
[null,"DB InfraGO","17F66-010","Hannover - Magdeburg","<","Magdeburg-Neustadt","Gerwisch",2025,2025,18,18,"2025-05-03","04:50:00","2025-05-03","06:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-12-19"]
[null,"DB InfraGO","17FD4-003","Falkenberg - Dresden","< >","Weinböhla","Großenhain Berl Bf",2025,2025,21,21,"2025-05-23","01:30:00","2025-05-23","04:00:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FD4-007","Falkenberg - Dresden","<","Großenhain Berl Bf","Weinböhla",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","01:30:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FD4-010","Berlin - Dresden","< >","Kottewitz","Leckwitz",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","01:30:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FE3-001","Dresden - Děčín",">","Dresden Hbf","Dresden Mitte",2025,2025,39,39,"2025-09-26","21:00:00","2025-09-27","01:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FE3-007","Dresden - Děčín",">","Dresden-Neustadt","Dresden-Neustadt",2025,2025,39,39,"2025-09-27","21:00:00","2025-09-28","00:30:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FE3-012","Dresden - Děčín","<","Dresden Mitte","Dresden Hbf",2025,2025,39,40,"2025-09-28","21:00:00","2025-09-29","04:30:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FE3-014","Dresden - Děčín","<","Dresden Hbf","Dresden Hbf",2025,2025,39,40,"2025-09-28","23:00:00","2025-09-29","01:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","17FE3-020","Dresden - Děčín",">","Dresden Freiberger Straße","Dresden-Neustadt",2025,2025,40,40,"2025-09-29","01:00:00","2025-09-29","04:30:00","0d, 3h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","18006-006","Hannover - Magdeburg","<","Biederitz","Möser",2025,2025,18,18,"2025-05-02","00:30:00","2025-05-02","01:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-07-11"]
[null,"DB InfraGO",0.18049999999999999,"Hamburg - Magdeburg","< >","Hamburg Unterelbe","Hamburg Unterelbe Seehafen",2025,2025,14,14,"2025-04-04","16:00:00","2025-04-04","19:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-07-31"]
[null,"DB InfraGO",1.8050000000000001E-7,"Hamburg - Magdeburg","< >","Hamburg Unterelbe Seehafen","Hamburg Unterelbe",2025,2025,16,16,"2025-04-14","13:00:00","2025-04-14","16:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2024-07-31"]
[null,"DB InfraGO","18216-003","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,40,42,"2025-09-29","08:00:00","2025-10-19","16:00:00","20d, 8h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","182DA-002","Hannover - Magdeburg",">","Bindfelde Abzw","Stendal Hauptbahnhof",2025,2025,17,17,"2025-04-25","22:00:00","2025-04-25","23:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-07-22"]
[null,"DB InfraGO","18697-001","Hannover - Magdeburg",">","Magdeburg-Sudenburg","Niederndodeleben",2025,2025,18,18,"2025-05-03","21:25:00","2025-05-04","21:55:00","1d, 0h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","18697-002","Hannover - Magdeburg","< >","Magdeburg-Sudenburg","Eilsleben (b Magdeburg) Gbf",2025,2025,18,19,"2025-05-03","21:25:00","2025-05-05","00:55:00","1d, 3h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","18697-007","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg)","Helmstedt",2025,2025,18,19,"2025-05-04","00:55:00","2025-05-05","04:10:00","1d, 3h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","18697-010","Hannover - Magdeburg",">","Marienborn","Helmstedt",2025,2025,18,19,"2025-05-04","03:15:00","2025-05-05","04:10:00","1d, 0h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-07-11"]
[null,"DB InfraGO","18921-004","Berlin - Dresden","< >","Selchow West","Selchow Süd",2025,2025,47,47,"2025-11-21","21:30:00","2025-11-21","22:30:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18921-007","Berlin - Dresden","< >","Schönefeld (bei Berlin) F-Bahn","Schönefeld (bei Berlin) F-Bahn",2025,2025,47,47,"2025-11-21","22:30:00","2025-11-22","01:00:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18921-011","Berlin - Dresden","< >","Grünauer Kreuz West","Grünauer Kreuz Süd",2025,2025,47,47,"2025-11-22","01:00:00","2025-11-22","02:30:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18A90-001","Berlin - Dresden","<","Glasower Damm Ost","Diedersdorf",2025,2025,47,47,"2025-11-23","20:00:00","2025-11-23","21:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18A90-004","Berlin - Dresden","<","Grünauer Kreuz Nord","Schönefeld (bei Berlin) F-Bahn",2025,2025,48,48,"2025-11-24","00:00:00","2025-11-24","02:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18A90-005","Berlin - Dresden","< >","Grünauer Kreuz West","Grünauer Kreuz Süd",2025,2025,48,48,"2025-11-24","00:00:00","2025-11-24","02:00:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18B0E-003","Hannover - Magdeburg","<","Wellen","Magdeburg-Sudenburg",2025,2025,19,19,"2025-05-07","22:00:00","2025-05-08","02:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18B0E-006","Hannover - Magdeburg",">","Niederndodeleben","Wellen",2025,2025,19,19,"2025-05-08","03:00:00","2025-05-08","05:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18B99-003","Dresden - Děčín","<","Dresden Freiberger Straße","Dresden Hbf",2025,2025,14,16,"2025-04-06","19:30:00","2025-04-17","05:00:00","10d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,7",null,"N",null,"2024-01-03"]
[null,"DB InfraGO","18B99-006","Dresden - Děčín","<","Dresden Freiberger Straße","Dresden Hbf",2025,2025,19,20,"2025-05-11","19:30:00","2025-05-15","05:00:00","3d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,7",null,"N",null,"2024-01-03"]
[null,"DB InfraGO","18BC0-005","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2025,2025,17,17,"2025-04-22","19:30:00","2025-04-27","04:30:00","4d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18BCB-003","Hannover - Magdeburg","<","Wellen","Magdeburg-Sudenburg",2025,2025,19,19,"2025-05-08","22:30:00","2025-05-09","02:30:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18BCB-004","Hannover - Magdeburg","< >","Niederndodeleben","Niederndodeleben",2025,2025,19,19,"2025-05-08","22:30:00","2025-05-09","02:30:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18BC0-010","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2025,2025,20,21,"2025-05-18","19:30:00","2025-05-21","04:30:00","2d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18BCB-007","Hannover - Magdeburg","< >","Niederndodeleben","Niederndodeleben",2025,2025,19,19,"2025-05-09","03:45:00","2025-05-09","05:15:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18BE8-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,19,"2025-05-05","19:30:00","2025-05-08","04:30:00","2d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18BE8-006","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,19,"2025-05-07","19:30:00","2025-05-08","04:30:00","0d, 9h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18BE8-009","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,19,19,"2025-05-07","19:30:00","2025-05-08","04:30:00","0d, 9h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C01-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,41,"2025-10-06","23:00:00","2025-10-07","04:00:00","0d, 5h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C01-006","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,41,"2025-10-07","19:30:00","2025-10-08","04:30:00","0d, 9h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C01-009","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,41,42,"2025-10-12","19:30:00","2025-10-15","04:30:00","2d, 9h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C01-010","Dresden - Děčín","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,41,42,"2025-10-12","19:30:00","2025-10-15","04:30:00","2d, 9h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C01-013","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,42,"2025-10-15","19:30:00","2025-10-16","04:30:00","0d, 9h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C5F-001","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,43,"2025-10-19","19:30:00","2025-10-20","04:30:00","0d, 9h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C5F-004","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,42,43,"2025-10-19","19:30:00","2025-10-20","04:30:00","0d, 9h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18C6D-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,43,43,"2025-10-20","19:30:00","2025-10-24","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-01-03"]
[null,"DB InfraGO","18C8B-003","Berlin - Dresden","<","Genshagener Heide Ost","Genshagener Heide Mitte",2025,2025,47,47,"2025-11-22","20:10:00","2025-11-23","00:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18C8B-006","Berlin - Dresden","<","Genshagener Heide","Saarmund",2025,2025,47,47,"2025-11-22","20:10:00","2025-11-23","00:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18C8B-010","Berlin - Dresden","<","Diedersdorf","Diedersdorf",2025,2025,47,47,"2025-11-23","00:00:00","2025-11-23","03:50:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18C8B-011","Berlin - Dresden","<","Diedersdorf","Genshagener Heide Mitte",2025,2025,47,47,"2025-11-23","00:00:00","2025-11-23","03:50:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18C8B-014","Berlin - Dresden","< >","Genshagener Heide Mitte","Gensh Heide Nord",2025,2025,47,47,"2025-11-23","00:00:00","2025-11-23","03:50:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18CE6-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,43,44,"2025-10-24","21:00:00","2025-10-27","04:00:00","2d, 8h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18CE6-006","Dresden - Děčín","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,43,44,"2025-10-24","21:00:00","2025-10-27","04:00:00","2d, 8h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D0A-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,45,45,"2025-11-03","19:30:00","2025-11-07","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D23-003","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,47,"2025-11-07","21:00:00","2025-11-17","04:00:00","9d, 7h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D23-006","Dresden - Děčín","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,47,"2025-11-07","21:00:00","2025-11-17","04:00:00","9d, 7h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D23-007","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,47,"2025-11-07","21:00:00","2025-11-17","04:00:00","9d, 7h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D4A-001","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2025,46,46,"2025-11-10","19:30:00","2025-11-14","04:30:00","3d, 9h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D4A-004","Dresden - Děčín","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,46,46,"2025-11-10","19:30:00","2025-11-14","04:30:00","3d, 9h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D4A-008","Dresden - Děčín","< >","Dresden Hbf","Dresden Freiberger Straße",2025,2025,46,46,"2025-11-10","19:30:00","2025-11-14","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D55-003","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2025,2025,47,47,"2025-11-17","19:30:00","2025-11-22","04:30:00","4d, 9h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,4,5",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D55-006","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2025,2025,47,47,"2025-11-17","19:30:00","2025-11-22","04:30:00","4d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,4,5",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","18D5A-004","Hannover - Magdeburg","< >","Dreileben-Drackenstedt","Dreileben-Drackenstedt",2025,2025,19,19,"2025-05-09","20:50:00","2025-05-09","23:50:00","0d, 3h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18D5A-007","Hannover - Magdeburg","< >","Dreileben-Drackenstedt","Dreileben-Drackenstedt",2025,2025,19,19,"2025-05-10","00:50:00","2025-05-10","02:20:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18D5A-008","Hannover - Magdeburg","< >","Dreileben-Drackenstedt","Eilsleben (b Magdeburg) Gbf",2025,2025,19,19,"2025-05-10","02:20:00","2025-05-10","03:55:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18DF4-001","Rostock - Berlin",">","Kargow","Waren (Müritz)",2025,2025,24,25,"2025-06-12","23:00:00","2025-06-20","05:00:00","7d, 6h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-06"]
[null,"DB InfraGO","18DA6-004","Rostock - Berlin",">","Kargow","Waren (Müritz)",2025,2025,42,42,"2025-10-15","23:00:00","2025-10-16","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-02-22"]
[null,"DB InfraGO","18E00-003","Berlin - Dresden",">","Saarmund","Genshagener Heide",2025,2025,48,48,"2025-11-24","22:00:00","2025-11-25","02:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18E00-008","Berlin - Dresden","<","Glasower Damm Ost","Saarmund",2025,2025,48,48,"2025-11-24","22:00:00","2025-11-25","06:00:00","0d, 8h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18E00-012","Berlin - Dresden",">","Genshagener Heide Ost","Diedersdorf",2025,2025,48,48,"2025-11-25","02:00:00","2025-11-25","06:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18E00-015","Berlin - Dresden","< >","Birkengrund Süd","Genshagener Heide Ost",2025,2025,48,48,"2025-11-25","02:00:00","2025-11-25","06:00:00","0d, 4h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18E6B-004","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg)","Wefensleben",2025,2025,20,20,"2025-05-12","00:15:00","2025-05-12","01:45:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18E6B-005","Hannover - Magdeburg","<","Wefensleben","Eilsleben (b Magdeburg)",2025,2025,20,20,"2025-05-12","01:45:00","2025-05-12","04:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18E82-003","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg) Gbf","Eilsleben (b Magdeburg) Gbf",2025,2025,20,20,"2025-05-12","21:05:00","2025-05-12","23:00:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18E82-006","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg) Gbf","Eilsleben (b Magdeburg) Gbf",2025,2025,20,20,"2025-05-13","00:30:00","2025-05-13","02:00:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-07-17"]
[null,"DB InfraGO","18EAF-002","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,18,19,"2025-05-01","22:00:00","2025-05-09","04:00:00","7d, 6h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","18EAF-005","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,18,19,"2025-05-01","22:00:00","2025-05-09","04:00:00","7d, 6h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","18EE2-008","Rostock - Berlin","< >","Berlin-Karow Ost","Hohen Neuendorf West",2025,2025,50,50,"2025-12-08","21:00:00","2025-12-12","04:00:00","3d, 7h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18EE2-011","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2025,2025,50,50,"2025-12-08","21:00:00","2025-12-12","04:00:00","3d, 7h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","18EE2-014","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2025,2025,50,50,"2025-12-08","21:00:00","2025-12-12","04:00:00","3d, 7h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2023-10-16"]
[null,"DB InfraGO","1AEE8-001","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,14,14,"2025-03-31","22:00:00","2025-04-01","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","18F53-006","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,48,49,"2025-11-29","20:00:00","2025-12-01","04:00:00","1d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,6,7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","18FB0-003","Bremen - Hannover","<","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,13,14,"2025-03-26","23:00:00","2025-03-31","04:00:00","4d, 4h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5,6,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F95-001","Bremen - Hannover","<","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,14,14,"2025-04-01","23:00:00","2025-04-06","04:00:00","4d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F95-004","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Abstellbahnhof",2025,2025,14,15,"2025-04-06","23:00:00","2025-04-07","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F95-008","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Abstellbahnhof",2025,2025,15,15,"2025-04-10","23:00:00","2025-04-11","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-003","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,23,23,"2025-06-03","03:00:00","2025-06-03","06:00:00","0d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-007","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,23,23,"2025-06-06","23:00:00","2025-06-07","04:00:00","0d, 5h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-008","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Abstellbahnhof",2025,2025,23,23,"2025-06-06","23:00:00","2025-06-07","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-011","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,23,23,"2025-06-07","23:00:00","2025-06-08","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-014","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,23,24,"2025-06-08","23:00:00","2025-06-09","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-017","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,24,24,"2025-06-09","23:00:00","2025-06-10","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-020","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,24,24,"2025-06-10","23:00:00","2025-06-12","03:00:00","1d, 4h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","190DB-024","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Abstellbahnhof",2025,2025,24,24,"2025-06-13","23:00:00","2025-06-14","03:00:00","0d, 4h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","19026-027","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,25,25,"2025-06-17","23:00:00","2025-06-20","03:00:00","2d, 4h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","19026-030","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,25,25,"2025-06-20","23:00:00","2025-06-21","04:00:00","0d, 5h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F92-001","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,25,25,"2025-06-22","02:00:00","2025-06-22","05:00:00","0d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","1A3C2-001","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2024,2024,51,51,"2024-12-19","00:01:00","2024-12-20","23:59:00","1d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","1A3C1-001","Hamburg - Magdeburg","< >","Maschen Rbf (Msof)","Maschen Rbf (Msof)",2025,2025,50,50,"2025-12-08","00:01:00","2025-12-09","23:59:00","1d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","18E84-010","Berlin - Dresden",">","Blankenfelde (Kr Teltow-Fläming)","Zossen",2025,2025,39,39,"2025-09-27","00:30:00","2025-09-27","06:00:00","0d, 5h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-12-04"]
[null,"DB InfraGO","18F92-009","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,26,27,"2025-06-28","23:00:00","2025-07-01","05:00:00","2d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","1914A-002","Hannover - Magdeburg","< >","Braunschweig-Buchhorst","Schandelah",2025,2025,12,12,"2025-03-18","01:30:00","2025-03-18","04:30:00","0d, 3h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","18F92-012","Bremen - Hannover","<","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,27,28,"2025-07-04","23:00:00","2025-07-07","05:00:00","2d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F92-013","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,27,28,"2025-07-04","23:00:00","2025-07-07","05:00:00","2d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F92-016","Bremen - Hannover","<","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Pbf",2025,2025,28,28,"2025-07-08","23:00:00","2025-07-11","05:00:00","2d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2023-06-29"]
[null,"DB InfraGO","18F92-019","Bremen - Hannover","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Lehe Abstellbahnhof",2025,2025,28,28,"2025-07-11","23:00:00","2025-07-12","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-29"]
[null,"DB InfraGO",1.9130000000000001E-2,"Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,29,29,"2025-07-14","00:01:00","2025-07-15","23:59:00","1d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-06-08"]
[null,"DB InfraGO","1A3D1-001","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,36,37,"2025-09-06","00:01:00","2025-09-08","23:59:00","2d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2023-06-08"]
[null,"DB InfraGO","19290-001","Bremen - Hannover",">","Achim","Bremen-Sebaldsbrück",2025,2025,19,19,"2025-05-05","22:00:00","2025-05-06","06:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-18"]
[null,"DB InfraGO","19290-005","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Achim",2025,2025,19,19,"2025-05-08","00:00:00","2025-05-08","04:00:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4",null,"N",null,"2024-07-18"]
[null,"DB InfraGO","1A3D1-006","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,37,37,"2025-09-13","00:01:00","2025-09-13","23:59:00","0d, 23h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-06-08"]
[null,"DB InfraGO","1A3D1-007","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,37,37,"2025-09-14","00:01:00","2025-09-14","23:59:00","0d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-06-08"]
[null,"DB InfraGO","1A3D1-010","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,37,37,"2025-09-14","00:01:00","2025-09-14","23:59:00","0d, 23h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-06-08"]
[null,"DB InfraGO","1A3D0-003","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,40,40,"2025-10-03","00:00:00","2025-10-05","23:59:00","2d, 23h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-06-08"]
[null,"DB InfraGO","18E84-015","Berlin - Dresden","< >","Rangsdorf","Rangsdorf",2025,2025,40,40,"2025-09-29","21:00:00","2025-09-30","05:10:00","0d, 8h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-09-28"]
[null,"DB InfraGO","19FC2-004","Hamburg - Magdeburg","<","Hamburg-Harburg","Buchholz (Nordheide)",2025,2025,42,42,"2025-10-13","23:00:00","2025-10-16","06:00:00","2d, 7h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","19FD2-003","Hamburg - Magdeburg","<","Hamburg-Harburg","Buchholz (Nordheide)",2025,2025,48,49,"2025-11-30","21:40:00","2025-12-01","04:45:00","0d, 7h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","19FD2-006","Hamburg - Magdeburg",">","Buchholz (Nordheide)","Hamburg-Harburg",2025,2025,50,50,"2025-12-08","23:00:00","2025-12-10","06:00:00","1d, 7h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A0BF-002","Falkenberg - Dresden","< >","Röderau","Röderau",2025,2025,26,26,"2025-06-27","21:00:00","2025-06-27","23:30:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","1A0BF-004","Falkenberg - Dresden","<","Röderau","Röderau",2025,2025,26,26,"2025-06-27","21:00:00","2025-06-27","23:30:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-07-24"]
[null,"DB InfraGO","1A25B-002","Hamburg - Magdeburg","< >","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2025,2025,39,39,"2025-09-24","16:00:00","2025-09-26","16:00:00","2d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A25D-003","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2025,2025,37,37,"2025-09-08","12:00:00","2025-09-12","16:00:00","4d, 4h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A25E-003","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2025,2025,36,36,"2025-09-01","08:00:00","2025-09-05","16:00:00","4d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A261-003","Magdeburg - Falkenberg",">","Königsborn","Güterglück Stw Gkn",2025,2025,45,45,"2025-11-07","23:00:00","2025-11-08","02:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-09-29"]
[null,"DB InfraGO","1A3D2-002","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2025,2025,37,37,"2025-09-11","08:00:00","2025-09-12","16:00:00","1d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A3D2-004","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Meckelfeld",2025,2025,37,37,"2025-09-12","16:00:00","2025-09-12","19:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A3D2-007","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2025,2025,37,39,"2025-09-12","16:00:00","2025-09-22","16:00:00","10d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-06-07"]
[null,"DB InfraGO","1A261-004","Magdeburg - Falkenberg","<","Gommern","Königsborn",2025,2025,45,45,"2025-11-07","23:00:00","2025-11-08","02:00:00","0d, 3h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-07-06"]
[null,"DB InfraGO","1A261-007","Magdeburg - Falkenberg","<","Güterglück Stw Gkn","Gommern",2025,2025,45,45,"2025-11-08","21:00:00","2025-11-08","23:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2023-07-06"]
[null,"DB InfraGO","1A261-010","Magdeburg - Falkenberg",">","Königsborn","Gommern",2025,2025,45,45,"2025-11-08","23:00:00","2025-11-09","02:00:00","0d, 3h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-07-06"]
[null,"DB InfraGO","1A261-014","Magdeburg - Falkenberg","<","Rodleben","Güterglück",2025,2025,45,46,"2025-11-09","21:00:00","2025-11-10","01:00:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-07-06"]
[null,"DB InfraGO","190D4-001","Rostock - Berlin","< >","Löwenberg (Mark)","Fürstenberg (Havel)",2025,2025,17,17,"2025-04-23","22:00:00","2025-04-24","05:30:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-005","Rostock - Berlin","< >","Löwenberg (Mark)","Löwenberg (Mark)",2025,2025,17,17,"2025-04-24","02:00:00","2025-04-24","03:00:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-008","Rostock - Berlin",">","Seilershof","Fürstenberg (Havel)",2025,2025,17,17,"2025-04-24","23:00:00","2025-04-25","03:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-011","Rostock - Berlin","< >","Fürstenberg (Havel)","Fürstenberg (Havel)",2025,2025,17,17,"2025-04-25","03:00:00","2025-04-25","04:00:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-012","Rostock - Berlin","< >","Fürstenberg (Havel)","Neustrelitz Hbf",2025,2025,17,17,"2025-04-25","22:00:00","2025-04-26","05:30:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-016","Rostock - Berlin","<","Neustrelitz Hbf","Drewin",2025,2025,17,17,"2025-04-25","22:00:00","2025-04-25","23:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-12-04"]
[null,"DB InfraGO","190D4-019","Rostock - Berlin","<","Neustrelitz Hbf","Fürstenberg (Havel)",2025,2025,17,17,"2025-04-26","02:30:00","2025-04-26","05:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-023","Rostock - Berlin","<","Fürstenberg (Havel)","Gransee",2025,2025,17,18,"2025-04-27","22:30:00","2025-04-28","02:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","190D4-026","Rostock - Berlin","< >","Löwenberg (Mark)","Fürstenberg (Havel)",2025,2025,17,18,"2025-04-27","22:30:00","2025-04-28","06:00:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","1A794-001","Rostock - Berlin",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,46,46,"2025-11-15","20:00:00","2025-11-16","04:30:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","1A794-004","Rostock - Berlin","<","Biesdorfer Kreuz Süd","Berlin Eichgestell",2025,2025,46,47,"2025-11-16","20:00:00","2025-11-17","04:30:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-11-13"]
[null,"DB InfraGO","1A794-007","Rostock - Berlin","< >","Eichgestell Nord","Berlin Stadtforst",2025,2025,47,47,"2025-11-17","20:00:00","2025-11-19","04:30:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","1A794-008","Rostock - Berlin","< >","Berlin Eichgestell","Biesdorfer Kreuz Süd",2025,2025,47,47,"2025-11-17","20:00:00","2025-11-19","04:30:00","1d, 8h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","1A794-011","Rostock - Berlin","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,47,47,"2025-11-18","04:00:00","2025-11-19","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","1A794-015","Rostock - Berlin","< >","Biesdorfer Kreuz Süd","Berlin Eichgestell",2025,2025,47,47,"2025-11-20","04:00:00","2025-11-21","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","1A794-018","Rostock - Berlin","< >","Eichgestell Nord","Berlin Stadtforst",2025,2025,47,47,"2025-11-18","04:00:00","2025-11-19","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","1AAC1-003","Rostock - Berlin","< >","Lalendorf Ost","Lalendorf",2025,2025,19,19,"2025-05-07","23:15:00","2025-05-08","02:45:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","1AAC8-002","Rostock - Berlin","< >","Langhagen","Langhagen",2025,2025,19,19,"2025-05-08","22:00:00","2025-05-08","23:15:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","1AAC8-005","Rostock - Berlin","< >","Langhagen","Langhagen",2025,2025,19,19,"2025-05-08","23:15:00","2025-05-09","02:45:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","1AAC8-008","Rostock - Berlin","<","Lalendorf Ost","Langhagen",2025,2025,19,19,"2025-05-09","22:00:00","2025-05-09","23:15:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","1AAC8-009","Rostock - Berlin","< >","Langhagen","Langhagen",2025,2025,19,19,"2025-05-09","22:00:00","2025-05-09","23:15:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","1AAC8-012","Rostock - Berlin","< >","Langhagen","Langhagen",2025,2025,19,19,"2025-05-09","23:15:00","2025-05-10","02:45:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-06-12"]
[null,"DB InfraGO","19FC9-004","Berlin - Dresden","< >","Golßen (Niederlausitz)","Golßen (Niederlausitz)",2025,2025,42,42,"2025-10-14","22:00:00","2025-10-15","04:00:00","0d, 6h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-11-16"]
[null,"DB InfraGO","1AB7D-001","Rostock - Berlin",">","Grabowhöfe","Langhagen",2025,2025,12,12,"2025-03-22","01:10:00","2025-03-22","02:40:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","1AB7D-004","Rostock - Berlin",">","Grabowhöfe","Vollrathsruhe",2025,2025,12,12,"2025-03-22","22:45:00","2025-03-23","01:15:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","1AB7D-008","Rostock - Berlin","< >","Langhagen","Langhagen",2025,2025,12,12,"2025-03-23","01:15:00","2025-03-23","04:30:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","19FC9-007","Berlin - Dresden","< >","Golßen (Niederlausitz)","Golßen (Niederlausitz)",2025,2025,42,42,"2025-10-15","21:00:00","2025-10-16","00:30:00","0d, 3h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-11-16"]
[null,"DB InfraGO","19FC9-008","Berlin - Dresden",">","Luckau-Uckro","Baruth (Mark)",2025,2025,42,42,"2025-10-16","22:05:00","2025-10-17","06:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-11-16"]
[null,"DB InfraGO","1AB7D-011","Rostock - Berlin",">","Vollrathsruhe","Langhagen",2025,2025,12,13,"2025-03-23","22:45:00","2025-03-24","01:15:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","1AB7D-012","Rostock - Berlin","< >","Vollrathsruhe","Vollrathsruhe",2025,2025,12,13,"2025-03-23","22:45:00","2025-03-24","01:15:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","1AB7D-016","Rostock - Berlin","< >","Vollrathsruhe","Vollrathsruhe",2025,2025,13,13,"2025-03-24","01:15:00","2025-03-24","04:30:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","1AD79-007","Berlin - Dresden","< >","Genshagener Heide Mitte","Birkengrund",2025,2025,48,48,"2025-11-26","01:35:00","2025-11-26","03:05:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3",null,"N",null,"2023-05-16"]
[null,"DB InfraGO","1AD79-012","Berlin - Dresden","< >","Genshagener Heide Mitte","Großbeeren Süd",2025,2025,48,48,"2025-11-26","03:05:00","2025-11-26","04:35:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3",null,"N",null,"2023-05-16"]
[null,"DB InfraGO","1AD79-016","Berlin - Dresden","<","Genshagener Heide","Saarmund",2025,2025,48,48,"2025-11-26","03:05:00","2025-11-26","04:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2023-05-16"]
[null,"DB InfraGO","1AF90-003","Rostock - Berlin","< >","Langhagen","Langhagen",2025,2025,13,13,"2025-03-24","23:15:00","2025-03-25","02:45:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-06-19"]
[null,"DB InfraGO","1AF90-004","Rostock - Berlin","< >","Vollrathsruhe","Vollrathsruhe",2025,2025,13,13,"2025-03-24","23:15:00","2025-03-25","02:45:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-06-19"]
[null,"DB InfraGO","1AF90-007","Rostock - Berlin","< >","Vollrathsruhe","Vollrathsruhe",2025,2025,13,13,"2025-03-25","22:00:00","2025-03-25","23:15:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-06-19"]
[null,"DB InfraGO","1AF90-010","Rostock - Berlin","< >","Vollrathsruhe","Vollrathsruhe",2025,2025,13,13,"2025-03-25","23:15:00","2025-03-26","02:45:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-06-19"]
[null,"DB InfraGO","1B128-002","Berlin - Dresden","< >","Rangsdorf","Rangsdorf",2025,2025,37,37,"2025-09-08","21:10:00","2025-09-09","05:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-10-31"]
[null,"DB InfraGO","1B128-005","Berlin - Dresden","<","Zossen","Rangsdorf",2025,2025,37,37,"2025-09-10","21:10:00","2025-09-11","05:00:00","0d, 7h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-10-31"]
[null,"DB InfraGO","1B128-008","Berlin - Dresden","< >","Rangsdorf","Rangsdorf",2025,2025,37,37,"2025-09-11","21:10:00","2025-09-12","05:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2023-10-31"]
[null,"DB InfraGO","1B155-001","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2025,2025,37,39,"2025-09-08","06:00:00","2025-09-22","04:00:00","13d, 22h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-19"]
[null,"DB InfraGO","1B26D-001","Rostock - Berlin","<","Nassenheide","Oranienburg",2025,2025,24,24,"2025-06-14","07:00:00","2025-06-15","18:00:00","1d, 11h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1B26D-002","Rostock - Berlin","<","Oranienburg","Birkenwerder Nord",2025,2025,24,24,"2025-06-14","07:00:00","2025-06-15","18:00:00","1d, 11h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1B2E5-004","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,18,18,"2025-05-02","21:00:00","2025-05-03","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","1B3A8-002","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg",2024,2024,51,51,"2024-12-18","00:00:00","2024-12-18","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","1B36A-002","Rostock - Berlin","<","Schönfließ West","Berlin-Karow Ost",2025,2025,18,19,"2025-05-04","21:00:00","2025-05-05","05:00:00","0d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N"]
[null,"DB InfraGO","1B36A-005","Rostock - Berlin","<","Schönfließ West","Berlin-Karow Ost",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-11","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N"]
[null,"DB InfraGO","1B4EA-003","Rostock - Berlin","< >","Plaaz                               Abzw","Plaaz                               Abzw",2025,2025,12,12,"2025-03-21","22:40:00","2025-03-22","02:40:00","0d, 4h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-006","Rostock - Berlin","<","Laage (Meckl)","Plaaz                               Abzw",2025,2025,12,12,"2025-03-22","22:40:00","2025-03-23","06:20:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-009","Rostock - Berlin","< >","Laage (Meckl)","Laage (Meckl)",2025,2025,12,13,"2025-03-23","21:10:00","2025-03-24","04:40:00","0d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-010","Rostock - Berlin","<","Kavelstorf","Laage (Meckl)",2025,2025,12,13,"2025-03-23","21:10:00","2025-03-24","04:40:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-015","Rostock - Berlin","< >","Kavelstorf","Laage (Meckl)",2025,2025,13,13,"2025-03-24","21:30:00","2025-03-25","04:40:00","0d, 7h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-018","Rostock - Berlin","<","Kavelstorf","Laage (Meckl)",2025,2025,13,13,"2025-03-26","21:30:00","2025-03-27","04:40:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-022","Rostock - Berlin","< >","Kavelstorf","Kavelstorf",2025,2025,13,13,"2025-03-28","00:40:00","2025-03-28","04:40:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B4EA-026","Rostock - Berlin","< >","Kavelstorf","Laage (Meckl)",2025,2025,13,13,"2025-03-28","21:30:00","2025-03-29","06:20:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-10-23"]
[null,"DB InfraGO","1B8ED-004","Wilhelmshaven - Bremen","< >","Delmenhorst","Bremen-Neustadt",2025,2025,49,50,"2025-12-05","23:00:00","2025-12-08","04:00:00","2d, 5h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-07-18"]
[null,"DB InfraGO","1BA8A-002","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,19,19,"2025-05-05","12:00:00","2025-05-06","18:00:00","1d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA8A-005","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,19,19,"2025-05-10","00:00:00","2025-05-11","06:00:00","1d, 6h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-11-17"]
[null,"DB InfraGO","1BA8A-006","Rostock - Berlin",">","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,19,19,"2025-05-10","00:00:00","2025-05-11","06:00:00","1d, 6h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA8E-003","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,29,29,"2025-07-18","08:00:00","2025-07-18","11:00:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA8E-007","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,29,29,"2025-07-19","00:00:00","2025-07-20","06:00:00","1d, 6h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-11-17"]
[null,"DB InfraGO","1BA8E-010","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,31,31,"2025-08-01","08:00:00","2025-08-01","11:00:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA92-001","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,36,36,"2025-09-01","08:00:00","2025-09-01","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA94-002","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,43,44,"2025-10-23","22:00:00","2025-10-31","05:50:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-11-17"]
[null,"DB InfraGO","1BA94-005","Rostock - Berlin","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,43,43,"2025-10-24","08:00:00","2025-10-24","15:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5",null,"N",null,"2023-11-17"]
[null,"DB InfraGO","1BA94-008","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,44,44,"2025-11-02","16:00:00","2025-11-02","23:59:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA94-009","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,44,44,"2025-11-02","16:00:00","2025-11-02","23:59:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1B86A-046","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,47,47,"2025-11-23","08:00:00","2025-11-23","11:00:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA97-001","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,49,49,"2025-12-01","22:00:00","2025-12-02","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2023-11-17"]
[null,"DB InfraGO","1BBC7-001","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-09","20:00:00","2025-06-10","04:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N"]
[null,"DB InfraGO","1BBC7-004","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-09","23:30:00","2025-06-10","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N"]
[null,"DB InfraGO","1BBC7-009","Rostock - Berlin","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-10","23:30:00","2025-06-11","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N"]
[null,"DB InfraGO","1BBC7-012","Rostock - Berlin","<","Berlin-Karow Ost","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-11","20:00:00","2025-06-12","04:00:00","0d, 8h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N"]
[null,"DB InfraGO","1BBC7-015","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-12","20:00:00","2025-06-13","04:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N"]
[null,"DB InfraGO","1BBC7-016","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-12","20:00:00","2025-06-13","04:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N"]
[null,"DB InfraGO","1BBC7-019","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-12","23:30:00","2025-06-13","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N"]
[null,"DB InfraGO","1BBC7-024","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-13","20:00:00","2025-06-13","23:30:00","0d, 3h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5",null,"N"]
[null,"DB InfraGO","1BBC7-027","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-14","20:00:00","2025-06-15","04:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N"]
[null,"DB InfraGO","1BBC7-030","Rostock - Berlin","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,24,24,"2025-06-14","23:30:00","2025-06-15","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N"]
[null,"DB InfraGO","1C5B1-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,24,25,"2025-06-15","23:00:00","2025-06-20","05:00:00","4d, 6h","Periodical","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2023-11-10"]
[null,"DB InfraGO","1BA8A-010","Rostock - Berlin","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,19,19,"2025-05-09","20:00:00","2025-05-11","02:00:00","1d, 6h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1BA8A-011","Rostock - Berlin","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,19,19,"2025-05-10","00:00:00","2025-05-11","06:00:00","1d, 6h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","1A200-001","Hamburg - Magdeburg","< >","Glindenberg","Zielitz",2025,2025,14,14,"2025-04-03","23:30:00","2025-04-04","04:30:00","0d, 5h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-06-26"]
[null,"DB InfraGO","1A200-004","Hannover - Magdeburg","< >","Biederitz","Magdeburg Hbf",2025,2025,14,14,"2025-04-03","23:30:00","2025-04-04","01:45:00","0d, 2h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2023-06-26"]
[null,"DB InfraGO","14DE3-003","Hannover - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2025,7,18,"2025-02-10","09:30:00","2025-04-28","12:30:00","77d, 2h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-03-05"]
[null,"DB InfraGO","17A3C-008","Hannover - Magdeburg","<","Stendal Hauptbahnhof","Bindfelde Abzw",2025,2025,17,17,"2025-04-21","21:00:00","2025-04-21","22:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-07-22"]
[null,"DB InfraGO","18BE8-014","Falkenberg - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2025,2025,23,23,"2025-06-03","19:30:00","2025-06-04","04:30:00","0d, 9h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2023-08-30"]
[null,"DB InfraGO","168F3-008","Hamburg - Magdeburg","<","Angern-Rogätz","Zielitz",2025,2025,9,9,"2025-03-02","00:30:00","2025-03-02","02:30:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2023-08-08"]
[null,"DB InfraGO","16916-006","Hamburg - Magdeburg",">","Zielitz","Zielitz Stw B2",2025,2025,9,9,"2025-02-28","21:30:00","2025-03-01","00:30:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2023-07-13"]
[null,"DB InfraGO","1A261-017","Hannover - Magdeburg",">","Biederitz","Königsborn",2025,2025,45,45,"2025-11-07","21:00:00","2025-11-07","23:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2023-07-06"]
[null,"DB InfraGO","22814-003","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,25,31,"2025-06-20","22:00:00","2025-08-01","04:00:00","41d, 6h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-01-31"]
[null,"DB InfraGO","22814-006","Rostock - Berlin","< >","Oranienburg","Oranienburg",2025,2025,25,31,"2025-06-20","06:00:00","2025-08-01","22:00:00","42d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-01-31"]
[null,"DB InfraGO","22814-010","Rostock - Berlin","<","Oranienburg","Birkenwerder (b Berlin)",2025,2025,31,32,"2025-08-01","04:00:00","2025-08-04","03:00:00","2d, 23h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-01-31"]
[null,"DB InfraGO","229A7-005","Rostock - Berlin",">","Birkenwerder (b Berlin)","Oranienburg",2025,2025,22,22,"2025-05-31","01:00:00","2025-05-31","04:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-02-06"]
[null,"DB InfraGO","B845-004","Berlin - Dresden","< >","Glasower Damm Ost","Blankenfelde (Kr Teltow-Fläming)",2025,2025,37,37,"2025-09-10","23:00:00","2025-09-12","05:00:00","1d, 6h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N",null,"2024-02-13"]
[null,"DB InfraGO","14DE3-007","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Kläden (Kr Stendal)",2025,2025,17,17,"2025-04-22","07:00:00","2025-04-25","22:00:00","3d, 15h","Continuous","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-03-05"]
[null,"DB InfraGO","14DE3-009","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Osterburg",2025,2025,13,14,"2025-03-29","08:30:00","2025-03-31","12:30:00","2d, 3h","Periodical","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,6",null,"N"]
[null,"DB InfraGO","14DE3-012","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Kläden (Kr Stendal)",2025,2025,13,14,"2025-03-29","08:30:00","2025-03-31","12:30:00","2d, 3h","Periodical","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,6",null,"N",null,"2024-03-05"]
[null,"DB InfraGO","14DE3-017","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Kläden (Kr Stendal)",2025,2025,14,14,"2025-04-01","08:30:00","2025-04-02","12:30:00","1d, 4h","Periodical","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-05"]
[null,"DB InfraGO","23079-002","Rostock - Berlin","<","Waren (Müritz)","Waren (Müritz)",2025,2025,27,31,"2025-07-01","03:00:00","2025-08-01","04:00:00","31d, 1h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-19"]
[null,"DB InfraGO","23079-006","Rostock - Berlin","< >","Kargow","Grabowhöfe",2025,2025,27,31,"2025-07-02","22:00:00","2025-08-01","04:00:00","29d, 6h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-19"]
[null,"DB InfraGO","23079-012","Rostock - Berlin",">","Neustrelitz Hbf","Kargow",2025,2025,27,29,"2025-07-01","03:00:00","2025-07-18","04:00:00","17d, 1h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","26DBE-001","Hannover - Magdeburg","<","Groß Gleidingen","Peine",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-09"]
[null,"DB InfraGO","26DBE-004","Hannover - Magdeburg","<","Groß Gleidingen","Peine",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-09"]
[null,"DB InfraGO","26DCD-004","Bremen - Hannover","< >","Seelze Ost","Wunstorf",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","26DD3-001","Hannover - Magdeburg","<","Helmstedt","Frellstedt",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-25"]
[null,"DB InfraGO","26DD3-004","Hannover - Magdeburg","< >","Königslutter","Helmstedt",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-25"]
[null,"DB InfraGO","26E06-003","Hannover - Magdeburg",">","Lehrte","Lehrte",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","26E06-007","Hannover - Magdeburg","< >","Lehrte","Immensen-Arpke",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","26E06-010","Hannover - Magdeburg",">","Lehrte","Lehrte",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","26E0C-003","Hannover - Magdeburg","< >","Sandbach","Weddel (Braunschw)",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","26E1B-001","Hamburg - Magdeburg","<","Ehlershausen","Lehrte Nord",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","26E27-002","Hannover - Magdeburg","< >","Hannover Hbf","Lehrte",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","26E27-003","Hannover - Magdeburg","< >","Lehrte","Lehrte",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","26E2A-004","Hannover - Magdeburg","< >","Ramhorst","Lehrte",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","26E30-004","Hannover - Magdeburg","<","Königslutter","Schandelah",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-25"]
[null,"DB InfraGO","26E45-001","Bremen - Hannover","<","Brh-Speckenbütt","Bremerhaven-Wulsdorf",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26E48-002","Bremen - Hannover","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26E4E-003","Bremen - Hannover","< >","Bremerhaven-Wulsdorf","Stubben",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26E51-002","Bremen - Hannover","< >","Osterholz-Scharmbeck","Lübberstedt",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26E55-002","Bremen - Hannover","< >","Oldenbüttel","Bremen-Burg",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26E55-003","Bremen - Hannover","< >","Oldenbüttel","Bremen-Burg",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F35-001","Bremen - Hannover","<","Bremerhaven-Wulsdorf","Oldenbüttel",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F3B-002","Bremerhaven - Bremen","<","Bremen-Burg","Bremen-Vegesack",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,"C,,","R,,",null,"2,2,2",null,"weekdays: \t3,4",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F3E-001","Bremen - Hannover","<","Bremen Hbf","Bremen-Sebaldsbrück",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F41-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Einfahrt",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F44-004","Bremen - Hannover","< >","Bremen Hbf","Bremen-Mahndorf",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F47-001","Bremen - Hannover","<","Bremen-Sebaldsbrück","Baden (Kr Verden)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F4A-001","Bremen - Hannover","< >","Verden (Aller)","Rotenburg (Wümme)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F4A-002","Bremen - Hannover","< >","Verden (Aller)","Verden (Aller)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F50-001","Bremen - Hannover","< >","Rohrsen (b Nienburg)","Hagen (Han)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F50-005","Bremen - Hannover","<","Rohrsen (b Nienburg)","Hagen (Han)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F56-001","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26F59-003","Wilhelmshaven - Bremen","< >","Hude","Delmenhorst",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-25"]
[null,"DB InfraGO","26FEF-001","Bremen - Hannover","<","Dörverden","Nienburg (Weser)",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26FF2-001","Bremen - Hannover","<","Etelsen","Wahnebergen",2024,2024,51,51,"2024-12-21","21:00:00","2024-12-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","26FF2-002","Bremen - Hannover","< >","Wahnebergen","Etelsen",2024,2024,51,51,"2024-12-21","21:00:00","2024-12-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","27012-002","Bremen - Hannover","< >","Eystrup","Verden (Aller)",2024,2024,51,51,"2024-12-21","21:00:00","2024-12-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-03-22"]
[null,"DB InfraGO","270CF-002","Hannover - Magdeburg","<","Lehrte West","Lehrte",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","27102-002","Hannover - Magdeburg","< >","Weddel (Braunschw)","Fallersleben",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-04-26"]
[null,"DB InfraGO","2712C-003","Bremen - Hannover","< >","Neustadt a Rübenberge","Wunstorf",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","2748A-001","Hamburg - Magdeburg",">","Ashausen Abzw","Maschen Rbf (Mnof)",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","2748A-005","Hamburg - Magdeburg",">","Ashausen Abzw","Stelle",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","274F0-002","Hamburg - Magdeburg","< >","Stelle","Meckelfeld",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","274F0-003","Hamburg - Magdeburg","< >","Stelle","Meckelfeld",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","27503-003","Hamburg - Magdeburg","< >","Maschen Pbf","Hamburg-Harburg",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","27506-003","Hamburg - Magdeburg",">","Lüneburg","Winsen (Luhe)",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","2750B-002","Hamburg - Magdeburg","< >","Bad Bevensen","Lüneburg Gbf",2024,2024,51,52,"2024-12-22","21:00:00","2024-12-23","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","2750D-002","Hamburg - Magdeburg","< >","Buchholz (Nordheide)","Hamburg-Harburg",2024,2024,51,52,"2024-12-22","21:00:00","2024-12-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","27CE5-001","Bremen - Hannover",">","Hannover-Linden/Fischerhof","Lehrte Bahnhofsteil Ahlten",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","07:30:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-12"]
[null,"DB InfraGO","280C9-001","Hamburg - Magdeburg",">","Hamburg-Hausbruch","Hamburg-Neugraben",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","05:00:00","0d, 5h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-05"]
[null,"DB InfraGO","281ED-003","Bremen - Hannover","< >","Bremerhaven-Lehe Abstellbahnhof","Bremerhaven-Lehe Abstellbahnhof",2024,2024,50,51,"2024-12-15","00:00:00","2024-12-20","16:00:00","5d, 16h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","281ED-004","Bremen - Hannover","< >","Bremerhaven-Lehe Abstellbahnhof","Bremerhaven-Lehe Abstellbahnhof",2024,2024,50,51,"2024-12-15","00:00:00","2024-12-20","16:00:00","5d, 16h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","281ED-010","Bremen - Hannover","< >","Bremerhaven-Lehe Abstellbahnhof","Bremerhaven-Lehe Abstellbahnhof",2024,2024,51,51,"2024-12-17","18:00:00","2024-12-20","06:00:00","2d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","281ED-013","Bremen - Hannover","<","Bremerhaven-Lehe Abstellbahnhof","Bremerhaven-Lehe Abstellbahnhof",2024,2024,51,51,"2024-12-18","12:00:00","2024-12-18","15:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","281ED-017","Bremen - Hannover","<","Bremerhaven-Lehe Abstellbahnhof","Bremerhaven-Lehe Abstellbahnhof",2024,2024,51,51,"2024-12-19","22:00:00","2024-12-20","02:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","8051-035","Magdeburg - Falkenberg","< >","Güterglück","Rodleben",2025,2025,44,46,"2025-11-02","22:00:00","2025-11-16","05:00:00","13d, 7h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-05-08"]
[null,"DB InfraGO","28FCB-003","Hamburg - Magdeburg","< >","Stelle","Maschen Rbf (Msof)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-04-15"]
[null,"DB InfraGO","28FCF-001","Hannover - Magdeburg","<","Helmstedt","Frellstedt",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-25"]
[null,"DB InfraGO","28FCF-005","Hannover - Magdeburg","< >","Helmstedt Grenze","Helmstedt",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-25"]
[null,"DB InfraGO","2920F-001","Bremen - Hannover","<","Lindhorst (Schaumb-Lippe)","Wunstorf",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","2920F-006","Bremen - Hannover","<","Lindhorst (Schaumb-Lippe)","Wunstorf",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","2968B-002","Hamburg - Magdeburg",">","Uelzen","Uelzen",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-20"]
[null,"DB InfraGO","9C67-011","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Ost",2025,2025,45,46,"2025-11-07","04:00:00","2025-11-14","21:00:00","7d, 17h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-05-22"]
[null,"DB InfraGO","9CA3-011","Dresden - Děčín","< >","Schöna","Schöna",2025,2025,46,49,"2025-11-15","04:00:00","2025-12-02","22:00:00","17d, 18h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2023-05-22"]
[null,"DB InfraGO","2A9FC-002","Hamburg - Magdeburg","< >","Hmb-Wlb Abzw","Hmb-Wlb Abzw",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-04-11"]
[null,"DB InfraGO","2AA01-003","Hamburg - Magdeburg","< >","Hmb-Wlb Abzw","Hamburg Hbf",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-04-11"]
[null,"DB InfraGO","2ABCB-002","Hamburg - Magdeburg","< >","Winsen (Luhe)","Winsen (Luhe)",2024,2024,50,50,"2024-12-15","04:20:00","2024-12-15","05:20:00","0d, 1h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-04-15"]
[null,"DB InfraGO","2ABCB-003","Hamburg - Magdeburg","< >","Winsen (Luhe)","Winsen (Luhe)",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","04:20:00","0d, 4h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-15"]
[null,"DB InfraGO","2ACAA-002","Hamburg - Magdeburg","< >","Deutsch Evern","Bad Bevensen",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","07:00:00","0d, 7h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-09"]
[null,"DB InfraGO","2B377-002","Bremen - Hannover","< >","Haste","Wunstorf",2024,2024,50,50,"2024-12-15","00:10:00","2024-12-15","06:10:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-22"]
[null,"DB InfraGO","2B395-005","Berlin - Dresden","< >","Genshagener Heide Ost","Birkengrund Süd",2025,2025,39,50,"2025-09-24","00:00:00","2025-12-13","23:59:00","81d, 0h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","2B580-001","Wilhelmshaven - Bremen","<","Wüsting","Oldenburg (Oldb) Hbf",2024,2024,50,50,"2024-12-15","00:30:00","2024-12-15","04:40:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","2B580-005","Wilhelmshaven - Bremen","< >","Wüsting","Wüsting",2024,2024,50,50,"2024-12-15","04:40:00","2024-12-15","06:00:00","0d, 1h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","2B58C-003","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Hannover-Linden",2024,2024,51,51,"2024-12-16","00:30:00","2024-12-16","02:30:00","0d, 2h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-05-17"]
[null,"DB InfraGO","2B58C-006","Bremen - Hannover","< >","Hannover-Linden Hafen","Hannover-Linden Hafen",2024,2024,51,51,"2024-12-16","03:00:00","2024-12-16","06:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-05-17"]
[null,"DB InfraGO","2B58C-007","Bremen - Hannover","<","Hannover-Linden","Hannover-Linden Hafen",2024,2024,51,51,"2024-12-16","03:00:00","2024-12-16","06:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-05-17"]
[null,"DB InfraGO","2B661-008","Bremen - Hannover","< >","Wunstorf","Dedensen-Gümmer",2024,2024,50,50,"2024-12-15","02:30:00","2024-12-15","04:00:00","0d, 1h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-05-17"]
[null,"DB InfraGO","2B8F3-001","Wilhelmshaven - Bremen","< >","Delmenhorst","Wildeshausen",2024,2024,51,51,"2024-12-22","01:00:00","2024-12-22","06:55:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t7",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","2B8F5-003","Wilhelmshaven - Bremen","<","Bookholzberg","Hude",2024,2024,51,51,"2024-12-17","03:00:00","2024-12-17","04:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","22814-014","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Nassenheide",2025,2025,27,31,"2025-07-01","03:00:00","2025-08-01","04:00:00","31d, 1h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-01-31"]
[null,"DB InfraGO","2D359-004","Magdeburg - Falkenberg","< >","Trebnitz Strw","Lutherstadt Wittenberg-Piesteritz",2025,2025,42,42,"2025-10-18","22:00:00","2025-10-19","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","2D359-008","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf Ostseite","Lu Wittenberg-Piesteritz Werkbf Ostseite",2025,2025,42,42,"2025-10-18","22:00:00","2025-10-19","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","2D359-011","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf Ostseite","Lu Wittenberg-Piesteritz Werkbf Ostseite",2025,2025,42,42,"2025-10-18","22:00:00","2025-10-19","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","2D359-014","Magdeburg - Falkenberg","< >","Rodleben","Rodleben",2025,2025,42,42,"2025-10-18","22:00:00","2025-10-19","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","2D359-017","Magdeburg - Falkenberg","< >","Meinsdorf","Meinsdorf",2025,2025,42,42,"2025-10-18","22:00:00","2025-10-19","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","2E624-002","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Lutherstadt Wittenberg Hbf",2025,2025,38,44,"2025-09-20","08:00:00","2025-10-30","06:00:00","39d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","2EDF4-004","Magdeburg - Falkenberg","<","Roßlau Pbf","Meinsdorf",2025,2025,3,3,"2025-01-18","23:00:00","2025-01-19","04:00:00","0d, 5h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-10"]
[null,"DB InfraGO","2EDF4-008","Magdeburg - Falkenberg","< >","Roßlau Pbf","Meinsdorf",2025,2025,3,3,"2025-01-18","23:00:00","2025-01-19","04:00:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-10"]
[null,"DB InfraGO","235F6-006","Rostock - Berlin","< >","Kargow","Waren (Müritz)",2025,2025,26,27,"2025-06-26","05:15:00","2025-07-01","00:45:00","4d, 19h","Periodical","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,4,5,6,7",null,"N",null,"2024-01-31"]
[null,"DB InfraGO","32CF1-001","Hamburg - Magdeburg","< >","Uelzen Gbf","Uelzen",2025,2025,1,2,"2025-01-05","21:00:00","2025-01-06","05:00:00","0d, 8h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","32CF1-002","Hamburg - Magdeburg","< >","Uelzen Gbf","Uelzen Gbf",2025,2025,1,2,"2025-01-05","21:00:00","2025-01-06","05:00:00","0d, 8h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","1AA87-003","Bremen - Hannover","< >","Hannover-Waldheim","Misburg",2026,2026,18,20,"2026-05-01","22:00:00","2026-05-15","17:00:00","13d, 19h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-01-11"]
[null,"DB InfraGO","1AA87-006","Bremen - Hannover","< >","Hannover-Waldheim","Misburg",2026,2026,19,19,"2026-05-07","20:00:00","2026-05-08","05:00:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-01-11"]
[null,"DB InfraGO","1AA87-011","Bremen - Hannover","< >","Misburg","Hannover-Waldheim",2026,2026,20,20,"2026-05-12","21:00:00","2026-05-13","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-01-11"]
[null,"DB InfraGO","1B194-002","Bremen - Hannover","< >","Ahlem","Hannover Kurve",2025,2026,52,3,"2025-12-27","21:00:00","2026-01-13","10:00:00","16d, 13h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1B1AC-001","Bremen - Hannover",">","Seelze West","Ahlem",2026,2026,8,8,"2026-02-21","20:00:00","2026-02-22","06:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1B1BB-004","Bremen - Hannover","< >","Ahlem","Hannover-Linden",2025,2026,52,1,"2025-12-26","22:00:00","2026-01-04","06:00:00","8d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1B1BB-012","Bremen - Hannover","< >","Hannover-Linden","Ahlem",2026,2026,3,3,"2026-01-16","21:00:00","2026-01-17","21:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1B325-001","Bremen - Hannover","< >","Ahlem","Hannover-Linden",2026,2026,7,9,"2026-02-14","21:00:00","2026-02-23","05:00:00","8d, 8h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1B3E9-002","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Waldhausen",2025,2026,52,3,"2025-12-26","08:00:00","2026-01-16","20:00:00","21d, 12h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-08"]
[null,"DB InfraGO","1B3FB-001","Dresden - Děčín","< >","Dürrröhrsdorf","Pirna",2025,2026,50,14,"2025-12-14","00:00:00","2026-04-02","23:59:00","109d, 22h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-06-10"]
[null,"DB InfraGO","1B3E9-004","Hannover - Magdeburg","< >","Hannover-Wülfel","Waldhausen",2026,2026,2,2,"2026-01-10","08:00:00","2026-01-10","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2024-05-08"]
[null,"DB InfraGO","1B3E9-007","Bremen - Hannover",">","Hannover Bismarckstraße","Hannover-Linden",2026,2026,3,4,"2026-01-17","08:15:00","2026-01-24","15:55:00","7d, 7h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-05-08"]
[null,"DB InfraGO","1B42F-005","Bremen - Hannover","< >","Hannover-Linden","Hannover-Waldheim",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-08"]
[null,"DB InfraGO","1B3F6-004","Hannover - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2025,2026,50,29,"2025-12-14","00:00:00","2026-07-18","10:00:00","216d, 9h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1B613-004","Magdeburg - Falkenberg","<","Magdeburg-Buckau","Magdeburg Hbf",2026,2026,3,4,"2026-01-17","18:00:00","2026-01-25","14:00:00","7d, 20h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1B613-006","Hannover - Magdeburg","<","Magdeburg Südseite","Magdeburg Hbf",2026,2026,3,4,"2026-01-17","18:00:00","2026-01-25","14:00:00","7d, 20h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1B978-004","Magdeburg - Falkenberg","<","Magdeburg-Buckau","Magdeburg Hbf",2026,2026,9,9,"2026-02-23","08:00:00","2026-02-25","16:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1B992-006","Hannover - Magdeburg","<","Magdeburg Südseite","Magdeburg Hbf",2026,2026,12,13,"2026-03-16","08:00:00","2026-03-28","16:00:00","12d, 8h","Periodical","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1BE35-001","Hannover - Magdeburg","< >","Magdeburg-Neustadt","Niederndodeleben",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1BE35-003","Hannover - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1BE35-007","Magdeburg - Falkenberg","< >","Magdeburg Hbf","Magdeburg Südseite",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1BF3C-001","Falkenberg - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Kottewitz",2026,2026,13,13,"2026-03-23","20:00:00","2026-03-26","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2024-04-23"]
[null,"DB InfraGO","1BF3C-004","Falkenberg - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,36,36,"2026-08-31","20:00:00","2026-09-03","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1BF3C-005","Falkenberg - Dresden",">","Radebeul Abzw Az","Weinböhla",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1BF3C-008","Falkenberg - Dresden","<","Weinböhla","Radebeul-Naundorf",2026,2026,13,33,"2026-03-26","08:00:00","2026-08-11","16:00:00","138d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"Y",null,"2024-05-31"]
[null,"DB InfraGO","1BF3C-011","Falkenberg - Dresden","< >","Weinböhla","Weinböhla",2026,2026,33,36,"2026-08-12","08:00:00","2026-08-31","16:00:00","19d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1BF59-003","Falkenberg - Dresden","< >","Kottewitz","Radebeul-Naundorf                 (Abzw)",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-04-23"]
[null,"DB InfraGO","1BF59-006","Falkenberg - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,50,50,"2026-12-11","20:00:00","2026-12-12","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1BF59-010","Falkenberg - Dresden","< >","Weinböhla","Weinböhla",2026,2026,48,50,"2026-11-27","08:00:00","2026-12-11","16:00:00","14d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1C092-003","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,38,41,"2026-09-16","07:00:00","2026-10-05","16:00:00","19d, 9h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1C092-008","Falkenberg - Dresden","< >","Meißen","Coswig (bei Dresden) Stw 1",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1C092-009","Falkenberg - Dresden","< >","Niederau","Coswig (bei Dresden)",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1C092-012","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Coswig (bei Dresden)",2026,2026,40,40,"2026-09-28","04:00:00","2026-10-03","06:00:00","5d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1C107-001","Berlin - Dresden","< >","Elsterwerda","Elsterwerda-Biehla",2026,2026,37,40,"2026-09-13","23:40:00","2026-09-28","04:20:00","14d, 4h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-27"]
[null,"DB InfraGO","1C2D3-001","Falkenberg - Dresden","< >","Frauenhain","Elsterwerda",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1C2F9-001","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg) Gbf","Eilsleben (b Magdeburg) Gbf",2026,2026,33,35,"2026-08-13","08:00:00","2026-08-29","08:00:00","16d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1C2F9-005","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,33,35,"2026-08-14","22:00:00","2026-08-28","22:00:00","14d, 0h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1C2F9-008","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,35,36,"2026-08-28","22:00:00","2026-08-31","08:00:00","2d, 10h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1C2D3-006","Berlin - Dresden","< >","Elsterwerda","Frauenhain",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1C539-001","Falkenberg - Dresden","< >","Elsterwerda","Gröditz (b Riesa)",2026,2026,49,49,"2026-11-30","08:00:00","2026-12-04","18:00:00","4d, 10h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1C80D-001","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,28,29,"2026-07-10","17:15:00","2026-07-15","05:15:00","4d, 12h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","1C80D-006","Bremen - Hannover","< >","Wunstorf","Haste",2026,2026,32,32,"2026-08-06","09:00:00","2026-08-08","21:00:00","2d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","1C80D-008","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,33,35,"2026-08-13","19:00:00","2026-08-30","00:30:00","16d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","1CA02-002","Berlin - Dresden","< >","Grünauer Kreuz Süd","Grünauer Kreuz West",2026,2026,20,21,"2026-05-15","22:00:00","2026-05-18","04:00:00","2d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2023-12-15"]
[null,"DB InfraGO","1CA98-003","Falkenberg - Dresden","< >","Riesa","Seerhausen",2026,2026,21,21,"2026-05-18","21:00:00","2026-05-19","09:00:00","0d, 12h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-04-30"]
[null,"DB InfraGO","1CA98-007","Falkenberg - Dresden","< >","Riesa","Seerhausen",2026,2026,30,30,"2026-07-24","21:00:00","2026-07-25","09:00:00","0d, 12h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-04-30"]
[null,"DB InfraGO","1CA98-010","Falkenberg - Dresden","< >","Riesa","Riesa",2026,2026,21,30,"2026-05-19","09:00:00","2026-07-24","21:00:00","66d, 12h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-04-30"]
[null,"DB InfraGO","1CAAB-002","Berlin - Dresden","< >","Grünauer Kreuz Süd","Grünauer Kreuz West",2026,2026,25,26,"2026-06-15","22:00:00","2026-06-22","04:00:00","6d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-17"]
[null,"DB InfraGO","1CAD8-006","Berlin - Dresden","< >","Grünauer Kreuz West","Grünauer Kreuz Süd",2026,2026,39,39,"2026-09-26","22:00:00","2026-09-27","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-17"]
[null,"DB InfraGO","1CAFD-007","Bremen - Hannover","< >","Letter                            (Abzw)","Seelze West",2026,2026,32,33,"2026-08-07","23:00:00","2026-08-15","05:05:00","7d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1CAFD-010","Bremen - Hannover","< >","Seelze West","Wunstorf",2026,2026,33,33,"2026-08-15","03:00:00","2026-08-15","05:05:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1CB7B-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-24","04:00:00","3d, 7h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,5,6,7",null,"N",null,"2024-06-03"]
[null,"DB InfraGO","1CBAE-002","Bremen - Hannover","< >","Letter                            (Abzw)","Seelze West",2026,2026,41,42,"2026-10-05","23:10:00","2026-10-14","04:45:00","8d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1CBBC-001","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,31,31,"2026-07-29","08:00:00","2026-07-31","21:00:00","2d, 13h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CBF8-001","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg) Gbf","Eilsleben (b Magdeburg) Gbf",2026,2026,41,43,"2026-10-09","08:00:00","2026-10-19","08:00:00","10d, 0h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1CC41-003","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,27,28,"2026-07-05","23:00:00","2026-07-08","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-006","Bremen - Hannover","< >","Gümmerwald","Wunstorf",2026,2026,28,28,"2026-07-08","23:00:00","2026-07-10","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-009","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,28,29,"2026-07-10","23:00:00","2026-07-13","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CCC5-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-03"]
[null,"DB InfraGO","1CBF8-010","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,42,43,"2026-10-17","21:30:00","2026-10-19","04:30:00","1d, 7h","Periodical","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1D050-001","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,7,7,"2026-02-09","20:50:00","2026-02-11","04:20:00","1d, 7h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-06-14"]
[null,"DB InfraGO","1D050-004","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Klotzsche",2026,2026,18,21,"2026-04-30","20:50:00","2026-05-19","04:20:00","18d, 7h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-14"]
[null,"DB InfraGO","1D050-005","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,28,29,"2026-07-09","20:50:00","2026-07-15","04:20:00","5d, 7h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,4,5,6,7",null,"N",null,"2024-06-14"]
[null,"DB InfraGO","1D405-001","Falkenberg - Dresden","< >","Priestewitz","Leckwitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1D405-004","Berlin - Dresden","< >","Kottewitz","Leckwitz",2026,2026,37,39,"2026-09-07","05:00:00","2026-09-21","05:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1D405-009","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,39,39,"2026-09-21","05:00:00","2026-09-22","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1D41D-001","Falkenberg - Dresden","< >","Leckwitz","Weißig (b Großenhain)",2026,2026,47,47,"2026-11-21","08:00:00","2026-11-22","18:00:00","1d, 10h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1D41D-005","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,47,47,"2026-11-21","08:00:00","2026-11-22","18:00:00","1d, 10h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1D41D-009","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,47,48,"2026-11-22","18:00:00","2026-11-23","06:00:00","0d, 12h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1D41D-012","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Priestewitz",2026,2026,48,48,"2026-11-25","04:00:00","2026-11-27","04:00:00","2d, 0h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1D41D-013","Berlin - Dresden","< >","Kottewitz","Leckwitz",2026,2026,48,48,"2026-11-25","04:00:00","2026-11-27","04:00:00","2d, 0h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1CC41-017","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,29,31,"2026-07-16","04:35:00","2026-07-31","21:00:00","15d, 16h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-021","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,31,"2026-07-17","21:00:00","2026-07-31","21:00:00","14d, 0h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-030","Bremen - Hannover","< >","Seelze","Wunstorf",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","09:00:00","0d, 12h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-033","Bremen - Hannover","< >","Wunstorf","Seelze",2026,2026,31,31,"2026-08-01","09:00:00","2026-08-02","09:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-037","Bremen - Hannover","< >","Seelze West","Gümmerwald",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-040","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1CC41-042","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-05","23:00:00","2026-08-08","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1D4EE-001","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1D4EE-005","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,41,42,"2026-10-10","00:30:00","2026-10-12","04:30:00","2d, 4h","Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1D63D-001","Hannover - Magdeburg","< >","Werder (Havel)","Biederitz",2026,2026,20,20,"2026-05-16","21:00:00","2026-05-17","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","1DC0E-002","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DC0E-005","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-23"]
[null,"DB InfraGO","1DC42-003","Dresden - Děčín","< >","Dresden-Reick Abstellbahnhof","Dresden-Neustadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DC42-006","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DC42-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DC42-010","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Neustadt Gbf",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DCB3-003","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-23"]
[null,"DB InfraGO","1DCB3-008","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DD70-003","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,3,3,"2026-01-12","21:00:00","2026-01-15","04:00:00","2d, 7h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DD70-014","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,4,4,"2026-01-20","21:00:00","2026-01-25","04:00:00","4d, 7h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1DD70-018","Dresden - Děčín","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,6,6,"2026-02-02","21:00:00","2026-02-04","04:00:00","1d, 7h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1E1BD-007","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,2,3,"2026-01-09","21:00:00","2026-01-16","05:00:00","6d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1E4E6-001","Hamburg - Magdeburg","< >","Hamburg-Wilhelmsburg","Süderelbbrücke",2025,2025,50,51,"2025-12-14","00:00:00","2025-12-18","06:00:00","4d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","1E4E6-002","Hamburg - Magdeburg","< >","Hmb H Schaar Süd","Süderelbbrücke",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-13"]
[null,"DB InfraGO","1E4E6-003","Hamburg - Magdeburg","< >","Süderelbbrücke","Hmb H Schaar Süd",2025,2025,50,51,"2025-12-14","00:00:00","2025-12-18","06:00:00","4d, 6h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","1E552-003","Berlin - Dresden","< >","Walddrehna","Walddrehna",2026,2026,49,50,"2026-12-06","22:00:00","2026-12-07","22:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-04-12"]
[null,"DB InfraGO","1F270-001","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,22,22,"2026-05-26","08:00:00","2026-05-29","21:00:00","3d, 13h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","1F22B-001","Magdeburg - Falkenberg","< >","Coswig (Anh) Gbf","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,14,14,"2026-03-30","22:00:00","2026-04-01","06:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-06-26"]
[null,"DB InfraGO","1F22B-007","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2026,2026,23,23,"2026-06-02","06:00:00","2026-06-02","22:00:00","0d, 16h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2023-12-27"]
[null,"DB InfraGO","1F26D-005","Magdeburg - Falkenberg","< >","Elster (Elbe)","Lutherstadt Wittenberg-Piesteritz",2026,2026,17,17,"2026-04-25","20:00:00","2026-04-26","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1F26D-010","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg-Piesteritz Werkbf","Coswig (Anh) Gbf",2026,2026,18,18,"2026-04-27","20:00:00","2026-04-28","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1F26D-011","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2026,2026,18,18,"2026-04-28","20:00:00","2026-04-29","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1F26D-017","Magdeburg - Falkenberg","< >","Coswig (Anh) Gbf","Roßlau (Elbe) Gbf",2026,2026,18,18,"2026-05-02","20:00:00","2026-05-03","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2023-12-28"]
[null,"DB InfraGO","1F4BA-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-01-04"]
[null,"DB InfraGO","1F4BA-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2024-01-04"]
[null,"DB InfraGO","1F4BA-007","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-06","20:00:00","2026-02-07","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-01-04"]
[null,"DB InfraGO","1F4BA-011","Falkenberg - Dresden","< >","Cossebaude","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-01-04"]
[null,"DB InfraGO","1F4BA-014","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,7,7,"2026-02-13","20:00:00","2026-02-14","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-01-04"]
[null,"DB InfraGO","1F4BA-015","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,7,7,"2026-02-13","20:00:00","2026-02-14","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-01-04"]
[null,"DB InfraGO","1F4E5-001","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F4E5-006","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F4E5-008","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F50F-002","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","00:00:00","1d, 12h","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F50F-005","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","04:00:00","1d, 16h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F528-002","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F528-005","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-23"]
[null,"DB InfraGO","1F528-006","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F528-009","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F532-003","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","21:00:00","2026-02-10","05:00:00","0d, 8h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-02-01"]
[null,"DB InfraGO","1F26D-024","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Coswig (Anh) Gbf",2026,2026,19,19,"2026-05-04","20:00:00","2026-05-05","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1F26D-030","Magdeburg - Falkenberg","< >","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,19,19,"2026-05-07","20:00:00","2026-05-08","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","1F548-003","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-02-29"]
[null,"DB InfraGO","1F548-006","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-02-29"]
[null,"DB InfraGO","1F548-009","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-02-29"]
[null,"DB InfraGO","1F581-002","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,10,10,"2026-03-06","21:00:00","2026-03-08","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F581-005","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-12","21:00:00","2026-03-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F58D-001","Falkenberg - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F58D-005","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F59E-002","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,11,18,"2026-03-15","06:00:00","2026-05-03","16:00:00","49d, 9h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-23"]
[null,"DB InfraGO","1F59E-006","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5A4-002","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,12,12,"2026-03-16","06:00:00","2026-03-22","21:00:00","6d, 15h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5C3-002","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","08:00:00","0d, 3h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5C3-003","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","18:00:00","0d, 13h","Continuous","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5C3-014","Dresden - Děčín","< >","Freital Ost","Dresden Hbf",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5C3-017","Dresden - Děčín","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5FE-004","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F5FE-007","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F672-003","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F672-006","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-08","20:00:00","2026-05-09","04:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F672-010","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-09","04:00:00","2026-05-09","16:00:00","0d, 12h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F672-011","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Mitte",2026,2026,19,19,"2026-05-09","16:00:00","2026-05-10","04:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F672-014","Dresden - Děčín","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-09","18:00:00","2026-05-10","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F672-019","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,20,20,"2026-05-11","17:00:00","2026-05-12","04:00:00","0d, 11h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F722-002","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-23"]
[null,"DB InfraGO","1F722-005","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-23"]
[null,"DB InfraGO","1F722-007","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F748-004","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F748-007","Dresden - Děčín","< >","Dresden Hbf","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F748-008","Dresden - Děčín","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F543-003","Dresden - Děčín","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","1F89C-001","Falkenberg - Dresden","< >","Dresden-Neustadt","Dresden Mitte",2026,2026,14,15,"2026-04-05","21:00:00","2026-04-11","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1F89C-004","Falkenberg - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1F89C-007","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Neustadt Gbf",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1FA4A-002","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-17","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1FA4A-005","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1FA4A-006","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1FA4A-009","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-10","22:00:00","2026-03-12","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1FAD6-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,15,16,"2026-04-07","07:00:00","2026-04-16","17:00:00","9d, 10h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1FAD6-005","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","1FB4B-002","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,8,8,"2026-02-17","04:00:00","2026-02-21","06:00:00","4d, 2h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4,5,6",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1FB6A-001","Hannover - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","1FB56-011","Hannover - Magdeburg","< >","Stendal Hauptbahnhof","Bindfelde Abzw",2026,2026,38,39,"2026-09-18","21:00:00","2026-09-25","05:00:00","6d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","1FCFA-003","Rostock - Berlin","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-30"]
[null,"DB InfraGO","1FE81-001","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-14"]
[null,"DB InfraGO","1FB4B-006","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1FB4B-010","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2026,2026,9,10,"2026-02-28","06:00:00","2026-03-03","18:00:00","3d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,6,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","1FB4B-014","Falkenberg - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2026,2026,10,11,"2026-03-06","06:00:00","2026-03-10","18:00:00","4d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","20005-002","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,22,23,"2026-05-31","21:00:00","2026-06-05","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","20005-005","Dresden - Děčín","< >","Obervogelgesang","Pirna",2026,2026,24,26,"2026-06-14","21:00:00","2026-06-26","05:00:00","11d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","20189-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","20189-007","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","20189-008","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","20189-011","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-05-24"]
[null,"DB InfraGO","2027B-002","Dresden - Děčín","< >","Heidenau","Dresden-Reick",2026,2026,6,6,"2026-02-02","22:10:00","2026-02-04","04:10:00","1d, 6h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","20535-004","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau",2026,2026,1,9,"2026-01-03","04:00:00","2026-02-27","20:00:00","55d, 16h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","20535-007","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau",2026,2026,1,5,"2026-01-03","04:00:00","2026-01-31","20:00:00","28d, 16h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","20409-017","Hannover - Magdeburg","< >","Stendal Hauptbahnhof","Nahrstedt",2026,2026,23,28,"2026-06-05","21:00:00","2026-07-10","05:00:00","34d, 8h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20535-013","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2026,2026,6,9,"2026-02-02","07:00:00","2026-02-26","17:00:00","24d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","20409-019","Hannover - Magdeburg","< >","Stendal Hauptbahnhof","Nahrstedt",2026,2026,35,36,"2026-08-28","21:00:00","2026-09-04","05:00:00","6d, 8h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20535-016","Dresden - Děčín","< >","Bad Schandau Ost","Königst (Sä) Üst",2026,2026,9,9,"2026-02-26","20:00:00","2026-02-28","04:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","20535-018","Dresden - Děčín","< >","Bad Schandau Gr","Königst (Sä) Üst",2026,2026,9,9,"2026-02-26","20:00:00","2026-02-28","04:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","206A9-003","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,8,9,"2026-02-21","20:00:00","2026-02-26","04:00:00","4d, 8h","Periodical","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,6,7",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-008","Dresden - Děčín","< >","Obervogelgesang","Kurort Rathen (Kr Pirna)",2026,2026,9,11,"2026-02-26","04:00:00","2026-03-11","21:00:00","13d, 17h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-011","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,9,11,"2026-02-27","00:01:00","2026-03-11","04:00:00","12d, 3h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-015","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,11,11,"2026-03-11","21:00:00","2026-03-14","04:00:00","2d, 7h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-018","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,12,12,"2026-03-18","20:00:00","2026-03-22","04:00:00","3d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4,5,6",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-021","Dresden - Děčín","< >","Obervogelgesang","Pirna",2026,2026,12,14,"2026-03-22","04:00:00","2026-04-01","21:00:00","10d, 16h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-022","Dresden - Děčín","< >","Pirna Gbf","Pirna",2026,2026,13,14,"2026-03-29","22:00:00","2026-04-01","04:00:00","2d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206A9-026","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna Gbf",2026,2026,15,15,"2026-04-07","20:00:00","2026-04-11","04:00:00","3d, 8h","Periodical","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-06-06"]
[null,"DB InfraGO","206F2-005","Dresden - Děčín","< >","Bad Schandau","Kurort Rathen (Kr Pirna)",2026,2026,16,20,"2026-04-14","21:00:00","2026-05-12","04:30:00","27d, 7h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","206F2-009","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,16,17,"2026-04-17","04:30:00","2026-04-25","21:00:00","8d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","206F2-012","Dresden - Děčín","< >","Königst (Sä) Üst","Bad Schandau",2026,2026,16,17,"2026-04-17","22:00:00","2026-04-25","04:00:00","7d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","206F2-016","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,18,19,"2026-04-29","04:30:00","2026-05-08","21:00:00","9d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","206F2-019","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Königst (Sä) Üst",2026,2026,18,19,"2026-04-29","04:30:00","2026-05-08","21:00:00","9d, 16h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-16"]
[null,"DB InfraGO","206E8-002","Dresden - Děčín","< >","Obervogelgesang","Kurort Rathen (Kr Pirna)",2026,2026,9,11,"2026-02-26","04:00:00","2026-03-11","21:00:00","13d, 17h","Continuous","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-10"]
[null,"DB InfraGO","2078A-001","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2026,50,13,"2025-12-14","00:00:00","2026-03-27","21:00:00","103d, 21h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-31"]
[null,"DB InfraGO","207CD-003","Dresden - Děčín","< >","Pirna Gbf","Pirna Gbf",2026,2026,20,22,"2026-05-13","08:00:00","2026-05-26","16:00:00","13d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-07"]
[null,"DB InfraGO","207CD-008","Dresden - Děčín","< >","Heidenau","Pirna Gbf",2026,2026,20,21,"2026-05-16","05:00:00","2026-05-23","21:00:00","7d, 16h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-07"]
[null,"DB InfraGO","207CD-011","Dresden - Děčín","< >","Pirna","Heidenau",2026,2026,21,21,"2026-05-22","21:00:00","2026-05-24","05:00:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-06-07"]
[null,"DB InfraGO","20997-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,11,"2026-02-23","08:00:00","2026-03-09","16:00:00","14d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-007","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-011","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-02-27","07:00:00","2026-03-02","16:00:00","3d, 9h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-017","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-018","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-023","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-028","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20997-033","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-07","21:00:00","2026-03-08","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20B5C-001","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,4,4,"2026-01-19","08:00:00","2026-01-22","08:00:00","3d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4",null,"N",null,"2024-05-30"]
[null,"DB InfraGO","20BA3-003","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,12,"2026-03-16","09:00:00","2026-03-16","17:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","20BA3-008","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-17","08:00:00","2026-03-28","15:00:00","11d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","20BA3-010","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-17","08:00:00","2026-03-28","15:00:00","11d, 7h","Continuous","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","20BA3-014","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,12,"2026-03-17","08:00:00","2026-03-17","20:00:00","0d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","20B8B-004","Hannover - Magdeburg","< >","Tornitz Seehof","Magdeburg Hbf",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-27"]
[null,"DB InfraGO","20C8C-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20C8C-009","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20C8C-011","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20C8C-017","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20C8C-024","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-12","08:00:00","2026-06-12","17:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20D69-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","20D69-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","20D69-007","Falkenberg - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","20EDE-001","Hamburg - Magdeburg","< >","Schnega","Veerßen",2026,2026,29,33,"2026-07-17","21:30:00","2026-08-14","05:00:00","27d, 7h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","20EDE-004","Hamburg - Magdeburg","< >","Uelzen Gbf","Veerßen",2026,2026,29,33,"2026-07-17","21:30:00","2026-08-14","05:00:00","27d, 7h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","2103F-001","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,25,28,"2026-06-19","21:00:00","2026-07-10","21:00:00","21d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","2100C-005","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","2100D-001","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","2100D-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","21012-003","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,36,37,"2026-08-31","08:00:00","2026-09-11","16:00:00","11d, 8h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-01-25"]
[null,"DB InfraGO","21012-008","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,39,39,"2026-09-21","08:00:00","2026-09-22","16:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-27"]
[null,"DB InfraGO","21013-006","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,35,35,"2026-08-29","08:00:00","2026-08-29","18:00:00","0d, 10h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","210E1-001","Hamburg - Magdeburg","< >","Salzwedel","Wieren",2026,2026,35,37,"2026-08-28","20:00:00","2026-09-11","05:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-15"]
[null,"DB InfraGO","21340-003","Hamburg - Magdeburg","< >","Wolmirstedt","Zielitz Stw B2",2026,2026,39,40,"2026-09-22","20:30:00","2026-10-02","20:30:00","10d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-01-25"]
[null,"DB InfraGO","21340-006","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,39,40,"2026-09-22","20:30:00","2026-10-02","20:30:00","10d, 0h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-27"]
[null,"DB InfraGO","21793-002","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Birkenwerder (b Berlin)",2026,2026,36,37,"2026-09-06","06:00:00","2026-09-13","18:00:00","7d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","218FC-001","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück",2026,2026,39,39,"2026-09-26","20:00:00","2026-09-27","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-01-24"]
[null,"DB InfraGO","21A39-004","Berlin - Dresden","< >","Hennersdorf West","Doberlug-Kh Nord",2026,2026,42,42,"2026-10-15","21:00:00","2026-10-16","21:00:00","1d, 0h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","21AFD-001","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-27","04:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-006","Magdeburg - Falkenberg","< >","Dessau Gbf","Rodleben",2026,2026,36,36,"2026-09-04","21:00:00","2026-09-05","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-010","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe)",2026,2026,37,37,"2026-09-10","21:00:00","2026-09-11","05:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-015","Magdeburg - Falkenberg","< >","Dessau Gbf","Rodleben",2026,2026,37,37,"2026-09-12","13:00:00","2026-09-12","21:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-018","Magdeburg - Falkenberg","< >","Meinsdorf","Dessau Hbf",2026,2026,36,36,"2026-09-04","07:00:00","2026-09-04","15:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-021","Magdeburg - Falkenberg","< >","Meinsdorf","Dessau Hbf",2026,2026,37,37,"2026-09-12","05:00:00","2026-09-12","13:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-022","Magdeburg - Falkenberg","< >","Meinsdorf","Dessau Hbf",2026,2026,37,37,"2026-09-10","21:00:00","2026-09-11","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-025","Magdeburg - Falkenberg","< >","Dessau Gbf","Rodleben",2026,2026,37,37,"2026-09-12","21:00:00","2026-09-13","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21AFD-030","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Roßlau (Elbe)",2026,2026,36,40,"2026-09-04","06:00:00","2026-10-04","18:00:00","30d, 12h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21CBB-003","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6",null,"N",null,"2024-05-13"]
[null,"DB InfraGO","21D59-001","Falkenberg - Dresden","< >","Herzberg (Elster)","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,16,18,"2026-04-16","21:00:00","2026-04-30","21:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","21E8A-007","Rostock - Berlin","< >","Rostock Seehafen Süd","Rostock Seehafen Süd",2026,2026,18,21,"2026-05-01","07:00:00","2026-05-23","21:30:00","22d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-11"]
[null,"DB InfraGO","2225D-001","Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Pbf/Stw B 20",2026,2026,16,16,"2026-04-16","21:00:00","2026-04-18","03:00:00","1d, 6h","Periodical","Miscellaneous",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-03-19"]
[null,"DB InfraGO","20EC7-015","Rostock - Berlin","< >","Rostock Seehafen Süd","Bentwisch",2026,2026,40,42,"2026-10-02","23:15:00","2026-10-16","21:00:00","13d, 21h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-02-13"]
[null,"DB InfraGO","20EC7-021","Rostock - Berlin","< >","Bentwisch","Rostock Seehafen Süd",2026,2026,40,42,"2026-10-03","07:00:00","2026-10-16","16:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-02-13"]
[null,"DB InfraGO","22420-003","Magdeburg - Falkenberg","< >","Meinsdorf","Lutherstadt Wittenberg Hbf",2026,2026,20,20,"2026-05-15","21:30:00","2026-05-16","06:30:00","0d, 9h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","22420-007","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,20,20,"2026-05-15","21:30:00","2026-05-16","06:30:00","0d, 9h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-04-18"]
[null,"DB InfraGO","1DD70-019","Dresden - Děčín","< >","Dresden Mitte","Dresden Hbf",2026,2026,5,5,"2026-01-26","21:00:00","2026-01-28","04:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","22C9E-003","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg",2026,2026,19,20,"2026-05-09","21:00:00","2026-05-14","05:00:00","4d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,6,7",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-007","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg Betriebsbahnhof Süd",2026,2026,22,22,"2026-05-26","21:00:00","2026-05-29","05:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-010","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg",2026,2026,22,23,"2026-05-29","21:00:00","2026-06-01","05:00:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6,7",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-013","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg Betriebsbahnhof Süd",2026,2026,24,25,"2026-06-11","22:00:00","2026-06-17","06:00:00","5d, 8h","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-014","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg",2026,2026,24,25,"2026-06-12","00:00:00","2026-06-17","05:00:00","5d, 5h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-017","Hamburg - Magdeburg","< >","Meckelfeld Nord","Meckelfeld",2026,2026,25,25,"2026-06-17","05:00:00","2026-06-18","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-021","Hamburg - Magdeburg","< >","Meckelfeld","Meckelfeld Nord",2026,2026,26,26,"2026-06-22","05:00:00","2026-06-23","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-024","Hamburg - Magdeburg","< >","Meckelfeld","Meckelfeld Nord",2026,2026,26,26,"2026-06-24","21:00:00","2026-06-27","05:00:00","2d, 8h","Periodical","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4,5",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-027","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg Betriebsbahnhof Süd",2026,2026,27,27,"2026-06-30","21:00:00","2026-07-03","05:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22C9E-031","Hamburg - Magdeburg","< >","Meckelfeld","Meckelfeld Nord",2026,2026,28,28,"2026-07-06","21:00:00","2026-07-08","05:00:00","1d, 8h","Periodical","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-07"]
[null,"DB InfraGO","22E54-002","Hamburg - Magdeburg","< >","Lüneburg","Adendorf",2026,2026,18,20,"2026-05-01","21:00:00","2026-05-14","18:00:00","12d, 21h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-004","Hamburg - Magdeburg","< >","Ashausen Abzw","Maschen Rbf (Msof)",2026,2026,18,28,"2026-05-01","21:00:00","2026-07-10","21:00:00","70d, 0h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-05-03"]
[null,"DB InfraGO","22E54-010","Hamburg - Magdeburg","< >","Stelle","Maschen Pbf",2026,2026,18,23,"2026-05-01","21:00:00","2026-06-05","18:00:00","34d, 21h","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-02-07"]
[null,"DB InfraGO","22E54-026","Hamburg - Magdeburg","< >","Stelle","Maschen Rbf (Msof)",2026,2026,28,29,"2026-07-10","18:00:00","2026-07-14","18:00:00","4d, 0h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-033","Hamburg - Magdeburg","< >","Stelle","Stelle",2026,2026,18,23,"2026-05-01","21:00:00","2026-06-05","18:00:00","34d, 21h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-036","Hamburg - Magdeburg","< >","Stelle","Maschen Pbf",2026,2026,19,20,"2026-05-09","20:00:00","2026-05-11","06:00:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E57-009","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2026,2026,48,49,"2026-11-27","05:00:00","2026-11-30","05:00:00","3d, 0h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,5,6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-039","Hamburg - Magdeburg","< >","Stelle","Maschen Pbf",2026,2026,23,24,"2026-06-05","18:00:00","2026-06-10","17:00:00","4d, 23h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,5,6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-048","Hamburg - Magdeburg","< >","Uelzen Gbf","Celle",2026,2026,28,28,"2026-07-10","21:00:00","2026-07-11","12:00:00","0d, 15h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-050","Hamburg - Magdeburg","< >","Uelzen Gbf","Celle",2026,2026,28,28,"2026-07-11","12:00:00","2026-07-12","12:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-053","Hamburg - Magdeburg","< >","Bardowick","Deutsch Evern",2026,2026,28,28,"2026-07-10","21:00:00","2026-07-11","12:00:00","0d, 15h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-05-03"]
[null,"DB InfraGO","22E54-056","Hamburg - Magdeburg","< >","Deutsch Evern","Bardowick",2026,2026,28,28,"2026-07-11","12:00:00","2026-07-12","12:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-02-07"]
[null,"DB InfraGO","22E54-061","Hamburg - Magdeburg","< >","Stelle","Bardowick",2026,2026,28,28,"2026-07-11","12:00:00","2026-07-12","12:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-02-07"]
[null,"DB InfraGO","203FF-020","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,10,10,"2026-03-02","21:00:00","2026-03-03","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","20409-023","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,16,16,"2026-04-13","21:00:00","2026-04-14","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","23B3E-001","Rostock - Berlin","< >","Birkenwerder Nord","Nassenheide",2026,2026,46,50,"2026-11-13","21:00:00","2026-12-11","21:00:00","28d, 0h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","23B39-004","Rostock - Berlin","< >","Oranienburg","Oranienburg",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","21:00:00","7d, 0h","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","23B3D-001","Rostock - Berlin","< >","Berlin-Karow Ost","Hohen Neuendorf West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","23B3D-004","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","23B3D-007","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuendorf West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","23B3D-010","Rostock - Berlin","< >","Neustrelitz Hbf","Blankensee (Meckl)",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","23B3D-013","Rostock - Berlin","< >","Löwenberg (Mark)","Zehdenick (Mark)",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t5,6",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","23B5A-002","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","23B5A-005","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","23B5A-008","Rostock - Berlin","< >","Schönfließ West","Schönfließ West",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-08","14:00:00","3d, 17h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","23B5A-009","Rostock - Berlin","< >","Schönfließ West","Schönfließ West",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-08","14:00:00","3d, 17h","Continuous","Track & Rail",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","23B5A-012","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-21"]
[null,"DB InfraGO","24021-003","Rostock - Berlin","< >","Waren (Müritz)","Waren (Müritz)",2026,2026,32,40,"2026-08-03","08:00:00","2026-10-02","18:00:00","60d, 10h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-06-04"]
[null,"DB InfraGO","24036-003","Rostock - Berlin","< >","Kargow","Vollrathsruhe",2026,2026,46,50,"2026-11-13","23:00:00","2026-12-11","05:00:00","27d, 6h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","24036-008","Rostock - Berlin","< >","Nassenheide","Neustrelitz Hbf",2026,2026,46,50,"2026-11-13","22:45:00","2026-12-11","04:45:00","27d, 6h","Periodical","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-31"]
[null,"DB InfraGO","246B8-003","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,12,"2026-03-16","07:30:00","2026-03-20","14:30:00","4d, 7h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-02-23"]
[null,"DB InfraGO","24700-003","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,2,2,"2026-01-05","21:00:00","2026-01-07","05:00:00","1d, 8h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-02-26"]
[null,"DB InfraGO","24834-003","Berlin - Dresden","< >","Dresden Mitte","Dresden-Friedrichstadt",2026,2026,15,15,"2026-04-07","07:30:00","2026-04-10","14:30:00","3d, 7h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4,5",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","24834-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,15,15,"2026-04-07","07:30:00","2026-04-10","14:30:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","24834-007","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,15,15,"2026-04-07","07:30:00","2026-04-10","14:30:00","3d, 7h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","248CE-004","Falkenberg - Dresden","< >","Dresden-Cotta Bft","Dresden-Friedrichstadt",2026,2026,16,16,"2026-04-13","07:30:00","2026-04-16","14:30:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","248CE-008","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,16,16,"2026-04-13","07:30:00","2026-04-16","14:30:00","3d, 7h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-02-27"]
[null,"DB InfraGO","24AEA-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,19,19,"2026-05-04","07:30:00","2026-05-08","14:30:00","4d, 7h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-02-28"]
[null,"DB InfraGO","24EB0-002","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,26,26,"2026-06-22","07:30:00","2026-06-26","14:30:00","4d, 7h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-02-28"]
[null,"DB InfraGO","24EB0-005","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,26,26,"2026-06-22","07:30:00","2026-06-26","14:30:00","4d, 7h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-02-28"]
[null,"DB InfraGO","24FB2-003","Dresden - Děčín","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,29,29,"2026-07-14","00:15:00","2026-07-17","04:20:00","3d, 4h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4,5",null,"N",null,"2024-02-29"]
[null,"DB InfraGO","24FB2-004","Dresden - Děčín","< >","Dresden-Neustadt","Dresden Hbf",2026,2026,29,29,"2026-07-14","00:15:00","2026-07-17","04:20:00","3d, 4h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5",null,"N",null,"2024-02-29"]
[null,"DB InfraGO","24FC1-002","Dresden - Děčín","< >","Dresden-Neustadt","Dresden Hbf",2026,2026,31,31,"2026-07-29","23:40:00","2026-07-31","04:20:00","1d, 4h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-02-29"]
[null,"DB InfraGO","24FD2-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,35,35,"2026-08-24","07:30:00","2026-08-28","14:30:00","4d, 7h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-02-28"]
[null,"DB InfraGO","24FD2-004","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,35,35,"2026-08-24","07:30:00","2026-08-28","14:30:00","4d, 7h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-02-28"]
[null,"DB InfraGO","25E4A-001","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Gr",2026,2026,2,2,"2026-01-07","21:00:00","2026-01-09","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-12"]
[null,"DB InfraGO","29F74-002","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2026,2026,12,12,"2026-03-16","09:10:00","2026-03-16","18:50:00","0d, 9h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A097-003","Dresden - Děčín","< >","Bad Schandau Ost","Schmilka-Hir",2026,2026,12,45,"2026-03-17","00:01:00","2026-11-05","23:59:00","233d, 23h","Continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"Y",null,"2024-04-25"]
[null,"DB InfraGO","2A2D1-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,12,12,"2026-03-17","09:10:00","2026-03-22","17:10:00","5d, 8h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A2E0-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,13,14,"2026-03-23","09:10:00","2026-03-30","18:50:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1",null,"Y",null,"2024-05-14"]
[null,"DB InfraGO","2A2E0-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,16,21,"2026-04-13","09:10:00","2026-05-18","18:50:00","35d, 9h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1",null,"Y",null,"2024-05-14"]
[null,"DB InfraGO","2A2FF-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,16,16,"2026-04-14","09:10:00","2026-04-19","17:10:00","5d, 8h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2,3,4,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A3A6-003","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,41,41,"2026-10-06","09:10:00","2026-10-06","17:10:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A3A6-005","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,45,45,"2026-11-03","09:10:00","2026-11-05","17:10:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A4F2-003","Dresden - Děčín","< >","Bad Schandau Ost","Schöna",2026,2026,45,50,"2026-11-06","00:01:00","2026-12-12","23:59:00","36d, 23h","Continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A4FD-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,45,45,"2026-11-06","09:10:00","2026-11-08","17:10:00","2d, 8h","Periodical","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t5,6,7",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A4FD-003","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,46,46,"2026-11-10","09:10:00","2026-11-13","17:10:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3,4,5",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","2A4FD-006","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,49,49,"2026-12-01","09:10:00","2026-12-01","17:10:00","0d, 8h","Continuous","Bridge",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t2",null,"N",null,"2024-05-14"]
[null,"DB InfraGO","1B1BB-016","Bremen - Hannover","< >","Hannover-Linden","Hannover-Linden",2026,2026,1,3,"2026-01-04","06:00:00","2026-01-16","21:00:00","12d, 15h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-28"]
[null,"DB InfraGO","2BD9D-004","Berlin - Dresden","< >","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2026,2026,2,3,"2026-01-11","22:00:00","2026-01-13","05:00:00","1d, 7h","Periodical","Others",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","2BDB5-003","Berlin - Dresden","< >","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-15","05:00:00","1d, 7h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N"]
[null,"DB InfraGO","2C88D-001","Berlin - Dresden","< >","Luckau-Uckro","Luckau-Uckro",2026,2026,9,10,"2026-03-01","22:00:00","2026-03-03","03:45:00","1d, 5h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","2C911-001","Rostock - Berlin","< >","Oranienburg","Birkenwerder Nord",2026,2026,40,42,"2026-10-02","21:00:00","2026-10-16","21:00:00","14d, 0h","Continuous","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","2C911-004","Rostock - Berlin","< >","Hohen Neuendorf West","Birkenwerder Nord",2026,2026,41,41,"2026-10-05","01:30:00","2026-10-09","04:00:00","4d, 2h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-06-13"]
[null,"DB InfraGO","2C911-005","Rostock - Berlin","< >","Birkenwerder Nord","Hohen Neuend Sw",2026,2026,41,41,"2026-10-05","01:30:00","2026-10-09","04:00:00","4d, 2h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5",null,"N",null,"2024-06-13"]
[null,"DB InfraGO","2C911-008","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Bergfelde Ost",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-16","04:00:00","6d, 6h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","2D448-002","Berlin - Dresden","< >","Wünsdorf-Waldstadt","Baruth (Mark)",2026,2026,48,49,"2026-11-29","22:00:00","2026-12-02","04:00:00","2d, 6h","Periodical","Others",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N"]
[null,"DB InfraGO","2DB50-001","Rostock - Berlin","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2026,2026,14,14,"2026-04-01","08:00:00","2026-04-01","16:00:00","0d, 8h","Continuous","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3",null,"N"]
[null,"DB InfraGO","2DCBE-011","Rostock - Berlin","< >","Oranienburg","Nassenheide",2026,2026,19,20,"2026-05-10","23:30:00","2026-05-12","04:30:00","1d, 5h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","2DCBE-020","Rostock - Berlin","< >","Oranienburg","Oranienburg",2026,2026,21,21,"2026-05-19","23:00:00","2026-05-22","04:50:00","2d, 5h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4",null,"N",null,"2024-06-27"]
[null,"DB InfraGO","2DCBE-024","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Oranienburg",2026,2026,20,21,"2026-05-17","23:30:00","2026-05-19","04:30:00","1d, 5h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","2DCBE-027","Rostock - Berlin","< >","Oranienburg","Oranienburg",2026,2026,20,21,"2026-05-17","23:30:00","2026-05-19","04:30:00","1d, 5h","Periodical","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,7",null,"N"]
[null,"DB InfraGO","31C40-001","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,1,50,"2026-01-02","00:00:00","2026-12-11","23:59:00","343d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-10"]
[null,"DB InfraGO","31D79-002","Bremen - Hannover","< >","Hannover-Linden","Ronnenberg",2026,2026,4,4,"2026-01-23","23:20:00","2026-01-25","05:15:00","1d, 5h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-21"]
[null,"DB InfraGO","31E1A-003","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,3,3,"2026-01-16","21:00:00","2026-01-18","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-13"]
[null,"DB InfraGO","31E39-003","Dresden - Děčín","< >","Pirna","Kurort Rathen (Kr Pirna)",2026,2026,4,4,"2026-01-21","21:00:00","2026-01-23","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-13"]
[null,"DB InfraGO","31E7F-001","Dresden - Děčín","< >","Königst (Sä) Üst","Obervogelgesang",2026,2026,4,5,"2026-01-25","21:00:00","2026-01-26","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-03-13"]
[null,"DB InfraGO","3210F-002","Falkenberg - Dresden","< >","Großenhain Berl Bf","Weinböhla",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-22","01:00:00","2d, 4h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","3210F-005","Falkenberg - Dresden","< >","Weinböhla","Großenhain Berl Bf",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-23","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","3210F-008","Falkenberg - Dresden","< >","Großenhain Berl Bf","Weinböhla",2026,2026,4,4,"2026-01-22","21:00:00","2026-01-23","05:00:00","0d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","3210F-009","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,4,4,"2026-01-22","21:00:00","2026-01-23","05:00:00","0d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t4",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","32138-003","Falkenberg - Dresden","< >","Cossebaude","Cossebaude",2026,2026,5,5,"2026-01-26","21:00:00","2026-01-27","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","32138-006","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Radebeul-Naundorf",2026,2026,5,5,"2026-01-27","21:00:00","2026-01-28","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","32168-002","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,5,5,"2026-01-28","21:00:00","2026-01-29","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","321BB-002","Dresden - Děčín","< >","Bad Schandau","Kurort Rathen (Kr Pirna)",2026,2026,2,2,"2026-01-09","21:00:00","2026-01-11","05:00:00","1d, 8h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-12"]
[null,"DB InfraGO","321C8-002","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,29,32,"2026-07-15","05:15:00","2026-08-06","09:00:00","22d, 3h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-05-02"]
[null,"DB InfraGO","32292-001","Falkenberg - Dresden","< >","Radebeul Abzw Az","Cossebaude",2026,2026,5,5,"2026-01-30","21:00:00","2026-01-31","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-14"]
[null,"DB InfraGO","322B2-001","Falkenberg - Dresden","< >","Radebeul Abzw Az","Großenhain Berl Bf",2026,2026,5,6,"2026-02-01","21:00:00","2026-02-04","05:00:00","2d, 8h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2024-03-26"]
[null,"DB InfraGO","322B2-003","Falkenberg - Dresden","< >","Radebeul Nord","Radebeul Abzw Az",2026,2026,5,6,"2026-02-01","21:00:00","2026-02-02","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-03-26"]
[null,"DB InfraGO","322B2-004","Falkenberg - Dresden","< >","Weinböhla","Kottewitz",2026,2026,6,6,"2026-02-02","21:00:00","2026-02-03","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-03-26"]
[null,"DB InfraGO","322D6-004","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Blankenburg",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-13","04:00:00","1d, 6h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t3,4",null,"N"]
[null,"DB InfraGO","323BE-001","Falkenberg - Dresden","< >","Großenhain Berl Bf","Radebeul Abzw Az",2026,2026,6,6,"2026-02-04","21:00:00","2026-02-08","05:00:00","3d, 8h","Periodical","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4,6",null,"N",null,"2024-03-26"]
[null,"DB InfraGO","323BE-004","Falkenberg - Dresden","< >","Kottewitz","Weinböhla",2026,2026,6,6,"2026-02-04","23:00:00","2026-02-05","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-26"]
[null,"DB InfraGO","32427-002","Falkenberg - Dresden","< >","Niederau","Niederau",2026,2026,8,8,"2026-02-16","21:30:00","2026-02-18","05:30:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-06"]
[null,"DB InfraGO","32427-005","Falkenberg - Dresden","< >","Priestewitz","Coswig (bei Dresden) Stw 1",2026,2026,8,8,"2026-02-16","21:30:00","2026-02-18","05:30:00","1d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-05-06"]
[null,"DB InfraGO","32427-009","Falkenberg - Dresden","< >","Niederau","Coswig (bei Dresden) Stw 1",2026,2026,8,8,"2026-02-18","21:30:00","2026-02-20","05:30:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-05-06"]
[null,"DB InfraGO","32427-010","Falkenberg - Dresden","< >","Priestewitz","Coswig (bei Dresden) Stw 1",2026,2026,8,8,"2026-02-18","21:30:00","2026-02-20","05:30:00","1d, 8h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-05-06"]
[null,"DB InfraGO","32612-002","Dresden - Děčín","< >","Dresden-Reick Abstellbahnhof","Dresden Hbf",2026,2026,4,4,"2026-01-19","20:00:00","2026-01-21","04:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-06-17"]
[null,"DB InfraGO","32612-006","Dresden - Děčín","< >","Dresden-Reick Abstellbahnhof","Dresden Hbf",2026,2026,4,4,"2026-01-21","19:50:00","2026-01-25","04:00:00","3d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t3,4,5,6",null,"N",null,"2024-06-17"]
[null,"DB InfraGO","32612-015","Dresden - Děčín","< >","Dresden-Niedersedlitz Güteranlage  (DHD)","Dresden Hbf",2026,2026,4,5,"2026-01-25","19:50:00","2026-01-26","05:00:00","0d, 9h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-06-17"]
[null,"DB InfraGO","327BA-001","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,5,5,"2026-01-31","20:00:00","2026-02-01","04:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t6,7",null,"N",null,"2024-06-13"]
[null,"DB InfraGO","327BA-005","Falkenberg - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,5,6,"2026-02-01","20:00:00","2026-02-02","04:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-06-13"]
[null,"DB InfraGO","327C2-007","Dresden - Děčín","< >","Dresden Hbf","Dresden-Niedersedlitz Güteranlage  (DHD)",2026,2026,8,9,"2026-02-22","19:50:00","2026-02-23","04:00:00","0d, 8h","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,7",null,"N",null,"2024-07-17"]
[null,"DB InfraGO","32C49-001","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,12,12,"2026-03-16","21:30:00","2026-03-20","05:30:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","32C49-002","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,12,12,"2026-03-16","21:30:00","2026-03-20","05:30:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","32C59-003","Dresden - Děčín","< >","Pirna","Heidenau",2026,2026,14,14,"2026-03-30","21:00:00","2026-04-01","05:00:00","1d, 8h","Periodical","Track & Rail",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","32CB2-002","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t6,7",null,"N",null,"2024-05-29"]
[null,"DB InfraGO","32D07-002","Falkenberg - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,15,15,"2026-04-07","18:00:00","2026-04-12","03:00:00","4d, 9h","Periodical","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3,4,5,6",null,"N",null,"2024-04-17"]
[null,"DB InfraGO","32D2F-001","Rostock - Berlin","< >","Schönfließ West","Hohen Neuend Sw",2026,2026,45,47,"2026-11-08","22:00:00","2026-11-20","04:00:00","11d, 6h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N"]
[null,"DB InfraGO","32D9B-002","Hannover - Magdeburg","< >","Lehrte","Fallersleben",2026,2026,40,45,"2026-10-02","23:20:00","2026-11-06","21:00:00","34d, 22h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-25"]
[null,"DB InfraGO","32D9B-005","Hannover - Magdeburg","< >","Fallersleben","Lehrte",2026,2026,45,50,"2026-11-06","21:00:00","2026-12-11","21:00:00","35d, 0h","Continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-25"]
[null,"DB InfraGO","32D9B-006","Hannover - Magdeburg","< >","Fallersleben","Lehrte",2026,2026,45,50,"2026-11-06","21:00:00","2026-12-11","21:00:00","35d, 0h","Continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-25"]
[null,"DB InfraGO","32D2F-010","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2026,2026,49,50,"2026-12-06","22:00:00","2026-12-11","04:00:00","4d, 6h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,7",null,"N"]
[null,"DB InfraGO","32E0F-004","Berlin - Dresden","< >","Grünauer Kreuz Nord","Berlin-Grünau",2026,2026,13,14,"2026-03-28","22:00:00","2026-04-03","04:00:00","5d, 5h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,6,7",null,"N"]
[null,"DB InfraGO","32E0F-008","Berlin - Dresden","< >","Grünauer Kreuz Nord","Berlin-Grünau",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-14","04:00:00","3d, 6h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N"]
[null,"DB InfraGO","32D2F-011","Rostock - Berlin","< >","Schönfließ West","Hohen Neuend Sw",2026,2026,46,47,"2026-11-09","04:00:00","2026-11-20","21:00:00","11d, 17h","Continuous","Others",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","32D2F-014","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-11","04:00:00","6d, 7h","Continuous","Others",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","3346A-002","Berlin - Dresden","< >","Leckwitz","Kottewitz",2026,2026,17,17,"2026-04-20","21:30:00","2026-04-24","05:30:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","3347C-003","Falkenberg - Dresden","< >","Radebeul Abzw Az","Radebeul-Naundorf                 (Abzw)",2026,2026,19,19,"2026-05-05","21:00:00","2026-05-06","05:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-03-20"]
[null,"DB InfraGO","3347C-004","Falkenberg - Dresden","< >","Weinböhla","Radebeul Abzw Az",2026,2026,19,19,"2026-05-05","21:00:00","2026-05-06","05:00:00","0d, 8h","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-07-25"]
[null,"DB InfraGO","3347C-007","Falkenberg - Dresden","< >","Weinböhla","Radebeul Abzw Az",2026,2026,19,19,"2026-05-05","21:00:00","2026-05-06","05:00:00","0d, 8h","Continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-03-20"]
[null,"DB InfraGO","3349B-002","Dresden - Děčín","< >","Heidenau","Heidenau",2026,2026,20,20,"2026-05-11","21:00:00","2026-05-12","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-03-27"]
[null,"DB InfraGO","33510-004","Dresden - Děčín","< >","Dresden Hbf","Dresden-Reick",2026,2026,20,20,"2026-05-15","21:00:00","2026-05-16","01:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t5,6",null,"N",null,"2024-03-20"]
[null,"DB InfraGO","33510-006","Dresden - Děčín","< >","Dresden Hbf","Dresden-Reick",2026,2026,20,20,"2026-05-16","03:00:00","2026-05-16","05:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t6",null,"N",null,"2024-03-20"]
[null,"DB InfraGO","3356B-001","Dresden - Děčín","< >","Dresden Mitte","Dresden-Neustadt",2026,2026,21,21,"2026-05-20","21:00:00","2026-05-22","05:00:00","1d, 8h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-21"]
[null,"DB InfraGO","335CD-002","Berlin - Dresden","< >","Selchow West","Selchow Süd",2026,2026,11,12,"2026-03-13","22:00:00","2026-03-20","05:00:00","6d, 7h","Periodical","Others","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","335CD-005","Berlin - Dresden","< >","Schönefeld (bei Berlin) F-Bahn","Schönefeld (bei Berlin) F-Bahn",2026,2026,12,13,"2026-03-20","22:00:00","2026-03-27","05:00:00","6d, 7h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","335CD-006","Berlin - Dresden","< >","Schönefeld (bei Berlin) F-Bahn","Glasower Damm Ost",2026,2026,12,13,"2026-03-20","22:00:00","2026-03-27","05:00:00","6d, 7h","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","335CD-010","Berlin - Dresden","< >","Glasower Damm Ost","Schönefeld (bei Berlin) F-Bahn",2026,2026,13,16,"2026-03-27","22:00:00","2026-04-17","05:00:00","20d, 6h","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","335CD-013","Berlin - Dresden","< >","Glasower Damm Ost","Schönefeld (bei Berlin) F-Bahn",2026,2026,13,16,"2026-03-27","22:00:00","2026-04-17","05:00:00","20d, 6h","Continuous","Others",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"DB InfraGO","335CD-017","Berlin - Dresden","< >","Schönefeld (bei Berlin) F-Bahn","Schönefeld (bei Berlin) F-Bahn",2026,2026,16,17,"2026-04-17","22:00:00","2026-04-24","05:00:00","6d, 7h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","3369F-001","Falkenberg - Dresden","< >","Priestewitz","Coswig (bei Dresden) Stw 1",2026,2026,22,22,"2026-05-27","21:00:00","2026-05-29","05:00:00","1d, 8h","Periodical","Maintenance",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-03-21"]
[null,"DB InfraGO","335CD-023","Berlin - Dresden","< >","Schönefeld (bei Berlin) F-Bahn","Schönefeld (bei Berlin) F-Bahn",2026,2026,17,18,"2026-04-24","22:00:00","2026-05-01","05:00:00","6d, 7h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-07-29"]
[null,"DB InfraGO","3370C-001","Falkenberg - Dresden","< >","Leckwitz","Niederau",2026,2026,24,24,"2026-06-11","21:00:00","2026-06-12","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t4,5",null,"N",null,"2024-05-22"]
[null,"DB InfraGO","33711-002","Berlin - Dresden","< >","Glasower Damm Ost","Flughafen BER F-Bahn",2026,2026,22,23,"2026-05-31","22:00:00","2026-06-03","04:00:00","2d, 6h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2024-06-10"]
[null,"DB InfraGO","336F5-001","Hannover - Magdeburg","< >","Braunschweig Hbf","Wolfenbüttel",2026,2026,10,11,"2026-03-08","23:30:00","2026-03-11","04:50:00","2d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","336F5-006","Hannover - Magdeburg","< >","Braunschweig Hbf","Wolfenbüttel",2026,2026,11,12,"2026-03-15","23:45:00","2026-03-18","05:10:00","2d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2,7",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","336F5-010","Hannover - Magdeburg","< >","Salzgitter-Drütte","Braunschweig Hbf",2026,2026,12,12,"2026-03-18","23:45:00","2026-03-20","05:10:00","1d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-05-23"]
[null,"DB InfraGO","33804-001","Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,13,18,"2026-03-23","08:00:00","2026-04-30","18:00:00","38d, 9h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","337F2-004","Berlin - Dresden","< >","Elsterwerda","Elsterwerda",2026,2026,23,23,"2026-06-04","21:00:00","2026-06-06","05:00:00","1d, 8h","Periodical","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t4,5",null,"N",null,"2024-04-30"]
[null,"DB InfraGO","337F2-008","Berlin - Dresden","< >","Elsterwerda","Frauenhain",2026,2026,24,24,"2026-06-08","21:00:00","2026-06-10","00:00:00","1d, 3h","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-30"]
[null,"DB InfraGO","337F2-011","Berlin - Dresden","< >","Elsterwerda","Elsterwerda",2026,2026,24,24,"2026-06-09","00:00:00","2026-06-10","04:00:00","1d, 4h","Periodical","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-04-30"]
[null,"DB InfraGO","33827-001","Falkenberg - Dresden","< >","Leckwitz","Priestewitz",2026,2026,25,25,"2026-06-15","21:30:00","2026-06-17","05:30:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","33804-005","Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Pbf/Stw B 20",2026,2026,15,16,"2026-04-07","06:00:00","2026-04-16","18:00:00","9d, 12h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","33827-004","Falkenberg - Dresden","< >","Priestewitz","Leckwitz",2026,2026,25,25,"2026-06-17","21:30:00","2026-06-19","05:30:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-04-10"]
[null,"DB InfraGO","33877-001","Hamburg - Magdeburg","< >","Maschen Rbf (Msof)","Maschen Rbf (Msof)",2026,2026,42,43,"2026-10-16","22:00:00","2026-10-19","05:00:00","2d, 7h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N"]
[null,"DB InfraGO","33883-002","Hamburg - Magdeburg","< >","Maschen Rbf (Msof)","Maschen Rbf (Msof)",2026,2026,45,46,"2026-11-07","12:00:00","2026-11-09","18:00:00","2d, 6h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,6,7",null,"N"]
[null,"DB InfraGO","338B4-002","Hamburg - Magdeburg","< >","Maschen Rbf (Msof)","Maschen Rbf (Mswf)",2026,2026,46,47,"2026-11-13","20:00:00","2026-11-17","06:00:00","3d, 10h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,5,6,7",null,"N"]
[null,"DB InfraGO","338FC-003","Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,17,18,"2026-04-24","21:00:00","2026-04-30","05:00:00","5d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2,3,4,5,6,7",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","33905-002","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2026,2026,7,8,"2026-02-13","16:00:00","2026-02-16","07:00:00","2d, 15h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,5,6,7",null,"N"]
[null,"DB InfraGO","33934-002","Falkenberg - Dresden","< >","Priestewitz","Priestewitz",2026,2026,28,28,"2026-07-06","22:00:00","2026-07-08","06:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-10"]
[null,"DB InfraGO",33.909999999999997,"Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,41,41,"2026-10-06","21:00:00","2026-10-07","05:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-06-12"]
[null,"DB InfraGO",0.33910000000000001,"Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,41,41,"2026-10-06","21:00:00","2026-10-07","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t2,3",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","33951-002","Falkenberg - Dresden","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,41,41,"2026-10-07","18:00:00","2026-10-08","06:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","33951-005","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Pbf/Stw B 20",2026,2026,41,41,"2026-10-07","18:00:00","2026-10-08","06:00:00","0d, 12h","Continuous","Switch",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t3,4",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","3395C-001","Dresden - Děčín","< >","Dresden-Niedersedlitz Güteranlage  (DHD)","Pirna Gbf",2026,2026,31,31,"2026-07-27","21:00:00","2026-07-29","05:00:00","1d, 8h","Periodical","Catenary",null,null,null,"P",null,null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-24"]
[null,"DB InfraGO","3395C-005","Dresden - Děčín","< >","Heidenau","Heidenau",2026,2026,31,31,"2026-07-27","21:00:00","2026-07-29","05:00:00","1d, 8h","Periodical","Catenary",null,null,null,null,"Do",null,null,null,null,null,"weekdays: \t1,2",null,"N",null,"2024-04-24"]
[null,"DB InfraGO","3395C-006","Dresden - Děčín","< >","Dresden-Niedersedlitz Güteranlage  (DHD)","Pirna Gbf",2026,2026,31,31,"2026-07-28","00:30:00","2026-07-29","05:00:00","1d, 4h","Periodical","Catenary","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t2,3",null,"N",null,"2024-04-24"]
[null,"DB InfraGO","33961-002","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-13","05:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,"C,,","R,,",null,",,",null,"weekdays: \t1,2",null,"N",null,"2024-06-12"]
[null,"DB InfraGO","3394A-006","Hamburg - Magdeburg","< >","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2026,2026,9,10,"2026-02-24","10:00:00","2026-03-02","10:00:00","6d, 0h","Continuous","Others",null,"ST",null,null,null,null,null,null,null,null,"weekdays: \t1,2,3,4,5,6,7",null,"N"]
[null,"SZCZ","V-018067/22","Brno - Břeclav","< >","Vranovice","Hrušovany u Brna",2025,2025,34,35,"2025-08-19","00:00:00","2025-08-25","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-017598/22","Praha-Libeň - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,14,15,"2025-04-05","00:00:00","2025-04-09","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005787/24","Česká Třebová - Brno","< >","Odb Zádulka","Č.Třebová vjezd.sk.",2025,2025,12,12,"2025-03-19","00:00:00","2025-03-23","23:59:00","5 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"4 jen TV, 101,102,104,106,108,110,112,114 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-020750/21","Kolín - Brno-Maloměřice","< >","Brno-Maloměřice St.3","Brno-Královo Pole",2025,2025,18,22,"2025-05-01","00:00:00","2025-06-01","23:59:00","32 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-017551/22","Břeclav - Kúty","< >","Lanžhot","Břeclav os.n.",2025,2025,37,38,"2025-09-10","00:00:00","2025-09-19","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-020028/23","Děčín - Kolín","< >","Nymburk seř.n.","Odb Babín",2025,2025,20,22,"2025-05-17","00:00:00","2025-05-27","23:59:00","11 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"4. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-020027/23","Děčín - Kolín","< >","Odb Babín","Nymburk seř.n.",2025,2025,18,19,"2025-05-01","00:00:00","2025-05-11","23:59:00","11 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"3. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-020011/23","Děčín - Kolín","< >","Odb Babín","Nymburk seř.n.",2025,2025,14,14,"2025-04-02","00:00:00","2025-04-06","23:59:00","5 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"3. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-016490/23","Brno - Břeclav","< >","Odb Brno-Židenice z","Brno-Maloměřice St.3",2025,2025,30,35,"2025-07-26","00:00:00","2025-08-27","23:59:00","33 days","Continuous","Switch",null,"LT",null,null,"X",null,null,null,null,null,"2K + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-016482/23","Brno - Břeclav","< >","Brno-Maloměřice St.3","Odb Brno-Židenice z",2025,2025,14,18,"2025-04-01","00:00:00","2025-04-30","23:59:00","30 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1K + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005722/24","Česká Třebová - Brno","< >","Odb Zádulka","Česká Třebová",2025,2025,11,13,"2025-03-12","18:00:00","2025-03-24","06:00:00","12 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015859/23","Děčín - Praha-Libeň","< >","Děčín hl.n.","Povrly",2025,2025,8,8,"2025-02-21","00:00:00","2025-02-23","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015855/23","Děčín - Praha-Libeň","< >","Prackovice nad Labem","Lovosice",2025,2025,6,7,"2025-02-09","00:00:00","2025-02-11","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015842/23","Děčín - Kolín","< >","Sebuzín","Ústí n.L.-Střekov",2025,2025,24,25,"2025-06-15","00:00:00","2025-06-17","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015841/23","Děčín - Kolín","< >","Ústí n.L.-Střekov","Sebuzín",2025,2025,24,24,"2025-06-12","00:00:00","2025-06-14","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015838/23","Děčín - Kolín","< >","Litoměřice dolní n.","Polepy",2025,2025,17,17,"2025-04-23","00:00:00","2025-04-25","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005698/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2025,2025,3,4,"2025-01-19","18:00:00","2025-01-26","06:00:00","7 x 9 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015830/23","Děčín - Kolín","< >","Štětí","Liběchov",2025,2025,24,26,"2025-06-09","00:00:00","2025-06-28","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005685/24","Kolín - Brno-Maloměřice","< >","Brno-Královo Pole","Kuřim",2025,2025,16,17,"2025-04-17","00:00:00","2025-04-22","23:59:00","6 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-010093/19","Děčín - Praha-Libeň","< >","Děčín hl.n.","Povrly",2025,2025,27,35,"2025-07-01","00:00:00","2025-08-29","23:59:00","60 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007629/23","Děčín - Kolín","< >","Kostomlaty nad Labem","Lysá nad Labem",2025,2025,37,37,"2025-09-09","00:00:00","2025-09-12","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007626/23","Děčín - Kolín","< >","Stará Boleslav","Lysá nad Labem",2025,2025,38,38,"2025-09-17","00:00:00","2025-09-20","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007625/23","Děčín - Kolín","< >","Stará Boleslav","Dřísy",2025,2025,41,41,"2025-10-07","00:00:00","2025-10-10","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007622/23","Děčín - Kolín","< >","Všetaty","Dřísy",2025,2025,40,40,"2025-09-29","00:00:00","2025-10-02","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007619/23","Děčín - Kolín","< >","Mělník","Liběchov",2025,2025,43,43,"2025-10-23","00:00:00","2025-10-26","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007519/21","Děčín - Kolín","< >","Hoštka","Štětí",2025,2025,24,26,"2025-06-09","00:00:00","2025-06-28","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015288/23","Praha-Libeň - Česká Třebová","< >","Kostěnice","Moravany",2025,2025,48,48,"2025-11-25","00:00:00","2025-11-28","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-015236/23","Praha-Libeň - Česká Třebová","< >","Choceň","Brandýs n.O.předj.k.",2025,2025,45,46,"2025-11-05","00:00:00","2025-11-10","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007436/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2025,2025,12,13,"2025-03-17","18:00:00","2025-03-25","06:00:00","8 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007458/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2025,2025,31,32,"2025-08-03","18:00:00","2025-08-09","06:00:00","6 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007466/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2025,2025,36,37,"2025-09-01","18:00:00","2025-09-13","06:00:00","12 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-008121/24","Kolín - Brno-Maloměřice","< >","Brno-Maloměřice St.3","Brno-Maloměřice St.3",2025,2025,18,22,"2025-05-01","00:00:00","2025-06-01","23:59:00","32 days","Continuous","Switch",null,"ST",null,null,"X",null,null,null,null,null,"2d + TV, výh.: 52. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-007435/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2025,2025,9,46,"2025-03-01","00:00:00","2025-11-12","23:59:00","257 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005918/24","Praha-Libeň - Česká Třebová","< >","Česká Třebová","Odb Parník",2025,2025,13,15,"2025-03-28","18:00:00","2025-04-12","06:00:00","15 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,"X",null,null," ,X,X",null,null,"1,2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-012194/21","Děčín - Praha-Libeň","< >","Bohušovice nad Ohří","Lovosice",2025,2025,45,45,"2025-11-05","18:00:00","2025-11-08","06:00:00","3 x 5 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005297/24","Praha-Libeň - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2025,2025,21,23,"2025-05-20","00:00:00","2025-06-03","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005227/23","Česká Třebová - Brno","< >","Letovice","Skalice nad Svitavou",2025,2025,14,25,"2025-04-01","00:00:00","2025-06-16","23:59:00","77 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-003808/24","Kolín - Brno-Maloměřice","< >","Křižanov","Vlkov u Tišnova",2025,2025,10,11,"2025-03-05","00:00:00","2025-03-15","23:59:00","11 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-003805/24","Kolín - Brno-Maloměřice","< >","Křižanov","Vlkov u Tišnova",2025,2025,13,13,"2025-03-25","18:00:00","2025-03-28","06:00:00","3 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-003783/24","Kolín - Brno-Maloměřice","< >","Vlkov u Tišnova","Řikonín",2025,2025,11,12,"2025-03-16","00:00:00","2025-03-18","23:59:00","3 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004580/23","Česká Třebová - Brno","< >","Svitavy","Svitavy",2025,2025,32,33,"2025-08-07","00:00:00","2025-08-12","23:59:00","6 days","Continuous","Switch",null,"ST",null,null,null,null,null," ,X,X",null,null,"5,7 + TV, výh.: 20,21. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004836/23","Česká Třebová - Brno","< >","Letovice","Svitavy",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-19","23:59:00","3 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005902/24","Praha-Libeň - Česká Třebová","< >","Č.Třebová odj.sk.","Odb Parník",2025,2025,7,8,"2025-02-14","18:00:00","2025-02-17","06:00:00","3 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004551/23","Brno - Břeclav","< >","Vranovice","Šakvice",2025,2025,36,38,"2025-09-01","00:00:00","2025-09-16","23:59:00","16 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004799/23","Brno - Břeclav","< >","Brno-Maloměřice","Letovice",2025,2025,20,20,"2025-05-12","00:00:00","2025-05-15","23:59:00","4 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004787/23","Břeclav - Kúty","< >","Lanžhot st.hr.","Břeclav os.n.",2025,2025,37,37,"2025-09-08","00:00:00","2025-09-11","23:59:00","16 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005858/24","Praha-Libeň - Česká Třebová","< >","Odb Parník","Č.Třebová odj.sk.",2025,2025,2,2,"2025-01-07","00:00:00","2025-01-10","23:59:00","4 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004404/24","Břeclav - Wien","< >","Břeclav st.hr.","Břeclav os.n.",2025,2025,5,5,"2025-01-28","00:00:00","2025-01-30","23:59:00","3 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004035/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2025,2025,47,48,"2025-11-20","00:00:00","2025-11-25","23:59:00","6 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004023/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2025,2025,44,45,"2025-11-01","00:00:00","2025-11-03","23:59:00","3 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004756/23","Brno - Břeclav","< >","Popice z","Modřice",2025,2025,36,36,"2025-09-01","00:00:00","2025-09-02","23:59:00","10 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-002914/22","Kolín - Brno-Maloměřice","< >","Golčův Jeníkov","Sázavka z",2025,2025,17,17,"2025-04-24","00:00:00","2025-04-25","23:59:00","4 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-002775/24","Praha-Libeň - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,12,13,"2025-03-21","00:00:00","2025-03-25","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-003924/24","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2025,2025,6,7,"2025-02-03","00:00:00","2025-02-14","23:59:00","12 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004752/23","Brno - Břeclav","< >","Popice z","Modřice",2025,2025,21,21,"2025-05-19","00:00:00","2025-05-22","23:59:00","20 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-004711/23","Kolín - Brno-Maloměřice","< >","Ostrov nad Oslavou","Vlkov u Tišnova",2025,2025,21,21,"2025-05-22","00:00:00","2025-05-23","23:59:00","4 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-003872/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Brno hl.n.",2025,2025,29,30,"2025-07-19","00:00:00","2025-07-23","23:59:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-019613/21","Kolín - Brno-Maloměřice","< >","Kolín","Záboří nad Labem",2025,2025,9,10,"2025-02-28","00:00:00","2025-03-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2023-12-04T08:12:54"]
[null,"SZCZ","V-005288/24","Praha-Libeň - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,10,11,"2026-03-08","00:00:00","2026-03-09","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015278/23","Praha-Libeň - Česká Třebová","< >","Uhersko","Moravany",2026,2026,19,20,"2026-05-08","00:00:00","2026-05-11","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015274/23","Praha-Libeň - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-03","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015270/23","Praha-Libeň - Česká Třebová","< >","Moravany","Kostěnice",2026,2026,20,20,"2026-05-12","00:00:00","2026-05-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015256/23","Praha-Libeň - Česká Třebová","< >","Pardubice hl.n.","Kostěnice",2026,2026,22,22,"2026-05-27","00:00:00","2026-05-31","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015247/23","Praha-Libeň - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-08","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-012789/21","Praha-Libeň - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,48,50,"2026-11-28","00:00:00","2026-12-09","23:59:00","12 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. TZZ.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-012359/24","Kolín - Brno-Maloměřice","< >","Golčův Jeníkov","Vlkaneč",2026,2026,27,32,"2026-07-01","00:00:00","2026-08-05","23:59:00","36 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. \nzab. zař. TZZ v 1.TK.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-007567/23","Děčín - Kolín","< >","Dřísy","Všetaty",2026,2026,33,33,"2026-08-10","00:00:00","2026-08-15","23:59:00","6 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-007566/23","Děčín - Kolín","< >","Dřísy","Všetaty",2026,2026,30,31,"2026-07-22","00:00:00","2026-07-31","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-007565/23","Děčín - Kolín","< >","Všetaty","Dřísy",2026,2026,27,29,"2026-07-01","00:00:00","2026-07-16","23:59:00","16 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005099/24","Praha-Libeň - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 x 12 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005103/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,9,15,"2026-03-01","00:00:00","2026-04-07","23:59:00","38 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"zhlaví 2.TK směr Havl. Brod od nám. výh. č. 11, 13 po hrot výh. č. 15.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-007529/22","Kolín - Brno-Maloměřice","< >","Havlíčkův Brod","Pohled",2026,2026,30,31,"2026-07-22","00:00:00","2026-07-31","23:59:00","10 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005102/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,49,51,"2026-12-05","00:00:00","2026-12-18","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ 2.,1. TK.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005101/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,15,25,"2026-04-08","00:00:00","2026-06-20","23:59:00","74 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"1,3 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005087/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2026,2026,9,46,"2026-03-01","00:00:00","2026-11-14","23:59:00","259 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005075/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,12,13,"2026-03-17","18:00:00","2026-03-24","06:00:00","7 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005082/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,14,15,"2026-04-01","18:00:00","2026-04-07","06:00:00","6 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015944/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,20,21,"2026-05-15","18:00:00","2026-05-19","06:00:00","4 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015948/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,24,25,"2026-06-14","18:00:00","2026-06-16","06:00:00","2 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005063/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,29,30,"2026-07-19","18:00:00","2026-07-21","06:00:00","2 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005065/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,31,33,"2026-08-01","18:00:00","2026-08-11","06:00:00","9 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-005074/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,36,37,"2026-09-01","18:00:00","2026-09-13","06:00:00","12 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015961/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,40,42,"2026-10-01","18:00:00","2026-10-18","06:00:00","17 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018478/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018467/22","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018465/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003951/24","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,7,7,"2026-02-12","00:00:00","2026-02-14","23:59:00","3 x 12 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. \nzáhlaví a zhlaví 1. TK směr Havlíčkův Brod.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003948/24","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-11","23:59:00","3 x 12 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. \nzáhlaví a zhlaví 2. TK směr Havlíčkův Brod.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003947/24","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,49,49,"2026-12-02","00:00:00","2026-12-03","23:59:00","2 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. \nzáhlaví a zhlaví 1. TK směr Přibyslav.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018463/22","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018453/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006609/24","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,36,37,"2026-09-01","00:00:00","2026-09-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003944/24","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2026,2026,6,6,"2026-02-06","00:00:00","2026-02-08","23:59:00","3 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003903/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb Brno-Židenice z",2026,2026,11,47,"2026-03-10","00:00:00","2026-11-20","23:59:00","256 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"zhlaví 1. TK směr Odb Brno-Černovice zhl. Táborská od hrotu výh. č. 2 po nám. výh. č.6b, od nám. výh. č. 3 po nám. výh. č. 8 a 13\n\nzhlaví 2. TK směr Odb Brno-Černovice zhl. Táborská od hrotu výh. č. 4 po výh. č. 7 (mimo).",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003902/24","Brno - Břeclav","< >","Brno hl.n.","Odb Brno-Židenice z",2026,2026,48,49,"2026-11-28","00:00:00","2026-11-30","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003901/24","Brno - Břeclav","< >","Brno hl.n.","Odb Brno-Židenice z",2026,2026,13,14,"2026-03-28","00:00:00","2026-03-30","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003899/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Brno-Maloměřice",2026,2026,47,48,"2026-11-21","00:00:00","2026-11-23","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,null,null,null,null,"2024-07-11"]
[null,"SZCZ","V-006542/24","Děčín - Praha-Libeň","< >","Povrly","Děčín hl.n.",2026,2026,21,22,"2026-05-22","00:00:00","2026-05-25","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006541/24","Děčín - Praha-Libeň","< >","Děčín hl.n.","Povrly",2026,2026,21,21,"2026-05-18","00:00:00","2026-05-21","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006539/24","Děčín - Praha-Libeň","< >","Ústí n.L.hl.n.jih","Prackovice nad Labem",2026,2026,19,20,"2026-05-10","00:00:00","2026-05-13","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006538/24","Děčín - Praha-Libeň","< >","Prackovice nad Labem","Ústí n.L.hl.n.jih",2026,2026,20,20,"2026-05-14","00:00:00","2026-05-17","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006537/24","Děčín - Praha-Libeň","< >","Lovosice","Prackovice nad Labem",2026,2026,19,19,"2026-05-06","00:00:00","2026-05-09","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006536/24","Děčín - Praha-Libeň","< >","Prackovice nad Labem","Lovosice",2026,2026,18,19,"2026-05-02","00:00:00","2026-05-05","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006260/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2026,2026,49,53,"2026-12-05","00:00:00","2026-12-31","23:59:00","27 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006259/24","Praha-Libeň - Česká Třebová","< >","Česká Třebová","Odb Parník",2026,2026,7,8,"2026-02-14","00:00:00","2026-02-20","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006258/24","Praha-Libeň - Česká Třebová","< >","Odb Parník","Česká Třebová",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-13","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006252/24","Praha-Libeň - Česká Třebová","< >","Česká Třebová","Česká Třebová",2026,2026,8,9,"2026-02-21","00:00:00","2026-02-23","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"7,9 jen TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006249/24","Česká Třebová - Brno","< >","Odb Zádulka","Č.Třebová vjezd.sk.",2026,2026,16,47,"2026-04-14","00:00:00","2026-11-22","23:59:00","223 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003898/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb Brno-Židenice z",2026,2026,10,49,"2026-03-07","00:00:00","2026-12-04","23:59:00","273 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"záhlaví 1. TK směr Odb Brno-Černovice zhl. Táborská",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003896/24","Brno - Břeclav","< >","Odb B.-Čern.zhl.Táb.","Odb Brno-Židenice z",2026,2026,10,11,"2026-03-07","00:00:00","2026-03-09","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006248/24","Česká Třebová - Brno","< >","Odb Zádulka","Česká Třebová",2026,2026,16,16,"2026-04-14","00:00:00","2026-04-16","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006247/24","Česká Třebová - Brno","< >","Česká Třebová","Opatov",2026,2026,49,49,"2026-11-30","00:00:00","2026-12-04","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006246/24","Česká Třebová - Brno","< >","Česká Třebová","Odb Zádulka",2026,2026,48,48,"2026-11-25","00:00:00","2026-11-29","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003895/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Brno hl.n.",2026,2026,10,11,"2026-03-07","00:00:00","2026-03-09","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003752/24","Brno - Břeclav","< >","Brno-Maloměřice","Brno-Maloměřice",2026,2026,28,30,"2026-07-10","00:00:00","2026-07-24","23:59:00","15 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"1p,113.,114.,115.,116.,117.,118.,119.,120.,121.,122.,123. jen TV, 1v + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-006244/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2026,2026,11,16,"2026-03-15","00:00:00","2026-04-13","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003674/24","Česká Třebová - Brno","< >","Rájec-Jestřebí","Skalice nad Svitavou",2026,2026,42,43,"2026-10-16","00:00:00","2026-10-21","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-003673/24","Česká Třebová - Brno","< >","Skalice nad Svitavou","Rájec-Jestřebí",2026,2026,42,42,"2026-10-12","00:00:00","2026-10-16","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018256/22","Česká Třebová - Brno","< >","Skalice nad Svitavou","Letovice",2026,2026,19,20,"2026-05-04","00:00:00","2026-05-11","23:59:00","8 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař.  PZS km 199,369 (P6813).",null,null,null,"2024-07-11"]
[null,"SZCZ","V-018141/22","Česká Třebová - Brno","< >","Rájec-Jestřebí","Skalice nad Svitavou",2026,2026,15,16,"2026-04-06","00:00:00","2026-04-13","23:59:00","8 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. PZS v km 188,870 (P6807).",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016660/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2026,2026,28,43,"2026-07-11","00:00:00","2026-10-19","23:59:00","101 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016659/23","Kolín - Brno-Maloměřice","< >","Kutná Hora hl.n.","Kolín",2026,2026,14,28,"2026-04-02","00:00:00","2026-07-10","23:59:00","100 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016322/23","Česká Třebová - Brno","< >","Blansko","Rájec-Jestřebí",2026,2026,45,46,"2026-11-06","00:00:00","2026-11-10","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016321/23","Česká Třebová - Brno","< >","Rájec-Jestřebí","Blansko",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016320/23","Česká Třebová - Brno","< >","Blansko","Adamov",2026,2026,9,9,"2026-02-28","00:00:00","2026-03-01","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016319/23","Česká Třebová - Brno","< >","Adamov","Blansko",2026,2026,8,8,"2026-02-21","00:00:00","2026-02-22","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016318/23","Česká Třebová - Brno","< >","Adamov","Odb Svitava",2026,2026,7,7,"2026-02-14","00:00:00","2026-02-15","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016317/23","Česká Třebová - Brno","< >","Odb Svitava","Adamov",2026,2026,6,6,"2026-02-07","00:00:00","2026-02-08","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016316/23","Česká Třebová - Brno","< >","Odb Svitava","Brno-Maloměřice St.6",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-11","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016315/23","Česká Třebová - Brno","< >","Brno-Maloměřice St.6","Odb Svitava",2026,2026,6,6,"2026-02-02","00:00:00","2026-02-04","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016313/23","Brno - Břeclav","< >","Brno-Horní Heršpice","Brno-Horní Heršpice",2026,2026,27,33,"2026-07-01","00:00:00","2026-08-14","23:59:00","45 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"5.,707.,709.,709b,711.,713.,717. bez TV, 3.,3a,3b,5.,7.,9.,90.,603.,707.,709. jen TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016312/23","Brno - Břeclav","< >","Brno jih","Brno jih",2026,2026,38,42,"2026-09-14","00:00:00","2026-10-13","23:59:00","30 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"108a bez TV, 104.,106.,108.,110a jen TV, 110b,110c + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016016/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,48,"2026-08-15","00:00:00","2026-11-23","23:59:00","101 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"zhlaví 2. TK směr Havl. Brod, jeho část.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016015/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,31,33,"2026-08-01","00:00:00","2026-08-14","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-016007/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,33,"2026-08-11","18:00:00","2026-08-15","06:00:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015996/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,27,"2026-06-21","18:00:00","2026-06-29","06:00:00","8 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. \nzhlaví 2. TK směr Přibyslav.",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015982/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,48,49,"2026-11-24","00:00:00","2026-11-30","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá jen TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015981/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,31,48,"2026-08-01","00:00:00","2026-11-23","23:59:00","115 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015980/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,26,"2026-06-21","00:00:00","2026-06-27","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"3 bez TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015979/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,30,"2026-06-21","00:00:00","2026-07-21","23:59:00","31 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"3 jen TV, 1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015978/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,15,16,"2026-04-08","00:00:00","2026-04-14","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"1,3 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015933/23","Děčín - Kolín","< >","Poděbrady","Odb Babín",2026,2026,19,19,"2026-05-07","00:00:00","2026-05-10","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015932/23","Děčín - Kolín","< >","Libice nad Cidlinou","Poděbrady",2026,2026,18,19,"2026-05-03","00:00:00","2026-05-06","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015931/23","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-02","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015929/23","Kolín - Brno-Maloměřice","< >","Kolín","Velký Osek",2026,2026,13,14,"2026-03-25","00:00:00","2026-04-01","23:59:00","8 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015928/23","Kolín - Brno-Maloměřice","< >","Kutná Hora hl.n.","Kolín",2026,2026,28,28,"2026-07-06","00:00:00","2026-07-10","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015927/23","Kolín - Brno-Maloměřice","< >","Čáslav","Kutná Hora hl.n.",2026,2026,10,11,"2026-03-08","00:00:00","2026-03-11","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015926/23","Kolín - Brno-Maloměřice","< >","Golčův Jeníkov","Čáslav",2026,2026,12,12,"2026-03-16","00:00:00","2026-03-19","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015925/23","Kolín - Brno-Maloměřice","< >","Čáslav","Golčův Jeníkov",2026,2026,12,13,"2026-03-20","00:00:00","2026-03-23","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015924/23","Kolín - Brno-Maloměřice","< >","Kutná Hora hl.n.","Čáslav",2026,2026,11,11,"2026-03-12","00:00:00","2026-03-15","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015923/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2026,2026,29,29,"2026-07-13","00:00:00","2026-07-16","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015921/23","Kolín - Brno-Maloměřice","< >","Velký Osek","Kolín",2026,2026,13,14,"2026-03-29","00:00:00","2026-04-01","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015920/23","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,17,17,"2026-04-21","00:00:00","2026-04-24","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015919/23","Děčín - Kolín","< >","Poděbrady","Libice nad Cidlinou",2026,2026,16,17,"2026-04-17","00:00:00","2026-04-20","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015917/23","Děčín - Kolín","< >","Odb Babín","Poděbrady",2026,2026,16,16,"2026-04-13","00:00:00","2026-04-16","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015894/23","Brno - Břeclav","< >","Odb B.-Čern.zhl.Táb.","Odb Brno-Židenice z",2026,2026,47,47,"2026-11-21","00:00:00","2026-11-22","23:59:00","2 x 12 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015893/23","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb B.-Čern.zhl.Táb.",2026,2026,9,49,"2026-02-28","00:00:00","2026-12-04","23:59:00","280 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-11"]
[null,"SZCZ","V-015888/23","Děčín - Kolín","< >","Polepy","Hoštka",2026,2026,32,34,"2026-08-03","00:00:00","2026-08-22","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11"]
[null,"ÖBB Infra","81-B-78026","Wien - Ebenfurth - Sopron","< >","Ebenfurth",null,2025,2025,2,9,"2025-01-12","00:15:00","2025-02-24","04:40:00","43 days + 4,4 h","Periodical","Others","T","ST",null,null,null,"C",null,"T",0,null,"Fahrleitungsumbau für die Errichtung der Schleife Ebenfurth",null,"Y",null,null,"2024-07-23"]
[null,"ÖBB Infra","81-B-78924","Wien - Ebenfurth - Sopron","< >","Ebenfurth",null,2025,2025,49,50,"2025-12-06","00:00:00","2025-12-09",1,"4 days","Continuous","Others","T","ST",null,null,null,"C","R","T",0,null,"Fahrleitungsarbeiten an der Sammelschiene, Gleisneulage auf Bgl 103 und Tausch der Weichen 7+8","Affected Border: GYSEV\nAffected Ims: Ef  G\nDeviation Border(s): Wul G, Ls  G","Y",null,null,"2024-05-20"]
[null,"ÖBB Infra","81-B-65828","Wien - Hegyeshalom","< >","Wien Zvbf",null,2025,2025,39,43,"2025-09-27","08:00:00","2025-10-26","18:00:00","29 days + 11,0 h","Continuous","Others","T","ST",null,null,null,null,null,null,0,null,"Weichen- und Gleisneulage der Weichen 372 bis 387 in der gesamten Tfz-Harfe",null,"N",null,null,"2024-03-27"]
[null,"ÖBB Infra","81-B-65829","Wien - Hegyeshalom","< >","Zentralfriedhof","Wien Zvbf",2025,2025,16,17,"2025-04-19","07:00:00","2025-04-22","11:00:00","3 days + 4,0 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Weichenneulage Weiche 281+282",null,"N",null,null,"2024-06-04"]
[null,"ÖBB Infra","81-B-78399","Parndorf - Bratislava","< >","Parndorf","Staatsgrenze nächst Kittsee",2025,2025,19,19,"2025-05-05","07:50:00","2025-05-09","12:30:00","4 days + 4,7 h","Periodical","Maintenance","T","LT",null,null,null,"C","R","T",0,null,"Instandhaltungsarbeiten","Affected Border: 56\nAffected Ims: Bratislava Petrzalka\nDeviation Border(s): Devinska Nova Ves","Y",null,null,"2024-05-23"]
[null,"ÖBB Infra","81-B-78237","Parndorf - Bratislava","< >","Kittsee",null,2025,2025,40,50,"2025-10-03","20:00:00","2025-12-12","17:00:00","69 days + 22,0 h","Continuous","Others","T","ST","S",null,null,null,null,null,0,null,"Bahnsteigneuerrichtung neben Gleis 1",null,"N",null,null,"2024-05-07"]
[null,"ÖBB Infra","81-B-73988","Břeclav - Wien","< >","Wien Floridsdorf","Wien Meidling",2024,2025,50,26,"2024-12-15","00:00:00","2025-06-27",1,"194 days + 23,0 h","Continuous","Others","T","LT","S",null,null,null,null,null,0,null,"Bauphase 3:\nProgramm Schnellbahn Wien\nErrichten von Bahnsteiglängen 220m; Stromschiene; ETCS L2;\nReinvestitionen ",null,"N",null,null,"2024-07-30"]
[null,"ÖBB Infra","81-B-62309","Břeclav - Wien","< >","Wien Floridsdorf","Wien Meidling",2025,2025,1,50,"2025-01-01","00:00:00","2025-12-13",1,"347 days","Continuous","Others","T","LT",null,null,null,"C","R","T",0,null,"Programm Schnellbahn Wien\nErrichten von Bahnsteiglängen 220m; Stromschiene; ETCS L2;\nReinvestitionen ",null,"N",null,null,"2023-12-19"]
[null,"ÖBB Infra","81-B-65827","Wien - Hegyeshalom","< >","Wien Zvbf","Kledering",2025,2025,43,44,"2025-10-25","08:00:00","2025-11-02","18:00:00","8 days + 11,0 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Weichenneulage Weiche 440",null,"N",null,null,"2023-12-19"]
[null,"ÖBB Infra","81-B-65830","Wien - Hegyeshalom","< >","Wien Zvbf-Einfgr","Abzww Zur",2025,2025,16,17,"2025-04-19","07:00:00","2025-04-25","15:00:00","6 days + 8,0 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Weichen- und Gleisneulage Weiche 177+178, sowie Bgl 273",null,"N",null,null,"2023-12-19"]
[null,"ÖBB Infra","81-B-76417","Wien - Hegyeshalom","< >","Himberg",null,2024,2025,50,6,"2024-12-15","00:00:00","2025-02-08","23:00:00","55 days + 23,0 h","Continuous","Others","T","ST",null,null,null,null,null,null,0,null,"Vorarbeiten für Bahnhofumbau Himberg (Baufeldfreimachung Bgl 4+6) ",null,"N",null,null,"2024-06-03"]
[null,"ÖBB Infra","81-B-77497","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,8,10,"2025-02-21","23:15:00","2025-03-03","04:40:00","9 days + 5,4 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 3a/b/c",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77795","Wien - Hegyeshalom","< >","Himberg",null,2025,2025,3,50,"2025-01-19","04:40:00","2025-12-13",1,"328 days + 19,3 h","Continuous","Miscellaneous","T","ST",null,null,null,null,null,null,0,null,"Umbau Bahnhof Himberg",null,"N",null,null,"2024-07-30"]
[null,"ÖBB Infra","81-B-76450","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,6,50,"2025-02-08","23:15:00","2025-12-13",1,"308 days + 0,8 h","Continuous","Miscellaneous","T","LT",null,null,null,null,null,null,0,null,"Umbau Bahnhof Himberg",null,"N",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77562","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,19,23,"2025-05-05","04:40:00","2025-06-03","04:40:00","29 days","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 6/7a/b/c",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77587","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,33,34,"2025-08-14","22:00:00","2025-08-18","04:40:00","3 days + 6,7 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 11a",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77799","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,34,37,"2025-08-18","04:40:00","2025-09-12","12:00:00","25 days + 7,3 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 11b",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77836","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,39,39,"2025-09-22","04:40:00","2025-09-26","22:00:00","4 days + 17,3 h","Continuous","Miscellaneous","T","LT",null,null,null,null,"R","T",0,null,"Umbau Bahnhof Himberg Phase 12a",null,"N",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77847","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2026,50,46,"2025-12-14","00:00:00","2026-11-14","04:40:00","335 days + 4,7 h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,0,null,"Umbau Bahnhof Himberg",null,"N",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77858","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,23,24,"2025-06-03","04:40:00","2025-06-10","04:40:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 8a/b",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77479","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,6,8,"2025-02-08","23:15:00","2025-02-21","23:15:00","13 days","Periodical","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 2a/b/c/d",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-76420","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Himberg",2025,2025,4,4,"2025-01-20","00:10:00","2025-01-24","04:40:00","4 days + 4,5 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Vorarbeiten für Bahnhofumbau Himberg (Vormontage, sowie Rammen und Maststellen)",null,"N",null,null,"2024-03-25"]
[null,"ÖBB Infra","81-B-77890","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,24,25,"2025-06-10","04:40:00","2025-06-18","18:00:00","8 days + 13,3 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 9a/b/c",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77811","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,37,39,"2025-09-12","12:00:00","2025-09-22","04:40:00","9 days + 16,7 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 11c/d/e",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77580","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,32,33,"2025-08-08","23:15:00","2025-08-14","22:00:00","5 days + 22,8 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 10e/f",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77518","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,10,15,"2025-03-03","04:40:00","2025-04-07","04:40:00","34 days + 23,0 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 4a/b/c",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77554","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,15,19,"2025-04-07","04:40:00","2025-05-05","04:40:00","28 days","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 5a/b",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-77570","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,25,32,"2025-06-18","18:00:00","2025-08-08","23:15:00","51 days + 5,2 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 10a/b/c/d",null,"Y",null,null,"2024-05-29"]
[null,"ÖBB Infra","81-B-65429","Wien - Hegyeshalom","< >","Abzw Bl 1","Neusiedl am See",2025,2025,44,48,"2025-10-27","05:00:00","2025-11-24","05:00:00","28 days","Continuous","Others","T","LT",null,null,null,"C","R","T",0,null,"Brückensanierung in km 35,057 und in km 37,639 sowie Gleisneulage und Bahnsteigsanierung in der Hst Parndorf Ort",null,"N",null,null,"2023-12-19"]
[null,"ŽSR","56TT2311001","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"ETCS",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311002","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311003","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Komplexná rekonštrukcia diaľnično-železničného mosta",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311007","Bratislava - Štúrovo","< >","Dvory nad Žitavou","Dvory nad Žitavou",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Rekonštrukcia výhybiek č. 1,2,3,4,5,6,7,8 ",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311008","Kúty - Galanta","< >","Šelpice","Boleráz",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č.1",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311009","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311010","Kúty - Bratislava","< >","Malacky","Kúty",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia železničnej trate Devínska Nová Ves - štátna hranica SR/ČR + DOZZ, ETCS",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311011a","Kúty - Galanta","< >","Trnava","Križovany nad Dudváhom",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia Trnava - Križovany",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311012","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia dvoch úsekov železničnej trate štátna hranica ČR/SR - Devínska Nová Ves",null,null,null,"2023-11-23"]
[null,"ŽSR","56TT2311013","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Rekonštrukcia koľají č. 1, 2 (mimo DŽM)",null,null,null,"2023-11-23"]
[null,"GYSEV",5512955,"Sopron - Győr","< >","Győr","Csorna",2025,2025,17,17,"2025-04-22","07:00:00","2025-04-22","15:00:00","8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-04-30",null,null,"Re-routing via Hegyeshalom"]
[null,"GYSEV",5512956,"Sopron - Győr","< >","Győr","Csorna",2025,2025,17,17,"2025-04-23","07:00:00","2025-04-23","15:00:00","8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-04-30",null,null,"Re-routing via Hegyeshalom"]
[null,"GYSEV",5512957,"Sopron - Győr","< >","Győr","Csorna",2025,2025,17,18,"2025-04-24","07:00:00","2025-04-29","23:59:00","6d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Track and catenary reconstruction",null,null,null,"2024-04-30",null,null,"Re-routing via Hegyeshalom"]
[null,"GYSEV",5512958,"Sopron - Győr","< >","Csorna","Fertőszentmiklós",2025,2025,20,21,"2025-05-12","06:00:00","2025-05-22","23:59:00","11d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Catenary maintenance and ballast tamping",null,null,null,"2024-04-30",null,null,"Re-routing via Hegyeshalom"]
[null,"GYSEV",5512959,"Sopron - Győr","< >","Fertőszentmiklós","Sopron",2025,2025,37,40,"2025-09-08","06:00:00","2025-09-30","23:59:00","23d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Track and catenary reconstruction",null,null,null,"2024-04-30",null,null,"Re-routing via Hegyeshalom"]
[null,"GYSEV",5512960,"Sopron - Győr","< >","Kapuvár","Kapuvár",2025,2025,41,48,"2025-10-06","06:00:00","2025-11-30","23:59:00","56d","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,null,null,"2024-04-30"]
[null,"GYSEV",5512962,"Rajka - Hegyeshalom","< >","Hegyeshalom","Rajka",2025,2025,42,46,"2025-10-13",null,"2025-11-10",null,"29d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Track reconstruction",null,null,null,"2024-04-30"]
[null,"CFR",5312830,"Arad - Simeria","< >","Varadia","Batuta",2019,2025,9,7,"2019-02-27","00:00:00","2025-02-11","23:59:00","2177d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312831,"Arad - Simeria","< >","Barzava","Barzava Noua",2019,2025,25,7,"2019-06-19","00:00:00","2025-02-11","23:59:00","2065d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312832,"Arad - Simeria","< >"," Bătuța ","Bârzava",2024,2025,30,7,"2024-07-27","00:00:00","2025-02-11","23:59:00","200d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312833,"Arad - Simeria","< >","Vărădia","Bârzava Nouă",2024,2025,32,7,"2024-08-11","00:00:00","2025-02-11","23:59:00","185d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312834,"Simeria - Brasov","< >","Brașov","Stupini",2021,2025,47,39,"2021-11-25","00:00:00","2025-09-27","23:59:00","1403d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312835,"Simeria - Brasov","< >","Stupini","Bod",2023,2025,22,48,"2023-06-01","00:00:00","2025-11-27","23:59:00","911d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312836,"Simeria - Brasov","< >","Bod","Feldioara",2023,2025,14,48,"2023-04-03","00:00:00","2025-11-27","23:59:00","970d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312837,"Simeria - Brasov","< >","Feldioara","Apața",2023,2025,7,48,"2023-02-15","00:00:00","2025-11-27","23:59:00","1017d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312838,"Simeria - Brasov","< >","Feldioara","Apața",2025,2025,4,6,"2025-01-21","00:00:00","2025-02-05","23:59:00","16d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312839,"Simeria - Brasov","< >","Cata","Rupea",2023,2026,5,50,"2023-02-02","00:00:00","2026-12-12","23:59:00","1410d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312840,"Simeria - Brasov","< >","Cața","Beia",2023,2026,5,9,"2023-02-02","00:00:00","2026-03-01","23:59:00","1124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312841,"Simeria - Brasov","< >","Beia","Mureni",2023,2026,44,40,"2023-10-30","00:00:00","2026-09-30","23:59:00","1067d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312842,"Simeria - Brasov","< >","Beia","Mureni",2025,2025,39,39,"2025-09-22","00:00:00","2025-09-25","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312843,"Simeria - Brasov","< >","Cața","Archita",2024,2025,29,12,"2024-07-17","00:00:00","2025-03-21","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312844,"Simeria - Brasov","< >","Cața","Archita",2026,2026,40,50,"2026-10-01","00:00:00","2026-12-12","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312845,"Simeria - Brasov","< >","Archita ","Vînători ",2024,2025,29,12,"2024-07-17","00:00:00","2025-03-21","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312846,"Simeria - Brasov","< >","Archita","Vînători ",2026,2026,40,50,"2026-10-01","00:00:00","2026-12-12","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312847,"Simeria - Brasov","< >","Mureni","Vînători",2022,2026,45,40,"2022-11-09","00:00:00","2026-09-30","23:59:00","1422d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312848,"Simeria - Brasov","< >","Vînători","Albești",2023,2026,24,20,"2023-06-16","00:00:00","2026-05-12","23:59:00","1062d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312849,"Simeria - Brasov","< >","Albești","Sighișoara",2023,2025,24,20,"2023-06-16","00:00:00","2025-05-12","23:59:00","697d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312850,"Simeria - Brasov","< >","Apata","Augustin",2021,2025,15,33,"2021-04-15","00:00:00","2025-08-11","23:59:00","1580d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312851,"Simeria - Brasov","< >","Augustin","Racos",2023,2025,28,40,"2023-07-14","00:00:00","2025-09-30","23:59:00","810d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312852,"Simeria - Brasov","< >","Racos","Rupea",2022,2025,10,11,"2022-03-08","00:00:00","2025-03-12","23:59:00","1101d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312853,"Simeria - Brasov","< >","Racos-Rupea","Racos-Rupea",2024,2025,41,43,"2024-10-10","00:00:00","2025-10-25","23:59:00","381d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312854,"Timisoara - Craiova","< >","Remetea Mare","Timisoara Est",2025,2025,27,27,"2025-07-01","00:00:00","2025-07-02","23:59:00","2d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312855,"Timisoara - Craiova","< >","Lugoj ","Jabăr",2025,2025,30,30,"2025-07-24","00:00:00","2025-07-24","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312856,"Timisoara - Craiova","< >","Jabăr","Belinț",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312857,"Timisoara - Craiova","< >","Belinț","Chizătău",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312858,"Timisoara - Craiova","< >","Chizătău","Topolovat",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312859,"Timisoara - Craiova","< >","Lugoj – Costeiu Mare","Lugoj – Costeiu Mare",2025,2025,27,30,"2025-07-04","00:00:00","2025-07-24","23:59:00","21d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312860,"Timisoara - Craiova","< >","Timișoara Est","Timișoara Nord",2025,2025,27,28,"2025-07-01","00:00:00","2025-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312861,"Timisoara - Craiova","< >","Timișoara Est ","Timișoara Nord",2026,2026,27,28,"2026-07-01","00:00:00","2026-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312862,"Arad - Timisoara","< >","Ronaț Triaj Gr. D",null,2025,2025,14,15,"2025-04-01","00:00:00","2025-04-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312863,"Arad - Timisoara","< >","Ronaț Triaj Gr. D",null,2025,2025,36,37,"2025-09-01","00:00:00","2025-09-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312864,"Arad - Timisoara","< >","Timișoara Nord",null,2025,2025,36,37,"2025-09-01","00:00:00","2025-09-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312865,"Arad - Timisoara","< >","Orțișoara",null,2025,2025,18,19,"2025-05-01","00:00:00","2025-05-08",1.9993055555555554,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312866,"Arad - Timisoara","< >","Sânandrei",null,2025,2025,18,19,"2025-05-01","02:00:00","2025-05-08",2.0826388888888898,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312867,"Arad - Timisoara","< >","Sânandrei ","Hodoni",2025,2025,18,19,"2025-05-01","03:00:00","2025-05-08",2.1243055555555599,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312868,"Arad - Timisoara","< >","Șag ","Valea Viilor",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312869,"Arad - Timisoara","< >","Șag ","Valea Viilor",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312870,"Arad - Timisoara","< >","Aradul Nou","Zădăreni",2024,2025,32,32,"2024-08-08","00:00:00","2025-08-08","23:59:00","366d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312871,"Arad - Timisoara","< >","Valea Viilor ","Aradul Nou",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312872,"Arad - Timisoara","< >","Valea Viilor ","Aradul Nou",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312873,"Arad - Timisoara","< >","Aradul Nou","Arad",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312874,"Arad - Timisoara","< >","Aradul Nou ","Arad",2026,2026,31,32,"2026-08-01","00:00:00","2026-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312875,"Arad - Timisoara","< >","Aradul Nou","Arad",2026,2027,19,1,"2026-05-08","00:00:00","2027-01-08","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312876,"Arad - Timisoara","< >","Ronat Triaj Gr.D ","Vinga",2026,2026,17,19,"2026-04-24","00:00:00","2026-05-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312877,"Arad - Timisoara","< >","Ramificație Pod Mureș ","Glogovăț",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312878,"Arad - Timisoara","< >","Glogovăț","Arad",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312879,"Arad - Timisoara","< >","Glogovăț ","Arad",2026,2026,19,32,"2026-05-08","00:00:00","2026-08-08","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312880,"Arad - Timisoara","< >","Orțișoara","Aradul Nou",2026,2026,31,37,"2026-08-01","00:00:00","2026-09-08","23:59:00","39d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312881,"Biharkeresztes - Coslariu","< >","Oradea Est ","Oradea",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312882,"Biharkeresztes - Coslariu","< >","Oradea Est ","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312883,"Biharkeresztes - Coslariu","< >","Oradea","Episcopia Bihor",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312884,"Biharkeresztes - Coslariu","< >","Episcopia Bihor","Episcopia Bihor",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312885,"Biharkeresztes - Coslariu","< >","Episcopia Bihor","Frontiera",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312886,"Biharkeresztes - Coslariu","< >","Oradea","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312887,"Biharkeresztes - Coslariu","< >","Alesd","Telechiu",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312888,"Biharkeresztes - Coslariu","< >","Telechiu","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312889,"Biharkeresztes - Coslariu","< >","Oșorhei","Tileagd ",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312890,"Biharkeresztes - Coslariu","< >","Oradea","Oradea Vest",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312891,"Biharkeresztes - Coslariu","< >","Episcopia Bihor","Oradea Vest",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312892,"Biharkeresztes - Coslariu","< >","Oradea Est ","Ceica",2024,2026,5,53,"2024-02-01","00:00:00","2026-12-31","23:59:00","1065d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312893,"Biharkeresztes - Coslariu","< >","Episcopia Bihor","Biharia",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312894,"Biharkeresztes - Coslariu","< >","Aleșd","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312895,"Biharkeresztes - Coslariu","< >","Tileagd","Oșorhei",2026,2026,12,40,"2026-03-16","00:00:00","2026-10-01","23:59:00","200d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312896,"Biharkeresztes - Coslariu","< >","Oșorhei","Oradea Est",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312897,"Biharkeresztes - Coslariu","< >","Oradea Est","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312898,"Biharkeresztes - Coslariu","< >","Oradea ","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312899,"Biharkeresztes - Coslariu","< >","Episcopia Bihor","Frontieră Ungaria",2026,2026,40,53,"2026-10-01","00:00:00","2026-12-31","23:59:00","92d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312900,"Biharkeresztes - Coslariu","< >","Poieni","Ciucea",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312901,"Biharkeresztes - Coslariu","< >","Ciucea","Piatra Craiului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312902,"Biharkeresztes - Coslariu","< >","Piatra Craiului ","Bulz",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312903,"Biharkeresztes - Coslariu","< >","Bulz ","Bratca",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312904,"Biharkeresztes - Coslariu","< >","Bratca","Suncuius",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312905,"Biharkeresztes - Coslariu","< >","Suncuius","Vadul Crisului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312906,"Biharkeresztes - Coslariu","< >","Vadul Crisului","Alesd",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312907,"Biharkeresztes - Coslariu","< >","Cluj","Baciu Triaj",2024,2025,9,44,"2024-03-01","00:00:00","2025-10-31","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312908,"Biharkeresztes - Coslariu","< >","Cluj","Baciu Triaj",2025,2026,44,18,"2025-11-01","00:00:00","2026-04-30","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312909,"Biharkeresztes - Coslariu","< >","Cluj ","Baciu Triaj",2026,2026,18,36,"2026-05-01","00:00:00","2026-08-31","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312910,"Biharkeresztes - Coslariu","< >"," Baciu Triaj","Mera",2024,2025,9,44,"2024-03-01","00:00:00","2025-10-31","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312911,"Biharkeresztes - Coslariu","< >"," Baciu Triaj","Mera",2025,2026,44,18,"2025-11-01","00:00:00","2026-04-30","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312912,"Biharkeresztes - Coslariu","< >"," Baciu Triaj","Mera",2026,2026,18,36,"2026-05-01","00:00:00","2026-08-31","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312913,"Biharkeresztes - Coslariu","< >","Mera","Gârbău",2023,2025,44,44,"2023-11-01","00:00:00","2025-10-31","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312914,"Biharkeresztes - Coslariu","< >","Mera","Gârbău",2025,2026,44,18,"2025-11-01","00:00:00","2026-04-30","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312915,"Biharkeresztes - Coslariu","< >","Mera","Gârbău",2026,2026,18,36,"2026-05-01","00:00:00","2026-08-31","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312916,"Biharkeresztes - Coslariu","< >","Gârbău","Aghireș",2023,2025,44,44,"2023-11-01","00:00:00","2025-10-31","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312917,"Biharkeresztes - Coslariu","< >","Gârbău","Aghireș",2025,2026,44,18,"2025-11-01","00:00:00","2026-04-30","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312918,"Biharkeresztes - Coslariu","< >","Gârbău","Aghireș",2026,2026,18,36,"2026-05-01","00:00:00","2026-08-31","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312919,"Biharkeresztes - Coslariu","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312920,"Biharkeresztes - Coslariu","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312921,"Biharkeresztes - Coslariu","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5312922,"Biharkeresztes - Coslariu","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"NRIC",5312928,"Sofia - Promachon","< >","Blagoevgrad","Kulata",2025,2025,31,35,"2025-08-01T08:00:00",45505.333333333336,"2025-08-30T15:00:00",45899.625,"29d + 07h 00min","Continuous","Track & Rail","T",null,null,null,null,"C,C,C",null,null,null,null,"Full Interuption of the traffic",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312932,"Sofia - Plovdiv","< >","Sofia","Septemvri",2024,2025,50,50,"2024-12-14T23:00:00",45640.958333333336,"2025-12-13T22:45:00",46004.947916666664,"363d + 23h 45min","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Full interuption of the traffic along one track",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312933,"Sofia - Promachon","< >","Volujak","Sofia",2024,2025,50,50,"2024-12-14T23:00:00",45640.958333333336,"2025-12-12T23:00:00",46003.958333333336,"363d + 00h 00min","Continuous","Track & Rail",null,"LT+ST",null,null,null,null,null,null,"60,,",null,"Full interuption of the traffic along one track",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312934,"Sofia - Promachon","< >","Sofia","Sofia",2024,2025,50,50,"2024-12-14T23:00:00",45640.958333333336,"2025-12-12T23:00:00",46003.958333333336,"363d + 00h 00min","Continuous","Track & Rail",null,"ST",null,null,null,null,null,",B,B","60,,",null,"Partial interuptin of station tracks",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312935,"Ruse - Karnobat","< >","Provadia","Kaspichan",2024,2025,50,27,"2024-12-14T23:00:00",45640.958333333336,"2025-06-30T16:00:00",45838.666666666664,"197d + 16h 00min","Continuous","Track & Rail",null,"LT+ST",null,null,null,null,null,null,"60,,",null,"Full interuption of the traffic along one track",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312936,"Ruse - Karnobat","< >","Obrazcov chiflik","Samuil",2024,2025,50,50,"2024-12-15T08:00:00",45641.333333333336,"2025-12-12T15:00:00",46003.625,"363 x 07h 00min every week","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"7-hour interruption of the traffic  ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312937,"Ruse - Karnobat","< >","Komunari","Karnobat",2024,2025,50,50,"2024-12-15T08:00:00",45641.333333333336,"2025-12-13T15:00:00",46004.625,"363d x 07h 00min","Periodical","Track & Rail",null,"LT+ST",null,null,null,null,null,",B,B",null,null,"7-hour interruption of the traffic  ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312938,"Karnobat - Nova Zagora","< >","Karnobat","Stara Zagora",2025,2025,14,22,"2025-04-01T08:00:00",45748.333333333336,"2025-05-30T15:00:00",45807.625,"59d + 07h 00min","Continuous","Track & Rail","T",null,null,null,null,null,"R,R,R",",B,B","60,,",null,"Re-routing: Ruse razpredelitelna – Mezdra – Ilijanci – Karlovo – Plovdiv – Dimitrovgrad – Svilengrad ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312939,"Ruse - Karnobat","< >","Komunari","Karnobat",2025,2025,18,22,"2025-05-01T08:00:00",45778.333333333336,"2025-05-31T15:00:00",45808.625,"30d + 07h 00min","Continuous","Track & Rail","T",null,null,null,null,null,"R,R,R",null,null,null,"Re-routing: Ruse razpredelitelna – Mezdra – Ilijanci – Karlovo – Plovdiv – Dimitrovgrad – Svilengrad ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312940,"Nova Zagora - Simeonovgrad","< >","Radnevo","Lyubenovo Predavatelna",2025,2025,18,29,"2025-05-01T08:00:00",45778.333333333336,"2025-07-14T15:00:00",45852.625,"74d x 07h 00min","Periodical","Track & Rail",null,"LT+ST",null,null,null,null,null,null,"60,,",null,"7-hour interruption of the traffic  ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312941,"Ruse - Karnobat","< >","Samuil","Kaspichan",2025,2025,18,50,"2025-05-01T08:00:00",45778.333333333336,"2025-12-13T15:00:00",46004.625,"226d x 07h 00min","Periodical","Track & Rail",null,"LT+ST",null,null,null,null,null,",B,B",null,null,"7-hour interruption of the traffic  ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312942,"Ruse - Karnobat","< >","Obrazcov chiflik","Kaspichan",2025,2025,21,22,"2025-05-23T08:00:00",45800.333333333336,"2025-05-28T15:00:00",45805.625,"05d + 07h 00min","Continuous","Track & Rail","T",null,null,null,null,null,"R,R,R",null,null,null,"Re-routing: Ruse razpredelitelna – Gorna Oryahovica – Kaspichan/Komunari ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312943,"Nova Zagora - Simeonovgrad","< >","Nova Zagora","Simeonovgrad",2025,2025,29,33,"2025-07-15T08:00:00",45853.333333333336,"2025-08-13T15:00:00",45882.625,"29d + 07h 00min","Continuous","Track & Rail","T",null,null,null,null,null,"R,R,R",null,null,null,"Re-routing: Nova Zagora - Stara Zagora - Dimitrovgrad - Simeonovgrad",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312944,"Sofia - Promachon","< >","Razmenna","Batanowci",2025,2025,40,50,"2025-10-01T08:00:00",45901.333333333336,"2025-12-13T15:00:00",46004.625,"103d x 07h 00min","Periodical","Track & Rail",null,"LT+ST",null,null,null,null,null,",B,B",null,null,"7-hour interruption of the traffic  ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312945,"Sofia - Promachon","< >","Volujak","Batanowci",2025,2025,36,40,"2025-09-01T08:00:00",45901.333333333336,"2025-09-30T15:00:00",45930.625,"29d + 07h 00min","Continuous","Track & Rail","T",null,null,null,null,"C,C,C",null,null,null,null,"Re-routing: Sofia – Pernik razpredelitelna – Batanowci ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312946,"Nova Zagora - Simeonovgrad","< >","Lyubenovo Predavatelna","Simeonovgrad",2025,2025,36,40,"2025-09-01T08:00:00",45901.333333333336,"2025-09-30T16:00:00",45930.666666666664,"29d + 08h 00min","Continuous","Bridge","T",null,null,null,null,"C,,","R,,",",B,B",null,null,"Re-routing: Nova Zagora - Stara Zagora - Dimitrovgrad - Simeonovgrad",null,null,null,null,"2024-08-09T08:45:28"]
[null,"NRIC",5312947,"Sofia - Promachon","< >","Delqn","Dolni Rakovetz",2025,2025,36,50,"2025-09-01T08:00:00",45931.333333333336,"2025-12-13T15:00:00",46004.625,"73d x 07h 00min","Periodical","Track & Rail",null,"LT+ST",null,null,null,null,"R,,",",B,B",null,null,"7-hour interruption of the traffic  ",null,null,null,null,"2024-08-09T08:45:28"]
[null,"OSE",5312948,"Thessaloniki - Athina","< >","Larisa","Leianokladi",2024,2025,1,52,"2024-01-01","00:00:00","2025-12-31",1,"746d","Continuous","Maintenance",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2024-01-15"]
[null,"OSE",5312949,"Alexandroupolis - Strymonas","< >","Drama","Alexandroupolis",2024,2025,1,52,"2024-01-01","00:00:00","2025-12-31",1,"731d","Continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,"Failed level crossing protection ",null,null,null,"2024-01-15"]

{"sheet":"Graphic Overview","index":2,"n_rows":214,"n_cols":374,"rows_kept":214,"cut":false,"hidden":false,"merged":[[3,189,3,195],[3,196,3,202],[3,203,3,209],[3,210,3,216],[3,217,3,223],[3,259,3,265],[3,266,3,272],[3,273,3,279],[3,280,3,286],[3,224,3,230],[3,231,3,237],[3,238,3,244],[3,245,3,251],[3,252,3,258],[3,371,3,373],[3,287,3,293],[3,294,3,300],[3,301,3,307],[3,308,3,314],[3,315,3,321],[3,357,3,363],[3,364,3,370],[3,322,3,328],[3,329,3,335],[3,336,3,342],[3,343,3,349],[3,350,3,356],[3,182,3,188],[3,77,3,83],[3,84,3,90],[3,91,3,97],[3,98,3,104],[3,105,3,111],[3,147,3,153],[3,154,3,160],[3,112,3,118],[3,119,3,125],[3,126,3,132],[3,133,3,139],[3,140,3,146],[0,1,1,7],[2,9,2,39],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,40,2,67],[2,68,2,98],[2,99,2,128],[2,129,2,159],[2,160,2,189],[2,282,2,312],[2,313,2,342],[2,343,2,373],[3,70,3,76],[3,9,3,13],[3,14,3,20],[3,21,3,27],[3,28,3,34],[3,35,3,41],[3,42,3,48],[3,49,3,55],[3,56,3,62],[3,63,3,69],[3,161,3,167],[3,168,3,174],[3,175,3,181]]}
[null,"RFC 7 Overview"]
[]
[null,null,null,null,null,null,2025,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,1,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Wilhelmshaven - Bremen",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,3,5,3,3,3,5,5,5,5,4,4,4,4,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3]
[null," "]
[]
[null,"Bremerhaven - Bremen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Bremen - Hannover",null,null,null,null,null,null,null,3,3,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,3,3,3,3,3,5,5,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,5,5,5,5,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,5,5,5,5,5,5,5,5,5,4,4,4,5,3,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,5,5,5,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,5,5,5,5,5,5,5,5,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,5,5,5,5,3,3,3,3,3,4,4,4,4,4,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5]
[null," "]
[]
[null,"Hannover - Magdeburg",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,1,1,1,1,5,5,4,4,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,3,3,3,1,1,1,1,1,1,5,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,3,3,5,5,5,5,5,5,5,5,5,5,5,5,3,4,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,1,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Magdeburg - Falkenberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,null,null,null,2,2,4,3,3,3,3,4,5,5,null,null,1,1,1,1,1,1,1,1,null,null,null,5,5,2,2,2,2,2,2,3,3,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,1,1,null,null,null,5,5,null,null,null,null,null,null,null,1,1,1,1,1,1,1,null,null,null,null,3,3,null,null,null,null,null,null,5,null,null,3,3,3,3,3,3,3,3,3,3,5,5,5,5,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Falkenberg - Dresden",null,null,null,null,null,null,null,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,4,4,4,4,4,4,4,4,4,4,4,5,5,5,4,5,4,4,4,4,4,4,4,5,5,4,4,4,4,4,4,4,4,4,4,4,4,5,5,5,5,5,4,4,4,4,4,4,4,4,5,5,4,5,5,5,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,4,4,4,4,5,5,5,5,5,5,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hamburg - Magdeburg",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,5,5,5,5,5,4,5,5,4,4,4,4,4,4,5,4,4,4,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,3,3,3,3,3,3,3,3,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,4,3,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Rostock - Berlin",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,5,3,3,3,3,3,4,5,5,4,4,4,5,5,5,5,4,3,3,3,3,4,4,4,4,4,5,5,4,4,4,4,4,4,4,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,5,5,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,4,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,4,4,4,4,3,5,3,3,3,3,3,5,5,5,5,3,3,3,3,3,4,4,4,4,4,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Berlin - Dresden",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,2,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,3,5,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,1,1,1,1,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Dresden - Děčín",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,4,4,4,5,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,5,4,4,4,4,4,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,3,3,3,3,3,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,5,5,5,5,5,4,3,3,3,3,3,3,3,3,3,5,5,5,4,4,4,3,4,4,4,3,3,3,3,3,3,3,3,4,4,4,5,5,5,5,5,5,5,5,5,5,5,5,4,4,4,4,4,4,5,5,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,4,5,5,5,5,5,5,5,5,5,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Děčín - Kolín",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,1,1,1,null,1,1,3,3,3,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Děčín - Praha-Libeň",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Praha-Libeň - Česká Třebová",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kolín - Brno-Maloměřice",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,3,3,3,3,4,4,4,4,4,4,4,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Česká Třebová - Brno",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,1,1,1,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null," "]
[]
[null,"Brno - Břeclav",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Břeclav - Wien",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Gänserndorf - Devinska N.V."]
[null," "]
[]
[null,"Wien - Ebenfurth - Sopron",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5]
[null," "]
[]
[null,"Gramatneusiedl - Wr. Neustadt"]
[null," "]
[]
[null,"Wien - Wr. Neustadt"]
[null," "]
[]
[null,"Wr. Neustadt - Sopron"]
[null," "]
[]
[null,"Parndorf - Bratislava",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Wien - Hegyeshalom",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Břeclav - Kúty",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kúty - Bratislava",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Bratislava - Rajka",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Bratislava - Štúrovo"]
[null," "]
[]
[null,"Nové Zámky - Komárom"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Rajka - Hegyeshalom",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Sopron - Győr",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hegyeshalom - Ferencváros"]
[null," "]
[]
[null,"Štúrovo - Ferencváros"]
[null," "]
[]
[null,"Vác - Hatvan - Újszász"]
[null," "]
[]
[null,"Ferencváros - Szajol (100)"]
[null," "]
[]
[null,"Ferencváros - Szolnok (120a)"]
[null," "]
[]
[null,"Szajol - Curtici"]
[null," "]
[]
[null,"Szajol - PL - Biharkeresztes"]
[null," "]
[]
[null,"Curtici - Arad"]
[null," "]
[]
[null,"Arad - Timisoara",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Timisoara - Craiova",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5]
[null," "]
[]
[null,"Craiova - Vidin tovarna"]
[null," "]
[]
[null,"Arad - Simeria",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Simeria - Brasov",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Braşov - Chitila"]
[null," "]
[]
[null,"Chitila - Constanta"]
[null," "]
[]
[null,"Simeria - Filiasi"]
[null," "]
[]
[null,"Craiova - Videle"]
[null," "]
[]
[null,"Videle - Chitila"]
[null," "]
[]
[null,"Videle - Ruse"]
[null," "]
[]
[null,"Biharkeresztes - Coslariu",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Vidin tovarna - Mezdra jug"]
[null," "]
[]
[null,"Mezdra jug - Sofia"]
[null," "]
[]
[null,"Sofia - Promachon",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,2]
[null," "]
[]
[null,"Sofia - Plovdiv",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Plovdiv - Dimitrovgrad"]
[null," "]
[]
[null,"Plovdiv - Mihailovo"]
[null," "]
[]
[null,"Stara Zagora - Dimitrovgrad"]
[null," "]
[]
[null,"Dimitrovgrad - Svilengrad"]
[null," "]
[]
[null,"Ruse - Karnobat",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Karnobat - Burgas"]
[null," "]
[]
[null,"Karnobat - Nova Zagora",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nova Zagora - Simeonovgrad",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nova Zagora - Stara Zagora"]
[null," "]
[]
[null,"Promachon - Strymonas"]
[null," "]
[]
[null,"Thessaloniki - Strymonas"]
[null," "]
[]
[null,"Thessaloniki - Athina",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Svilengrad - Alexandroupolis"]
[null," "]
[]
[null,"Alexandroupolis - Strymonas",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":71,"n_cols":23,"rows_kept":71,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["IM",null,"Section",null,"Direction","Duration","ID value","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","In yearly timetable","Classification","Status","Automatic process","Year","Week"]
["DB InfraGO AG",80,"Wilhelmshaven - Bremen",1,"< >","Continuous",12963,"Signal","T","LT","S","W","Do","C,,","R,,",",B,","O,,","Y","Major","Planned","Y",2024,1]
["SZCZ",54,"Bremerhaven - Bremen",2,">","Periodical",null,"Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,","N","High","Coordination","N",2025,2]
["ŽSR",56,"Bremen - Hannover",3,"<",null,null,"Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",null,"Medium","Consultation",null,2026,3]
["ÖBB Infra",81,"Hannover - Magdeburg",4,null,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",null,"Minor","Published",null,2027,4]
["MÁV",55,"Magdeburg - Falkenberg",5,null,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",null,null,"Canceled",null,null,5]
["GYSEV",55,"Falkenberg - Dresden",6,null,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",null,null,null,null,null,6]
["CFR",53,"Hamburg - Magdeburg",7,null,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",null,null,null,null,null,7]
["NRIC",52,"Rostock - Berlin",8,null,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,null,null,null,null,null,8]
["OSE",73,"Berlin - Dresden",9,null,null,null,"Others",null,null,null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,"Dresden - Děčín",10,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,"Děčín - Kolín",11,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,"Děčín - Praha-Libeň",12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,"Praha-Libeň - Česká Třebová",13,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,"Kolín - Brno-Maloměřice",14,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,"Česká Třebová - Brno",15,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,"Brno - Břeclav",16,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,"Břeclav - Wien",17,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,"Gänserndorf - Devinska N.V.",18,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,"Wien - Ebenfurth - Sopron",19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,"Gramatneusiedl - Wr. Neustadt",20,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20]
[null,null,"Wien - Wr. Neustadt",21,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,21]
[null,null,"Wr. Neustadt - Sopron",22,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22]
[null,null,"Parndorf - Bratislava",23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,23]
[null,null,"Wien - Hegyeshalom",24,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,24]
[null,null,"Břeclav - Kúty",25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25]
[null,null,"Kúty - Bratislava",26,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,26]
[null,null,"Bratislava - Rajka",27,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,27]
[null,null,"Bratislava - Štúrovo",28,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,28]
[null,null,"Nové Zámky - Komárom",29,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,29]
[null,null,"Kúty - Galanta",30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30]
[null,null,"Rajka - Hegyeshalom",31,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,31]
[null,null,"Sopron - Győr",32,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,32]
[null,null,"Hegyeshalom - Ferencváros",33,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,33]
[null,null,"Štúrovo - Ferencváros",34,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,34]
[null,null,"Vác - Hatvan - Újszász",35,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,35]
[null,null,"Ferencváros - Szajol (100)",36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36]
[null,null,"Ferencváros - Szolnok (120a)",37,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,37]
[null,null,"Szajol - Curtici",38,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,38]
[null,null,"Szajol - PL - Biharkeresztes",39,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,39]
[null,null,"Curtici - Arad",40,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40]
[null,null,"Arad - Timisoara",41,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,41]
[null,null,"Timisoara - Craiova",42,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,42]
[null,null,"Craiova - Vidin tovarna",43,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43]
[null,null,"Arad - Simeria",44,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,44]
[null,null,"Simeria - Brasov",45,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,45]
[null,null,"Braşov - Chitila",46,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,46]
[null,null,"Chitila - Constanta",47,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,47]
[null,null,"Simeria - Filiasi",48,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48]
[null,null,"Craiova - Videle",49,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,49]
[null,null,"Videle - Chitila",50,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50]
[null,null,"Videle - Ruse",51,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,51]
[null,null,"Biharkeresztes - Coslariu",52,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,52]
[null,null,"Vidin tovarna - Mezdra jug",53]
[null,null,"Mezdra jug - Sofia",54]
[null,null,"Sofia - Promachon",55]
[null,null,"Sofia - Plovdiv",56]
[null,null,"Plovdiv - Dimitrovgrad",57]
[null,null,"Plovdiv - Mihailovo",58]
[null,null,"Stara Zagora - Dimitrovgrad",59]
[null,null,"Dimitrovgrad - Svilengrad",60]
[null,null,"Ruse - Karnobat",61]
[null,null,"Karnobat - Burgas",62]
[null,null,"Karnobat - Nova Zagora",63]
[null,null,"Nova Zagora - Simeonovgrad",64]
[null,null,"Nova Zagora - Stara Zagora",65]
[null,null,"Promachon - Strymonas",66]
[null,null,"Thessaloniki - Strymonas",67]
[null,null,"Thessaloniki - Athina",68]
[null,null,"Svilengrad - Alexandroupolis",69]
[null,null,"Alexandroupolis - Strymonas",70]