## Schedule
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination |  | IM Project ID (Optional) | Last update | Classification | Weekdays |  | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process
0051 PKP-I 0054 SZCZ 0056 ZSR 0081 OEBB-I 0055 MAV/Gysev/KTI 0079 SZ-I 0078 HZ-I 0083 RFI |  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Rerouting | Train replacement | Delays | Other |  |  | In annual timetable |  |  |  |  | Impact on traffic
51 | 51_01_01 | Czechowice Dziedzice - Ostrava | > | Pruchna | Zebrzydowice | 2026 | 2027 | 8 | 34 | 2026-02-20 | 0:00 | 2027-08-29 | 24:00 | 218 days | continuous | Track & Rail |  | LT | S | [7 empty] | modernization |  | Y |  | 2026-01-05 | high | [6 empty] | publication |  | y
51 | 51_01_02 | Chorzew - Katowice | < | Radzionków | Nakło Śląskie | 2026 | 2027 | 37 | 31 | 2026-09-08 | 0:00 | 2027-08-05 | 24:00 | 238 days | periodical | Track & Rail | T | LT | S | [7 empty] | surface replacement, construction of engineering structures, replacement of the network, one track operations, 4 hours total closure at night |  | Y |  | 2026-01-05 | high | [6 empty] | publication |  | y
51 | 51_01_03 | Chorzew - Katowice | > | Nakło Śląskie | Tarnowskie Góry | 2027 | 2028 | 42 | 9 | 2027-08-06 | 0:00 | 2028-01-31 | 24:00 | 178 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 2026-01-05 | high | [6 empty] | planned |  | Y
51 | 51_01_04 | Chorzew - Katowice | > | Nakło Śląskie | Tarnowskie Góry | 2026 | 2027 | 42 | 9 | 2026-10-16 | 0:00 | 2027-03-05 | 24:00 | 140 | continuous | Track & Rail |  | LT | S | [7 empty] | modernization, one track operations |  | N |  | 2026-01-05 | high | [6 empty] | publication |  | Y
51 | 51_01_05 | Chorzew - Katowice | < | TGE | Kalety | 2026 | 2027 | 37 | 31 | 2026-09-08 | 0:00 | 2027-08-05 | 24:00 | 331 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 2026-01-05 | high | [6 empty] | publication |  | Y
51 | 51_01_06 | Chorzew - Katowice | < | Kalety | Boronów | 2027 | 2028 | 9 | 5 | 2027-03-05 | 0:00 | 2028-02-01 | 24:00 | 333 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 2026-01-05 | high | [6 empty] | planned |  | Y
51 | 51_01_07 | Chorzew - Katowice | > | Boronów | Kalina | 2026 | 2027 | 37 | 9 | 2026-09-08 | 0:00 | 2027-03-04 | 24:00 | 177 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 2026-01-05 | high | [6 empty] | planned |  | Y
51 | 51_01_08 | Wroclaw - Katowice | > | Gliwice Łabędy | Pyskowice | 2027 | 2027 | 21 | 35 | 2027-05-25 | 0:00 | 2027-09-03 | 24:00 | 101 | continuous | Track & Rail | T | LT | [8 empty] | Reconstruction of track systems along with the traction network and railway traffic control, demolition and construction of engineering structures |  | Y |  | 2026-01-05 | high | [6 empty] | publication |  | Y
51 | 51_01_09 | Wroclaw - Katowice | < > | Gliwice | Gliwice Łabędy | 2026 | 2026 | 15 | 18 | 2026-04-06 | 0:00 | 2026-04-30 | 24:00 | 24 | continuous | Track & Rail | T | LT | [8 empty] | construction works related to the renovation of the overpass at km 28.279 of line no. 137 |  | Y |  | 2026-01-05 | high | [6 empty] | publication |  | Y
51 | 51_01_10 | Opole - Bohumin | > | Krzyżanowice | Chałupki | 2027 | 2027 | 7 | 52 | 2027-02-15 | 0:00 | 2027-12-31 | 24:00 | 319 | continuous | Track & Rail | T | LT | [8 empty] | modernization, one track operations |  | Y |  | 2026-01-05 | high | [6 empty] | publication |  | Y
51 | 51_01_11 | Gdynia - Maksymilianowo | < | Kościerzyna | Gołubie Kaszubskie | 2025 | 2027 | 36 | 40 | 2025-09-02 | 0:00 | 2027-09-30 | 24:00 | 758 | continuous | Track & Rail | T | LT | S | [7 empty] | comprehensive trail renovation |  | Y |  | 2026-01-05 | major | [6 empty] | publication |  | Y
51 | 51_01_12 | Gdynia - Maksymilianowo | < | Gołubie Kaszubskie | Somonino | 2025 | 2027 | 36 | 19 | 2025-09-02 | 0:00 | 2027-05-04 | 24:00 | 609 | continuous | Track & Rail | T | LT | S | [7 empty] | comprehensive trail renovation |  | Y |  | 2026-01-05 | major | [6 empty] | publication |  | Y
51 | 51_01_13 | Gdynia - Maksymilianowo | < | Somonino | Glincz | 2026 | 2027 | 33 | 28 | 2026-08-11 | 0:00 | 2027-07-14 | 24:00 | 337 | continuous | Track & Rail | T | LT | S | [7 empty] | modernization of the line, construction of a second track |  | Y |  | 2026-01-05 | major | [6 empty] | publication |  | Y
51 | 51_01_14 | Chorzew - Katowice | > | Radzionków | Nakło Śląskie | 2027 | 2028 | 37 | 31 | 2027-12-12 | 0:00 | 2028-08-04 | 24:00 | 236 | continuous | Track & Rail | T | LT | S | [7 empty] | single-track bidirectional traffic, 4 hours total closure at night |  | Y |  | 46027 | major | [6 empty] | planned |  | y
51 | 51_01_15 | Chorzew - Katowice | > | Nakło Śląskie | Tarnowskie Góry | 2028 | 2028 | 31 | 49 | 2028-08-04 | 0:00 | 2028-12-09 | 24:00 | 127 | continuous | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_16 | Chorzew - Katowice | > | TGE | Kalety | 2027 | 2028 | 49 | 31 | 2027-12-12 | 0:00 | 2028-08-04 | 24:00 | 236 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_17 | Chorzew - Katowice | < | Kalety | Boronów | 2028 | 2028 | 9 | 49 | 2028-03-05 | 0:00 | 2028-12-09 | 24:00 | 279 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_18 | Chorzew - Katowice | < | Boronów | Kalina | 2027 | 2028 | 37 | 9 | 2027-12-12 | 0:00 | 2028-03-03 | 24:00 | 82 | periodical | Track & Rail | T | LT | S | [7 empty] | modernization, one track operations, 4 hours total closure at night |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_19 | Opole - Bohumin | < | Krzyżanowice | Chałupki | 2028 | 2028 | 2 | 49 | 2028-01-14 | 0:00 | 2028-12-09 | 24:00 | 330 | continuous | Track & Rail | T | LT | [8 empty] | Modernization of the line, reconstruction of the track layout along with other infrastructure elements |  | Y |  | 46027 | major | [6 empty] | publication |  | Y
51 | 51_01_20 | Gdynia - Maksymilianowo | < | Maksymilianowo | Stronno | 2028 | 2028 | 28 | 32 | 2028-07-12 | 0:00 | 2028-08-10 | 24:00 | 29 | continuous | Track & Rail | T | LT | S | [7 empty] | traffic interruption, replacement rail service |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_21 | Opole - Bohumin | < | Racibórz | Krzyżanowice | 2027 | 2027 | 36 | 19 | 2027-12-12 | 0:00 | 2027-12-31 | 24:00 | 19 | continuous | Track & Rail | T | LT | S | [7 empty] | Modernization of the line, reconstruction of the track layout along with other infrastructure elements. |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_22 | Gdynia - Maksymilianowo | < | Serock | Wierzchucin | 2028 | 2028 | 28 | 32 | 2028-07-12 | 0:00 | 2028-08-10 | 24:00 | 29 | continuous | Track & Rail | T | LT | S | [7 empty] | Modernization of the line, reconstruction of the track layout along with other infrastructure elements. |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_23 | Gdynia - Maksymilianowo | < | Łąg Południowy | Kościerzyna | 2027 | 2028 | 49 | 49 | 2027-12-12 | 0:00 | 2028-12-09 | 24:00 | 363 | continuous | Track & Rail | T | LT | S | [7 empty] | modernization of the line, construction of a second track |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
51 | 51_01_24 | Wroclaw - Katowice | < | Sosnowiec Maczki | Długoszyn | 2028 | 2028 | 35 | 48 | 2028-09-01 | 0:00 | 2028-11-30 | 24:00 | 90 | continuous | Track & Rail | T | LT | S | [7 empty] | construction of a railroad bridge |  | Y |  | 46027 | major | [6 empty] | planned |  | Y
0056 | 56TT2311011b |  | < > | Bratislava-Rača | Trnava | 2025 | 2026 | 1 | 9 | 2025-01-01 08:00 | 45658.3333 | 2026-02-28 17:00 | 46081.7083 | 371 x 23h 59min every week | periodical | signal | [10 empty] | CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0
0056 | 056TT2311014 |  | < > | Bratislava-Nové Mesto | Nové Košariská | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | miscellaneous | [10 empty] | Vybudovanie odb. Ružinov, rozšírenie stanice N. Košariská, AH N. Košariská - Kvetoslavov |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0
0056 | 056TT2311013 |  | < > | Bratislava ÚNS | Bratislava-Petržalka | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | track & rail | [10 empty] | Rekonštrukcia koľají č. 1, 2 (mimo DŽM) |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0
0056 | 056TT2311009 |  | < > | Bratislava-Nové Mesto | Bratislava ÚNS | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | track & rail | [10 empty] | KRŽZ koľ. č. 1, 2 |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0
0056 | 56TT2311011b |  | < > | Bratislava-Rača | Trnava | 2025 | 2026 | 1 | 9 | 2025-01-01 08:00 | 45658.3333 | 2026-02-28 17:00 | 17:00:00 | 371 x 23h 59min every week | periodical | signal | [10 empty] | CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0056 | 056TT2311009 |  | < > | Bratislava-Nové Mesto | Bratislava ÚNS | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 17:00 |  | periodical | track & rail | [10 empty] | KRŽZ koľ. č. 1, 2 |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0056 | 056TT2311013 |  | < > | Bratislava ÚNS | Bratislava-Petržalka | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 17:00:00 |  | periodical | track & rail | [10 empty] | Rekonštrukcia koľají č. 1, 2 (mimo DŽM) |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0056 | 56TT2311011b | Bratislava hl.st. - Trnava - Nové Mesto nad Váhom | < > | Bratislava-Rača | Trnava | 2025 | 2026 | 1 | 9 | 2025-01-01 08:00 | 45658.3333 | 2026-02-28 17:00 | 23:59 | 371 x 23h 59min every week | periodical | signal | [10 empty] | CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava |  | N |  | 2023-11-24 | unclassified
0056 | 056TT2311014 | Bratislava hl.st. - Dunajská Streda - Komárno | < > | Bratislava-Nové Mesto | Nové Košariská | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 23:59 |  | periodical | miscellaneous | [10 empty] | Vybudovanie odb. Ružinov, rozšírenie stanice N. Košariská, AH N. Košariská - Kvetoslavov |  | N |  | 2023-11-24 | unclassified
0056 | 056TT2311013 | Bratislava hl.st. - Bratislava-Petržalka št.hr. | < > | Bratislava ÚNS | Bratislava-Petržalka | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 23:59 |  | periodical | track & rail | [10 empty] | Rekonštrukcia koľají č. 1, 2 (mimo DŽM) |  | N |  | 2023-11-24 | unclassified
0056 | 056TT2311009 | Bratislava hl.st. - Bratislava-Petržalka št.hr. | < > | Bratislava-Nové Mesto | Bratislava ÚNS | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 23:59 |  | periodical | track & rail | [10 empty] | KRŽZ koľ. č. 1, 2 |  | N |  | 2023-11-24 | unclassified
0056 | 56TT2311011a | Trnava - Sereď - Galanta | < > | Trnava | Križovany nad Dudváhom | 2026 | 2026 | 1 | 9 | 2026-01-01 08:00 | 46023.3333 | 2026-02-28 17:00 | 23:59 | 371 x 23h 59min every week | periodical | Signal | [10 empty] | CRD Trnava + dispečerizácia Trnava - Križovany |  | Y |  | 2024-12-12 | N
0056 | A12084 | Vrútky - Žilina-Teplička - Žilina | < > | Žilina zr.stanica | Žilina | 2023 | 2026 | 1 | 53 | 01.01.2025 | 00:01 | 31.03.2026 | 23:59 |  | continuous | Miscellaneous | [10 empty] | Modernizácia celého železničného uzla |  | Y | A12084 | 2024-12-12 | N
0056 | 56TT2311011a | Nové Zámky - Leopoldov | < > | Križovany n/Dudváhom | Trnava | 2025 | 2026 | 1 | 9 | 2025-01-01 | 8:00 | 2026-02-28 | 17:00 | 423 days | periodical | Signal | [10 empty] | CRD Trnava + dispečerizácia |  |  |  | 2024-08-02
0056 | 056TT2306001 |  | < > | Kúty | Devínska Nová Ves | 2022 | 2026 | 16 | 53 | 2022-04-24 08:00 | 44675.3333 | 2026-12-31 16:00 | 46387.6667 |  | periodical | miscellaneous | [12 empty] | N |  | 2023-06-23 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056KE2212135 |  | < > | Vydrník | Poprad-Tatry | 2023 | 2026 | 35 | 27 | 2023-09-01 08:00 | 45170.3333 | 2026-06-30 16:00 | 46203.6667 |  | periodical | miscellaneous | [10 empty] | 105 |  | N |  | 2023-06-23 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056KE2212135 |  | < > | Vydrník | Poprad-Tatry | 2024 | 2026 | 1 | 14 | 2024-01-01 08:00 | 45292.3333 | 2026-03-31 16:00 | 46112.6667 |  | periodical | miscellaneous | [10 empty] | 105 |  | N |  | 2022-12-07 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056KE2212135 |  | < > | Vydrník | Poprad-Tatry | 2024 | 2026 | 14 | 31 | 2024-04-01 08:00 | 45383.3333 | 2026-07-31 16:00 | 46234.6667 |  | periodical | miscellaneous | [10 empty] | 105, TK 1/2, Modernizácia |  | N |  | 2023-11-22 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056KE2306001 |  | < > | Prešov | Strážske | 2024 | 2028 | 27 | 5 | 2024-07-01 08:00 | 45474.3333 | 2028-01-31 16:00 | 46783.6667 |  | periodical | signal | [10 empty] | 107 |  | N |  | 2023-06-23 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056KE2212134 |  | < > | Spišská Nová Ves | Vydrník | 2024 | 2026 | 31 | 31 | 2024-08-01 08:00 | 45505.3333 | 2026-07-31 16:00 | 46234.6667 |  | periodical | miscellaneous | [10 empty] | 105 |  | N |  | 2023-06-23 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | cancelled
0056 | 056KE2306001 |  | < > | Prešov | Strážske | 2025 | 2027 | 1 | 52 | 2025-01-01 08:00 | 45658.3333 | 2027-12-31 16:00 | 46752.6667 |  | periodical | signal | [10 empty] | 107, DOZZ |  | N |  | 2023-11-22 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 56TT2311011b |  | < > | Bratislava-Rača | Trnava | 2025 | 2026 | 1 | 9 | 2025-01-01 08:00 | 45658.3333 | 2026-02-28 17:00 | 46081.7083 | 371 x 23h 59min every week | periodical | signal | [10 empty] | CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 000000021406 |  | < > | Zohor | Zohor | 2025 | 2026 | 12 | 9 | 2025-03-20 08:00 | 45736.3333 | 2026-02-23 18:00 | 46076.75 | 340d + 10h 00min | continuous | track & rail |  | ST |  | L | [6 empty] | modernisation of station + catenary |  | Y | VY0000021406 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000020985 |  | > | Nižná Myšľa | Ruskov | 2025 | 2026 | 15 | 14 | 2025-04-07 06:00 | 45754.25 | 2026-03-30 16:00 | 46111.6667 | 357d + 10h 00min | continuous | track & rail |  | LT | [8 empty] | Modernisation track num. 2 + catenary |  | Y | VY0000020985 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 056KE2212131 |  | < > | Veľký Horeš | Streda nad Bodrogom | 2025 | 2026 | 18 | 27 | 2025-05-01 08:00 | 45778.3333 | 2026-06-30 16:00 | 46203.6667 |  | periodical | miscellaneous | [10 empty] | 101 |  | N |  | 2023-11-22 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 000000021193 |  | < > | Poprad-Tatry | Poprad-Tatry | 2026 | 2026 | 1 | 22 | 2026-01-01 | 46023 | 2026-05-25 16:00 | 46167.6667 | 144d + 15h 00min | continuous | miscellaneous |  | LT+ST | [8 empty] | track num.2 + catenary |  | Y | VY0000021193 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 056TT2311012 |  | < > | Kúty št. hr. | Devínska Nová Ves | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | miscellaneous | [10 empty] | Modernizácia dvoch úsekov železničnej trate štátna hranica ČR/SR - Devínska Nová Ves |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056TT2311009 |  | < > | Bratislava-Nové Mesto | Bratislava ÚNS | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | track & rail | [10 empty] | KRŽZ koľ. č. 1, 2 |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056TT2311008 |  | < > | Šelpice | Boleráz | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | track & rail | [10 empty] | KRŽZ koľ. č.1 |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 56TT2311011a |  | < > | Trnava | Križovany nad Dudváhom | 2026 | 2026 | 1 | 9 | 2026-01-01 08:00 | 46023.3333 | 2026-02-28 17:00 | 46081.7083 | 371 x 23h 59min every week | periodical | signal | [10 empty] | CRD Trnava + dispečerizácia Trnava - Križovany |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056TT2311010 |  | < > | Malacky | Kúty | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | miscellaneous | [10 empty] | Modernizácia železničnej trate Devínska Nová Ves - štátna hranica SR/ČR + DOZZ, ETCS |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056TT2311013 |  | < > | Bratislava ÚNS | Bratislava-Petržalka | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | track & rail | [10 empty] | Rekonštrukcia koľají č. 1, 2 (mimo DŽM) |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056TT2311014 |  | < > | Bratislava-Nové Mesto | Nové Košariská | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | miscellaneous | [10 empty] | Vybudovanie odb. Ružinov, rozšírenie stanice N. Košariská, AH N. Košariská - Kvetoslavov |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 056TT2311007 |  | < > | Dvory nad Žitavou | Dvory nad Žitavou | 2026 | 2026 | 1 | 53 | 2026-01-01 08:00 | 46023.3333 | 2026-12-31 17:00 | 46387.7083 |  | periodical | switch | [10 empty] | Rekonštrukcia výhybiek č. 1,2,3,4,5,6,7,8 |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 |  | 1 | 0 |  |  |  | publication
0056 | 000000021404 |  | < | Malacky | Zohor | 2026 | 2026 | 2 | 9 | 2026-01-09 08:00 | 46031.3333 | 2026-02-23 16:00 | 46076.6667 | 45d + 08h 00min | continuous | track & rail |  | LT | X | [7 empty] | modernisation track num. 1 + catenary |  | Y | VY0000021404 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021408 |  | < | Zohor | Devínska Nová Ves | 2026 | 2026 | 6 | 32 | 2026-02-03 08:00 | 46056.3333 | 2026-08-04 16:00 | 46238.6667 | 182d + 07h 00min | continuous | track & rail |  | LT | X | [7 empty] | track num1 + catenary |  | Y | VY0000021048 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021367 |  | < > | Cífer | Trnava | 2026 | 2026 | 8 | 27 | 2026-02-16 | 46069 | 2026-07-05 23:59 | 46208.9993 | 139d + 22h 59min | continuous | track & rail |  | LT | X | L | [6 empty] | comprehensive reconstruction of whole superstructure (until bedrock), both tracks (1/2) |  | Y | VY0000021367 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021407 |  | < > | Zohor | Zohor | 2026 | 2026 | 9 | 35 | 2026-02-24 06:00 | 46077.25 | 2026-08-25 18:00 | 46259.75 | 182d + 11h 00min | continuous | track & rail |  | ST | [8 empty] | Zohor psk modernisation + catenary |  | Y | VY0000021407 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021405 |  | > | Zohor | Malacky | 2026 | 2026 | 9 | 15 | 2026-02-24 08:00 | 46077.3333 | 2026-04-10 16:00 | 46122.6667 | 45d + 07h 00min | continuous | track & rail |  | LT | X | [7 empty] | modernisation track num. 2 + catenary |  | Y | VY0000021405 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021386 |  | < | Bratislava-Nové Mesto | Bratislava predmestie | 2026 | 2026 | 14 | 22 | 2026-03-30 08:00 | 46111.3333 | 2026-05-31 16:00 | 46173.6667 | 62d + 08h 00min | continuous | switch |  | LT+ST | X | [7 empty] | track num. 1 + switches num. - 3, 4, 5, 6, 13 for Bratislava-Nové Mesto |  | Y | VY0000021386 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021005 |  | > | Kysak | Malá Lodina | 2026 | 2026 | 14 | 22 | 2026-04-01 08:00 | 46113.3333 | 2026-05-31 18:00 | 46173.75 | 60d + 10h 00min | continuous | track & rail |  | LT | [8 empty] | Track. num. 1 + catenary |  | Y | VY0000021005 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 | 40 |  |  |  | publication
0056 | 000000020987 |  | < > | Nižná Myšľa | Ruskov | 2026 | 2026 | 14 | 22 | 2026-04-01 08:00 | 46113.3333 | 2026-05-31 16:00 | 46173.6667 | 615d + 23h 59min | continuous | miscellaneous |  | LT | [8 empty] | track num. 1 + catenary |  | Y | VY00000020987 | 2023-06-23 | high | 1,2,3,4,5,6,7 |  | 1 | 50 |  |  |  | planned
0056 | VY0000021339 |  | < > | Alekšince | Alekšince | 2026 | 2026 | 16 | 18 | 2026-04-13 08:00 | 46125.3333 | 2026-04-30 16:00 | 46142.6667 | 17d + 08h 00min | continuous | track & rail |  | ST | [8 empty] | comprehensive station track reconstruction |  | Y | VY0000021339 | 2026-01-08 05:07 | unclassified | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | planned
0056 | VY0000021312 |  | < > | Mníchova Lehota | Bánovce nad Bebravou | 2026 | 2026 | 17 | 42 | 2026-04-20 08:00 | 46132.3333 | 2026-10-16 18:00 | 46311.75 | 180 x 10h 00min every week | periodical | bridge | [10 empty] | parts renewal / interchange, hydroisolation replacement 4x stage TCR: I.stage- 20 - 24.4. = 4 days II. 27.7 - 28.8 = 32 days III. 05 - 09.10 = 4 days IV. 12 - 16.10 = 4 days |  | Y | VY0000021312/ 21313/ 21314/ 21315 | 2026-01-08 05:07 | medium | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000020965 |  | > | Slovenské Nové Mesto | Michaľany | 2026 | 2026 | 18 | 22 | 2026-05-01 06:00 | 46143.25 | 2026-05-31 18:00 | 46173.75 | 30d + 12h 00min | continuous | track & rail |  | LT | [8 empty] | track num.1 |  | Y | VY0000020965 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | VY0000021311 |  | < > | Bánovce nad Bebravou | Rybany | 2026 | 2026 | 18 | 19 | 2026-05-01 08:00 | 46143.3333 | 2026-05-05 16:00 | 46147.6667 | 04d + 08h 00min | continuous | bridge |  | LT | X | [7 empty] | renewal / parts replacement |  | Y | VY0000021311 | 2026-01-08 05:07 | minor | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | planned
0056 | 000000021400 |  | < | Malacky | Veľké Leváre | 2026 | 2026 | 19 | 25 | 2026-05-07 06:00 | 46149.25 | 2026-06-18 18:00 | 46191.75 | 42d + 12h 00min | continuous | track & rail |  | LT | [8 empty] | modernisation track num.1 + catenary |  | Y | VY0000021400 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021388 |  | < > | Bratislava-Nové Mesto | Bratislava hlavná stanica | 2026 | 2026 | 23 | 27 | 2026-06-01 | 46174 | 2026-07-05 23:59 | 46208.9993 | 34d + 23h 59min | continuous | bridge |  | LT | X | W+L+P | [6 empty] | bridge parts interchange (couples, pillons renewal...etc) |  | Y | VY0000021388 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000020966 |  | < | Michaľany | Slovenské Nové Mesto | 2026 | 2026 | 23 | 27 | 2026-06-01 08:00 | 46174.3333 | 2026-06-30 18:00 | 46203.75 | 29d + 10h 00min | continuous | track & rail |  | LT | [10 empty] | Y | VY0000020966 | 2026-01-08 05:07 | unclassified | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021194 |  | < > | Poprad-Tatry | Poprad-Tatry | 2026 | 2026 | 24 | 32 | 2026-06-14 08:00 | 46187.3333 | 2026-08-03 16:00 | 46237.6667 | 50d + 08h 00min | continuous | miscellaneous |  | LT+ST | [8 empty] | modernisation track num 2 + catenary |  | Y | VY0000021194 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021403 |  | < > | Malacky | Malacky | 2026 | 2027 | 25 | 7 | 2026-06-19 08:00 | 46192.3333 | 2027-02-19 16:00 | 46437.6667 | 245d + 09h 00min | continuous | track & rail |  | ST |  | L | [6 empty] | Malacky station + catenary |  | Y | VY0000021403 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021402 |  | > | Malacky | Veľké Leváre | 2026 | 2026 | 25 | 31 | 2026-06-19 08:00 | 46192.3333 | 2026-07-31 18:00 | 46234.75 | 42d + 10h 00min | continuous | track & rail |  | LT | [8 empty] | modernisation track num. 2 + catenary |  | Y | VY0000021402 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000020983 |  | < > | Slanec | Slanec | 2026 | 2026 | 27 | 50 | 2026-06-29 06:00 | 46202.25 | 2026-12-13 18:00 | 46369.75 | 167d + 13h 00min | continuous | catenary |  | ST |  |  | X | [5 empty] | Comprehensive catenary recontruction/ modernisation |  | Y | VY0000020983 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000020981 |  | < > | Slanec | Slanec | 2026 | 2026 | 27 | 50 | 2026-06-29 08:00 | 46202.3333 | 2026-12-13 18:00 | 46369.75 | 167d + 11h 00min | continuous | catenary |  | ST |  |  | X | [5 empty] | Comprehensive catenary recosntruction in station |  | Y | VY0000020981 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021995 |  | > | Poprad-Tatry | Výh. Gánovce | 2026 | 2026 | 33 | 46 | 2026-08-11 08:00 | 46245.3333 | 2026-11-09 18:00 | 46335.75 | 90d + 11h 00min | continuous | miscellaneous |  | LT | [8 empty] | modernisation - Výh. Gánovce (shunting traffic point), track num. 1 + catenary |  | Y | VY0000021995 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021409 |  | < | Zohor | Devínska Nová Ves | 2026 | 2026 | 35 | 48 | 2026-08-26 08:00 | 46260.3333 | 2026-11-25 16:00 | 46351.6667 | 91d + 09h 00min | continuous | track & rail |  | LT+ST | X | [7 empty] | modernisation + catenary + construc. of temporary passing loop (Výh. Háj) |  | Y | VY0000021409 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | VY0000021261 |  | < > | Banská Štiavnica | Hronská Dúbrava | 2026 | 2026 | 37 | 43 | 2026-09-07 08:00 | 46272.3333 | 2026-10-23 18:00 | 46318.75 | 35 x 10h 00min every week | periodical | track & rail |  | LT | [8 empty] | change of railway sleepers |  | Y | VY0000021261 | 2026-01-08 05:07 | medium | 1,2,3,4,5 |  | 1 |  |  |  |  | planned
0056 | 000000021204 |  | < > | Košice | Barca | 2026 | 2026 | 40 | 44 | 2026-10-01 06:00 | 46296.25 | 2026-10-30 16:00 | 46325.6667 | 29d + 11h 00min | continuous | switch |  | LT+ST | X | [7 empty] | Košice, switch č. 161, 161XA, 162, 162XA, 167, 168, Košice - Barca both tracks (1/2) |  | Y | VY0000021204 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021215 |  | < > | Sabinov | Veľký Šariš | 2026 | 2026 | 40 | 44 | 2026-10-01 08:00 | 46296.3333 | 2026-10-31 12:00 | 46326.5 | 30d + 05h 00min | continuous | bridge |  | LT | X | P | [6 empty] | Bridge coupler |  | Y | VY0000021215 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
56 | 000000021369 |  | < > | Vaďovce | Stará Turá | 2026 | 2026 | 10 | 13 | 2026-09-02 | 8:00 | 2026-09-20 | 18:00 | 17d + 11h 00min | continuous | track & rail |  | LT | X | [7 empty] | renewal / parts replacement |  |  | VY0000021369 | 2026-02-02 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
56 | VY197 | Nové Zámky - Leopoldov | < > | Trnovec nad Váhom | Šaľa | 2026 | 2026 | 26 | 29 | 2026-06-22 | 8:00 | 2026-07-13 | 16:00 | 20days + 8h 00min | continuous | bridge |  | LT | x | x | [6 empty] | bridge parts interchange (couples renewal...etc) |  | Y | 197 | 2026-05-20 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication | 28-29.06.2026 - without TCR
0056 | 000000021196 |  | < | Výh. Gánovce | Poprad-Tatry | 2026 | 2026 | 46 | 49 | 2026-11-10 08:00 | 46336.3333 | 2026-12-04 14:00 | 46360.5833 | 24d + 06h 00min | continuous | miscellaneous |  | LT | [8 empty] | modernisation, track num 1 + catenary |  | Y | VY0000021196 | 2026-01-08 05:07 | major | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0056 | 000000021410 |  | > | Devínska Nová Ves | Zohor | 2026 | 2027 | 48 | 5 | 2026-11-26 08:00 | 46352.3333 | 2027-02-05 18:00 | 46423.75 | 71d + 10h 00min | continuous | track & rail |  | LT+ST | X | [7 empty] | modernisation of track num 2 + catenary + (Výh. Malý Háj) + part of Zohor station from Devínska Nová Ves = even side |  | Y | VY0000021410 | 2026-01-08 05:07 | high | 1,2,3,4,5,6,7 |  | 1 |  |  |  |  | publication
0081 | 81-B-91635 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Nickelsdorf - (Hegyeshalom) | < > | Gramatneusiedl | Götzendorf | 2027 | 2027 | 3 | 8 | 18.01.2027 | 07:00 | 28.02.2027 | 19:00 | 41 days + 12,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Erneuerung der Fahrleitung |  | N |  | 06.06.2025 | High |  | 31-50%
0081 | 81-B-92502 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wiener Neustadt Hbf (in Nb)=Abzww Ne (in Nb) | < > | Abzww Ne | Mürzzuschlag | 2027 | 2027 | 27 | 29 | 10.07.2027 | 22:00 | 21.07.2027 | 18:00 | 10 days + 20,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Nbs - Mz: IH-Sperren Nb U2: Weichenneulage W703,W704 Nek: Weichenneulage W1-W4 Glo: Weichenneulage W74 Pr-Eib: Gleisneulage StrGl 2 Eib - Eib U3: Gleisneulage StrGl 2 Eib - Eib U3: Umbau der Oberleitung Eib - Eib U3: Herstellung einer Entwässerung Eib - Eib U3: Mauersanierung Bt-Sem: Mittelfuge Bodenplatte |  | N |  | 11.06.2025 | High |  | 51-100%
0081 | 81-B-91936 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Mixnitz-Bärenschützklamm | - | 2027 | 2027 | 21 | 24 | 29.05.2027 | 14:00 | 15.06.2027 | 17:00 | 17 days + 3,0 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Bahnhofsumbau Bf. Mixnitz-Bärenschützklamm Bauphasen 2027 Tragwerk Mixnitzbach - Fertigstellungsarbeiten Gleis 2 |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-91380 | Villach Süd Gvbf-Auen (in Vsv)=Staatsgrenze nächst Rosenbach - (Jesenice), Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), Villach Seebach=Villach Süd Gvbf-West (in Vsv) | < > | Villach Süd Gvbf-Auen | - | 2027 | 2027 | 32 | 35 | 15.08.2027 | 00:00 | 30.08.2027 | 24:00 | 16 days | continuous | Others | T | LT |  |  |  | C | R | T | 10 |  | Villach Süd Gvbf - Auen Weichenneulagen W101,106, 107 sowie Gleisneulage Gl 104, 106 von km 381,875 bis km 383,410 |  | N |  | 02.06.2025 | High |  | 31-50%
0081 | 81-B-86891 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Nickelsdorf - (Hegyeshalom) | < > | Lanzendorf-Rannersdorf | Gramatneusiedl | 2026 | 2026 | 10 | 26 | 08.03.2026 | 04:40 | 22.06.2026 | 04:40 | 105 days + 23,0 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Bahnhof Himberg |  | N |  | 12.09.2025 | High |  | 11-30%
0081 | 81-B-91040 | St.Veit a.d.Glan (in Vps)=Villach Hbf (in Vb) | < > | Steindorf am Ossiachersee | Sattendorf | 2026 | 2026 | 49 | 50 | 01.12.2026 | 00:00 | 12.12.2026 | 24:00 | 12 days | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Oberleitungserneuerung Bf. Ossiach-Bodensdorf |  | N |  | 25.05.2025 | High |  | 51-100%
0081 | 81-B-92461 | Kledering (in Zur)=Felixdorf | < > | Traiskirchen Aspangbahn | Felixdorf | 2027 | 2027 | 27 | 49 | 05.07.2027 | 00:00 | 11.12.2027 | 24:00 | 160 days + 1,0 h | continuous | Miscellaneous | T | LT |  |  |  | C |  | T | 0 |  | Errichten von ESTW in den Bahnhöfen Traiskirchen, Trumau und Tattendorf, sowie div. Attraktivierungsarbeiten |  | Y |  | 06.06.2025 | Major |  | 51-100%
0081 | 81-B-98731 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wien Meidling (in Wbf)=Wiener Neustadt Hbf (in Nb), W.Mat.-Oswaldgasse (in Wbf)=Wien Meidling (in Wbf), Wien Hütteldorf (in Hf)=Wien Praterstern (in Nw), Wien Hetzendorf (in Wbf)=Wien Meidling (in Wbf), Wien Meidling (in Wbf)=Linz Hbf (in Lz) | < > | Wien Meidling | - | 2026 | 2026 | 23 | 24 | 03.06.2026 | 22:00 | 08.06.2026 | 03:55 | 4 days + 5,9 h | continuous periodically | Others | T | LT |  |  |  |  | R | T | 0 |  | SAE Reinvestition: Weichentausch DKW 311/312 und DKW 313/314 Ausbau W309 |  | N |  | 24.10.2025 | High |  | 31-50%
0081 | 81-B-82718 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.) | < > | Thörl-Maglern | - | 2026 | 2026 | 34 | 38 | 22.08.2026 | 07:00 | 20.09.2026 | 17:00 | 29 days + 10,0 h | continuous periodically | Others | T | LT |  |  |  | C | R | T | 0 |  | Gleisneulagen (Gl 1-4) und Weichenneulagen im Bereich der Weichen W1-W6 | Affected Border: 83, 79 Affected Ims: Tarvis Deviation Border(s): Jesenice, Spielfeld | N |  | 04.03.2025 | High |  | 51-100%
0081 | 81-B-91874 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Eichberg | Üst Eib 3 | 2027 | 2027 | 29 | 30 | 21.07.2027 | 18:00 | 30.07.2027 | 17:00 | 8 days + 23,0 h | continuous | Others | T | LT | S |  |  | C | R | T | 0 |  | Nacharbeiten für Gleisneulage StrGl 2 Umbau der Oberleitung Herstellung einer Entwässerung Mauersanierung |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-92022 | St.Veit a.d.Glan (in Vps)=Villach Hbf (in Vb) | < > | Glanegg | St.Martin-Sittich | 2027 | 2027 | 28 | 30 | 13.07.2027 | 00:00 | 31.07.2027 | 24:00 | 19 days | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Gleisneulage von km 341,629 - km 346,576 |  | N |  | 02.06.2025 | High |  | 51-100%
0081 | 81-B-91910 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), Bruck a.d.Mur-Übelstein (in Bm)=Bruck a.d.Mur-Stadtwald (in Bm) | < > | Bruck a.d.Mur - gesamt | - | 2027 | 2027 | 42 | 44 | 24.10.2027 | 06:00 | 07.11.2027 | 05:00 | 14 days | continuous | Others | T | LT |  |  |  | C | R | T | 20 |  | Gleisneulage Gl.4 und Weichenneulage W214 inkl. Planumsverbesserung km 157,552-158,216, |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-91935 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Mixnitz-Bärenschützklamm | - | 2027 | 2027 | 18 | 21 | 07.05.2027 | 22:30 | 26.05.2027 | 17:00 | 18 days + 18,5 h | continuous | Miscellaneous | T | LT |  |  |  | C | R |  | 0 |  | Bahnhofsumbau Bf. Mixnitz-Bärenschützklamm Bauphasen 2027 Tragwerk Mixnitzbach - Fertigstellungsarbeiten Gleis 1 |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-65392 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wien Meidling (in Wbf)=Wiener Neustadt Hbf (in Nb), W.Mat.-Oswaldgasse (in Wbf)=Wien Meidling (in Wbf), W.Mat.-Laxenburg (in Wbf)=Laa a.d.Thaya, Wien Hütteldorf (in Hf)=Wien Praterstern (in Nw), Wien Hetzendorf (in Wbf)=Wien Meidling (in Wbf), Wien Meidling (in Wbf)=Linz Hbf (in Lz) | < > | Üst Wwb 1 | Wien Meidling | 2027 | 2027 | 43 | 49 | 29.10.2027 | 22:00 | 11.12.2027 | 24:00 | 43 days + 3,0 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Bauphase 9: Programm Schnellbahn Wien Inbetriebnahme ETCS L2 Süd Inbetriebnahme BFZ Zelle 20neu |  | N |  | 07.06.2025 | Major |  | 51-100%
0081 | 81-B-88144 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wien Meidling (in Wbf)=Wiener Neustadt Hbf (in Nb) | < > | Wiener Neustadt Hbf-Schleppbf | Wiener Neustadt Hbf | 2026 | 2026 | 36 | 50 | 06.09.2026 | 23:10 | 12.12.2026 | 24:00 | 97 days + 1,8 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Wiener Neustadt Nordkopf (Errichtung 4-gleisige Einfahrt) |  | N |  | 27.05.2025 | High |  | 31-50%
0081 | 81-B-91391 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), Villach Seebach=Villach Süd Gvbf-West (in Vsv) | < > | Fürnitz | Villach Süd Gvbf-West | 2027 | 2027 | 22 | 26 | 04.06.2027 | 07:00 | 28.06.2027 | 17:00 | 24 days + 10,0 h | continuous periodically | Others | T | LT |  |  |  | C | R |  | 10 |  | Hauptarbeiten GDA und GN Gl 401 |  | N |  | 01.08.2025 | High |  | 31-50%
0081 | 81-B-75714 | Wien Praterstern (in Nw)=Staatsgrenze nächst Bernhardsthal Fbf - (Breclav) | < > | Gänserndorf | Angern | 2026 | 2026 | 4 | 14 | 19.01.2026 | 23:00 | 03.04.2026 | 00:40 | 73 days + 0,7 h | continuous periodically | Miscellaneous | T | LT |  |  |  | C |  | T | 0 |  | Bph 03a0+03a1: Rammen und Masten stellen von Gae - Ag |  | N |  | 08.10.2025 | High |  | 31-50%
0081 | 81-B-86950 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Nickelsdorf - (Hegyeshalom) | < > | Lanzendorf-Rannersdorf | Gramatneusiedl | 2026 | 2026 | 44 | 49 | 31.10.2026 | 23:15 | 30.11.2026 | 04:40 | 29 days + 5,4 h | periodically | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Bahnhof Himberg |  | N |  | 07.02.2025 | High |  | 51-100%
0081 | 81-B-91854 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Neunkirchen N.Ö. | Ternitz | 2027 | 2027 | 36 | 40 | 09.09.2027 | 08:00 | 08.10.2027 | 17:00 | 29 days + 9,0 h | continuous | Others | T | LT | S |  |  | C | R | T | 0 |  | Streckenattraktivierung Südbahn Unterbausanierung und Gleisneulage StrGl 2 (Bauphase 4) |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-75727 | Wien Praterstern (in Nw)=Staatsgrenze nächst Bernhardsthal Fbf - (Breclav), Gänserndorf=Marchegg, Gänserndorf=Bad Pirawarth (vorübergehend eingestellt) | < > | Gänserndorf | Angern | 2026 | 2026 | 17 | 28 | 25.04.2026 | 00:00 | 06.07.2026 | 04:20 | 72 days + 4,3 h | continuous periodically | Miscellaneous | T | LT |  |  |  | C |  | T | 0 |  | Bph 03c: Gae:Herstellung Gl1 Str. 115; Querungen Str. 115; Rohrpressung km 32,075; Unterbausanierung Strgl 1 ab W66B-km32,950, Neubau W66N; Signale setzen , Softwaretausch |  | N |  | 08.04.2025 | High |  | 31-50%
0081 | 81-B-92190 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.) | < > | Villach Westbf | Villach Süd Gvbf-Auen | 2026 | 2026 | 17 | 21 | 25.04.2026 | 00:00 | 21.05.2026 | 24:00 | 27 days | continuous | Others | T | LT | [5 empty] | T | 0 |  | Gleisneulage mit Schotterbettreinigung StrGl. 002, von km 380,180 - 381,960 |  | N |  | 07.07.2025 | High |  | 31-50%
0081 | 81-B-83410 | W.Mat.-Laxenburg (in Wbf)=Laa a.d.Thaya | < > | Wien Stadlau | Wien Erdbergerlände | 2026 | 2026 | 1 | 9 | 01.01.2026 | 09:30 | 28.02.2026 | 04:00 | 57 days + 18,5 h | periodically | Others | T | LT | [6 empty] | 2 |  | Umsetzen Gerüst und Einhausung Donaustrom -Brücken ; grundsätzlich eingleisige Nachtsperren |  | N |  | 18.09.2025 | High |  | 31-50%
0081 | 81-B-88155 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wien Meidling (in Wbf)=Wiener Neustadt Hbf (in Nb) | < > | Wiener Neustadt Hbf-Schleppbf | Wiener Neustadt Hbf | 2026 | 2027 | 50 | 27 | 13.12.2026 | 00:00 | 05.07.2027 | 04:00 | 204 days + 3,0 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Wiener Neustadt Nordkopf (Errichtung 4-gleisige Einfahrt) |  | N |  | 27.05.2025 | High |  | 31-50%
0081 | 81-B-91848 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Neunkirchen N.Ö. | Ternitz | 2027 | 2027 | 14 | 21 | 10.04.2027 | 08:00 | 29.05.2027 | 17:00 | 49 days + 9,0 h | continuous | Others | T | LT | S |  |  | C | R | T | 0 |  | Streckenattraktivierung Südbahn Unterbausanierung und Gleisneulage StrGl 1 (Bauphase 1) |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-92365 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wien Meidling (in Wbf)=Wiener Neustadt Hbf (in Nb) | < > | Wiener Neustadt Hbf-Schleppbf | Wiener Neustadt Hbf | 2027 | 2027 | 27 | 36 | 05.07.2027 | 04:00 | 06.09.2027 | 04:00 | 63 days | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Wiener Neustadt Nordkopf (Errichtung 4-gleisige Einfahrt) |  | N |  | 05.06.2025 | High |  | 31-50%
0081 | 81-B-91382 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.) | < > | Villach Süd Gvbf-Auen | Fürnitz | 2027 | 2027 | 16 | 20 | 25.04.2027 | 07:00 | 17.05.2027 | 17:00 | 22 days + 10,0 h | continuous | Others | T | LT |  |  |  | C | R |  | 10 |  | Brückenhölzertausch Gailbrücke von km 383,862 - km 383,985 |  | N |  | 02.06.2025 | High |  | 31-50%
0081 | 81-B-91904 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Bruck a.d.Mur | Bruck a.d.Mur-Übelstein | 2027 | 2027 | 33 | 36 | 16.08.2027 | 07:00 | 08.09.2027 | 05:00 | 22 days + 22,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 10 |  | Unterbausanierung und Gleisneulage Gl2 |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-86847 | Wien Praterstern (in Nw)=Staatsgrenze nächst Bernhardsthal Fbf - (Breclav), Abzww Süßenbrunn-West (in Sue)=Abzww Süßenbrunn-Nord (in Sue), Abzww Süßenbrunn-West (in Sue)=Abzww Süßenbrunn-Nord (in Sue), Wien Süßenbrunn-Mitte (in Sue)=Wien Süßenbrunn (in Sue), Wien Süßenbrunn-Mitte (in Sue)=Abzww Süßenbrunn-Ost (in Sue) | < > | Abzww Süßenbrunn-West | Abzww Süßenbrunn-Ost | 2026 | 2026 | 4 | 6 | 24.01.2026 | 00:00 | 02.02.2026 | 24:00 | 10 days | periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | PNA: Montage neuer Umgehungs-Leitung |  | N |  | 22.10.2025 | High |  | 51-100%
0081 | 81-B-86903 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Nickelsdorf - (Hegyeshalom) | < > | Lanzendorf-Rannersdorf | Gramatneusiedl | 2026 | 2026 | 10 | 14 | 07.03.2026 | 23:15 | 30.03.2026 | 04:40 | 22 days + 4,4 h | periodically | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Bahnhof Himberg |  | N |  | 09.09.2025 | High |  | 51-100%
0081 | 81-B-84947 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.) | < > | Thörl-Maglern | Tarvisio Boscoverde | 2026 | 2026 | 34 | 38 | 22.08.2026 | 00:00 | 20.09.2026 | 24:00 | 30 days | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Tarvisio - Udine Streckenerneuerung RFI | Affected Border: 83, 79 Affected Ims: Tarvis Deviation Border(s): Jesenice | N |  | 04.03.2025 | High |  | 51-100%
0081 | 81-B-91571 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Wiener Neustadt Hbf (in Nb)=Fehring, Graz Don Bosco (in G)=Klagenfurt Hbf (in Kt), Graz-Süd (in G)=Staatsgrenze nächst Jennersdorf - (Szentgotthard), Gleisdorf=Weiz Bahnhof | < > | Graz-Süd | Staatsgrenze nächst Jennersdorf | 2026 | 2026 | 23 | 50 | 01.06.2026 | 21:20 | 12.12.2026 | 04:00 | 193 days + 7,7 h | continuous periodically | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Streckenelektrifizierung Graz Hbf - Staatsgrenze nächst Jennersdorf |  | N |  | 30.05.2025 | High |  | 31-50%
0081 | 81-B-91838 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Bruck a.d.Mur-Fbf | - | 2027 | 2027 | 9 | 11 | 06.03.2027 | 08:00 | 21.03.2027 | 17:00 | 15 days + 9,0 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Oberleitungserneuerung Bf. Bruck a. d. Mur Fbf Neubau OL BfGl 2 (302-502) |  | N |  | 20.06.2025 | High |  | 31-50%
0081 | 81-B-75734 | Wien Praterstern (in Nw)=Staatsgrenze nächst Bernhardsthal Fbf - (Breclav) | < > | Gänserndorf | Angern | 2026 | 2026 | 28 | 36 | 06.07.2026 | 04:20 | 31.08.2026 | 04:20 | 56 days | continuous periodically | Miscellaneous | T | LT |  |  |  | C |  | T | 0 |  | Bph 03d: Gae: Herstellung Anbindung neu Str. 115; Querungen Str. 115; Weichentausch W 64,67,68,69,70 inkl. geänderter Lage, Anpassung Fahrleitung, restl. Prüfarbeiten nach Softwaretausch |  | N |  | 08.04.2025 | High |  | 31-50%
0081 | 81-B-65389 | Wien Floridsdorf (in F)=Staatsgrenze nächst Retz - (Satov), Wien Praterstern (in Nw)=Staatsgrenze nächst Bernhardsthal Fbf - (Breclav), Abzww Süßenbrunn-West (in Sue)=Abzww Süßenbrunn-Nord (in Sue), Abzww Süßenbrunn-West (in Sue)=Abzww Süßenbrunn-Nord (in Sue), W.Mat.-Laxenburg (in Wbf)=Laa a.d.Thaya, Wien Süßenbrunn-Mitte (in Sue)=Wien Süßenbrunn (in Sue), Wien Süßenbrunn-Mitte (in Sue)=Abzww Süßenbrunn-Ost (in Sue), Wien Hütteldorf (in Hf)=Wien Praterstern (in Nw), Jedlersdorf (in F)=Leopoldau, Leopoldau=Wien Süßenbrunn-Mitte (in Sue) | < > | Abzww Süßenbrunn-Ost | Wien Praterstern Jedlersdorf Abzww Süßenbrunn-Nord Gerasdorf | 2026 | 2026 | 32 | 37 | 08.08.2026 | 00:00 | 07.09.2026 | 04:00 | 30 days + 4,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Bauphase 6.2.2: Programm Schnellbahn Wien Inbetriebnahme ETCS L2 bis Korneuburg und Süßenbrunn |  | N |  | 14.07.2025 | Major |  | 51-100%
0081 | 81-B-91861 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Eichberg | Üst Eib 3 | 2027 | 2027 | 21 | 27 | 29.05.2027 | 20:00 | 10.07.2027 | 22:00 | 42 days + 2,0 h | continuous | Others | T | LT | S |  |  | C | R | T | 0 |  | Vorarbeiten für Gleisneulage StrGl 2 Umbau der Oberleitung Herstellung einer Entwässerung Mauersanierung |  | N |  | 01.06.2025 | High |  | 31-50%
0081 | 81-B-86932 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Nickelsdorf - (Hegyeshalom) | < > | Lanzendorf-Rannersdorf | Gramatneusiedl | 2026 | 2026 | 23 | 26 | 06.06.2026 | 23:15 | 22.06.2026 | 04:40 | 15 days + 5,4 h | periodically | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Umbau Bahnhof Himberg |  | N |  | 07.02.2025 | High |  | 51-100%
0081 | 81-B-91656 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Nickelsdorf - (Hegyeshalom) | < > | Bruck a.d.Leitha Fbf | Abzw Bl 1 | 2027 | 2027 | 26 | 35 | 03.07.2027 | 06:00 | 05.09.2027 | 15:00 | 64 days + 9,0 h | continuous | Others | T | LT | S |  |  | C | R | T | 0 |  | Gleisneulage mit PLV |  | N |  | 06.06.2025 | High |  | 31-50%
0081 | 81-B-99187 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), St.Michael (in M)=St.Michael-West (in M) | < > | St.Michael-Ost | Kraubath | 2027 | 2027 | 29 | 31 | 25.07.2027 | 20:30 | 02.08.2027 | 20:30 | 8 days | continuous | Others | T | LT |  |  |  | C |  |  | 0 |  | Hauptarbeiten Weichenabtrag W155 PLV Gleisneulagen Gl1 |  | N |  | 23.10.2025 | High |  | 31-50%
0081 | 81-B-91388 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.) | < > | Velden am Wörthersee | Föderlach | 2027 | 2027 | 45 | 49 | 11.11.2027 | 07:00 | 07.12.2027 | 17:00 | 26 days + 10,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 10 |  | Unterbausanierung und Weichenneulage W52,55 |  | N |  | 02.06.2025 | High |  | 31-50%
0081 | 81-B-87043 | Wien Praterstern (in Nw)=Staatsgrenze nächst Bernhardsthal Fbf - (Breclav) | < > | Strasshof | Gänserndorf | 2026 | 2026 | 37 | 41 | 07.09.2026 | 00:00 | 05.10.2026 | 02:00 | 28 days + 2,0 h | continuous | Miscellaneous | T | LT | [5 empty] | T | 0 |  | Gleisneulage mit Unterbausanierung (AHM) von Silberwald bis Strasshof Restarbeiten in der Hst. Silberwald |  | N |  | 21.03.2025 | High |  | 31-50%
0081 | 81-B-91387 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.) | < > | Velden am Wörthersee | Föderlach | 2027 | 2027 | 40 | 45 | 09.10.2027 | 07:00 | 11.11.2027 | 07:00 | 33 days + 1,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 10 |  | Unterbausanierung und Weichenneulage W51,53,54 |  | N |  | 02.06.2025 | High |  | 31-50%
0081 | 81-B-99195 | Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), St.Michael (in M)=St.Michael-West (in M) | < > | St.Michael-Ost | Kraubath | 2027 | 2027 | 31 | 32 | 02.08.2027 | 20:30 | 12.08.2027 | 20:30 | 10 days | continuous | Others |  | LT | [6 empty] | 0 |  | Hauptarbeiten Weichenneulagen W153,W154 PLV Gleisneulagen Gl2 |  | N |  | 23.10.2025 | High |  | 31-50%
0055 | 5526001001 | Budapest - Komárom | > | Tata | Almásfüzitő felső | 2026 | 2026 | 7 | 7 | 2026-02-14 | 9:50 | 2026-02-14 | 18:00 | 8h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001002 | Budapest - Komárom | > | Tata | Almásfüzitő felső | 2026 | 2026 | 7 | 7 | 2026-02-15 | 9:50 | 2026-02-15 | 18:00 | 8h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001003 | Budapest - Komárom | > | Tata | Almásfüzitő | 2026 | 2026 | 8 | 8 | 2026-02-21 | 9:50 | 2026-02-21 | 18:00 | 8h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001004 | Budapest - Komárom | > | Tata | Almásfüzitő | 2026 | 2026 | 8 | 8 | 2026-02-22 | 9:50 | 2026-02-22 | 18:00 | 8h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001005 | Budapest - Komárom | > | Almásfüzitő | Almásfüzitő felső | 2026 | 2026 | 9 | 9 | 2026-02-23 | 9:50 | 2026-02-23 | 18:00 | 8h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001006 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 16 | 16 | 2026-04-17 | 22:00 | 2026-04-19 | 6:00 | 32h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001007 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 17 | 17 | 2026-04-24 | 22:00 | 2026-04-26 | 6:00 | 32h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001008 | Komárom-Hegyeshalom | > | Almásfüzitő felső | Komárom | 2026 | 2026 | 19 | 19 | 2026-05-05 | 19:00 | 2026-05-06 | 7:00 | 12h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001009 | Komárom-Hegyeshalom | > | Kimle-Károlyháza | Mosonmagyaróvár | 2026 | 2026 | 19 | 21 | 2026-05-10 | 21:00 | 2026-05-18 | 4:00 | 7d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001010 | Komárom-Hegyeshalom | > | Lébény-Mosonszentmiklós | Kimle-Károlyháza | 2026 | 2026 | 21 | 21 | 2026-05-18 | 4:00 | 2026-05-21 | 4:00 | 3d | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001011 | Komárom-Hegyeshalom | > | Győrszentiván | Győrszentiván | 2026 | 2026 | 24 | 25 | 2026-06-12 | 22:00 | 2026-06-15 | 5:00 | 2d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001012 | Budapest - Komárom | > | Tatabánya | Tata | 2026 | 2026 | 27 | 27 | 2026-06-29 | 0:00 | 2026-07-01 | 12:00 | 2d12h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001013 | Budapest - Komárom | > | Tatabánya | Tata | 2026 | 2026 | 27 | 27 | 2026-07-01 | 12:00 | 2026-07-03 | 23:59 | 2d11h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001014 | Budapest - Komárom | > | Szárliget | Tatabánya | 2026 | 2026 | 28 | 28 | 2026-07-10 | 22:00 | 2026-07-12 | 2:00 | 1d4h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001015 | Budapest - Komárom | > | Tata | Almásfüzitő | 2026 | 2026 | 29 | 30 | 2026-07-17 | 22:00 | 2026-07-20 | 5:00 | 2d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001016 | Budapest - Komárom | > | Almásfüzitő | Almásfüzitő | 2026 | 2026 | 33 | 34 | 2026-08-14 | 22:00 | 2026-08-17 | 5:00 | 2d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001017 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 11 | 11 | 2026-03-09 | 9:00 | 2026-03-09 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001018 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 11 | 11 | 2026-03-10 | 9:00 | 2026-03-10 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001019 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 11 | 11 | 2026-03-11 | 9:00 | 2026-03-11 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001020 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 11 | 11 | 2026-03-12 | 9:00 | 2026-03-12 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001021 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 11 | 11 | 2026-03-13 | 9:00 | 2026-03-13 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001022 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 12 | 12 | 2026-03-16 | 9:00 | 2026-03-16 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001023 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 12 | 12 | 2026-03-17 | 9:00 | 2026-03-17 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001024 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 12 | 12 | 2026-03-18 | 9:00 | 2026-03-18 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001025 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 12 | 12 | 2026-03-19 | 9:00 | 2026-03-19 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001026 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 12 | 12 | 2026-03-20 | 9:00 | 2026-03-20 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001027 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 13 | 13 | 2026-03-23 | 9:00 | 2026-03-23 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001028 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 13 | 13 | 2026-03-24 | 9:00 | 2026-03-24 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001029 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 13 | 13 | 2026-03-25 | 9:00 | 2026-03-25 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001030 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 13 | 13 | 2026-03-26 | 9:00 | 2026-03-26 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001031 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 13 | 13 | 2026-03-27 | 9:00 | 2026-03-27 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001032 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 14 | 14 | 2026-03-30 | 9:00 | 2026-03-30 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001033 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 14 | 14 | 2026-03-31 | 9:00 | 2026-03-31 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001034 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 14 | 14 | 2026-04-01 | 9:00 | 2026-04-01 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001035 | Budapest - Komárom | > | Budapest-Keleti | Ferencváros | 2026 | 2026 | 14 | 14 | 2026-04-02 | 9:00 | 2026-04-02 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001036 | Komárom-Hegyeshalom | > | Győr-Rendező | Győr-Rendező | 2026 | 2026 | 12 | 12 | 2026-03-20 | 22:50 | 2026-03-21 | 4:25 | 5h35m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001037 | Budapest - Komárom | > | Herceghalom | Herceghalom | 2026 | 2026 | 12 | 12 | 2026-03-20 | 22:15 | 2026-03-21 | 4:50 | 6h35m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001038 | Budapest - Komárom | > | Komárom szpu. | Komárom szpu. | 2026 | 2026 | 12 | 12 | 2026-03-21 | 22:50 | 2026-03-22 | 5:00 | 6h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001039 | Budapest - Komárom | > | Budaörs | Budaörs | 2026 | 2026 | 12 | 12 | 2026-03-21 | 22:25 | 2026-03-22 | 4:35 | 6h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001040 | Komárom-Hegyeshalom | > | Győr személy | Győr személy | 2026 | 2026 | 13 | 13 | 2026-03-27 | 23:40 | 2026-03-28 | 4:25 | 4h45m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001041 | Budapest - Komárom | > | Biatorbágy | Biatorbágy | 2026 | 2026 | 13 | 13 | 2026-03-27 | 22:10 | 2026-03-28 | 4:45 | 6h35m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001042 | Budapest - Komárom | > | Komárom-Rendező | Komárom-Rendező | 2026 | 2026 | 13 | 13 | 2026-03-28 | 22:50 | 2026-03-29 | 5:50 | 7h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001043 | Budapest - Komárom | > | Bicske | Bicske | 2026 | 2026 | 13 | 13 | 2026-03-28 | 22:05 | 2026-03-29 | 4:45 | 6h40m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001044 | Budapest - Komárom | > | Almásfüzitő | Almásfüzitő | 2026 | 2026 | 19 | 19 | 2026-05-08 | 22:40 | 2026-05-09 | 5:00 | 6h20m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001045 | Komárom-Hegyeshalom | > | Kimle-Károlyháza | Kimle-Károlyháza | 2026 | 2026 | 19 | 19 | 2026-05-08 | 23:10 | 2026-05-09 | 5:20 | 6h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001046 | Komárom-Hegyeshalom | > | Lébény-Mosonszentmiklós | Lébény-Mosonszentmiklós | 2026 | 2026 | 20 | 20 | 2026-04-11 | 23:05 | 2026-04-12 | 4:40 | 5h35m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001047 | Komárom-Hegyeshalom | > | Ács | Ács | 2026 | 2026 | 20 | 20 | 2026-04-11 | 22:10 | 2026-04-12 | 4:50 | 6h40m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001048 | Budapest - Komárom | > | Tatabánya | Tatabánya | 2026 | 2026 | 21 | 21 | 2026-04-18 | 22:50 | 2026-04-19 | 3:45 | 4h55m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001049 | Komárom-Hegyeshalom | > | Győrszentiván | Győrszentiván | 2026 | 2026 | 21 | 21 | 2026-04-18 | 22:15 | 2026-04-19 | 5:30 | 7h15m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001050 | Komárom-Hegyeshalom | > | Mosonmagyaróvár | Mosonmagyaróvár | 2026 | 2026 | 21 | 22 | 2026-04-24 | 23:15 | 2026-04-25 | 4:25 | 5h10m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001051 | Budapest - Komárom | > | Tata | Tata | 2026 | 2026 | 21 | 22 | 2026-04-24 | 22:00 | 2026-04-25 | 5:20 | 7h20m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001052 | Komárom-Hegyeshalom | > | Nagyszentjános | Nagyszentjános | 2026 | 2026 | 22 | 22 | 2026-04-25 | 22:10 | 2026-04-26 | 5:35 | 7h25m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001053 | Budapest - Komárom | > | Szárliget | Szárliget | 2026 | 2026 | 22 | 22 | 2026-04-25 | 22:10 | 2026-04-26 | 5:00 | 6h50m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001054 | Komárom-Hegyeshalom | > | Öttevény | Öttevény | 2026 | 2026 | 19 | 19 | 2026-05-09 | 23:05 | 2026-05-10 | 4:45 | 5h40m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001055 | Budapest - Komárom | > | Almásfüzitő-felső | Almásfüzitő-felső | 2026 | 2026 | 19 | 19 | 2026-05-09 | 22:45 | 2026-05-10 | 5:00 | 6h15m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001056 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 21 | 21 | 2026-05-22 | 22:40 | 2026-05-23 | 5:10 | 6h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001057 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 21 | 21 | 2026-05-23 | 22:40 | 2026-05-24 | 5:10 | 6h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001058 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 22 | 22 | 2026-05-29 | 22:40 | 2026-05-30 | 5:10 | 6h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001059 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 22 | 22 | 2026-05-30 | 22:40 | 2026-05-31 | 5:10 | 6h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001060 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 24 | 24 | 2026-06-12 | 22:40 | 2026-06-13 | 5:10 | 6h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001061 | Komárom-Hegyeshalom | > | Hegyeshalom | Hegyeshalom | 2026 | 2026 | 24 | 24 | 2026-06-13 | 22:40 | 2026-06-14 | 5:10 | 6h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001062 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 3 | 3 | 2026-01-12 | 9:00 | 2026-01-12 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001063 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 3 | 3 | 2026-01-13 | 9:00 | 2026-01-13 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001064 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-20 | 23:30 | 2026-01-21 | 2:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001065 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-21 | 2:00 | 2026-01-21 | 5:30 | 3h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001066 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-21 | 23:30 | 2026-01-22 | 2:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001067 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-22 | 2:30 | 2026-01-22 | 5:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001068 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-23 | 0:30 | 2026-01-23 | 2:30 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001069 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-23 | 2:30 | 2026-01-23 | 5:00 | 2h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001070 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-23 | 23:30 | 2026-01-24 | 2:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001071 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-24 | 2:00 | 2026-01-24 | 5:30 | 3h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001072 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-24 | 23:30 | 2026-01-25 | 2:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001073 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 4 | 4 | 2026-01-25 | 2:00 | 2026-01-25 | 5:30 | 3 | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001074 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-26 | 0:30 | 2026-01-26 | 2:45 | 3h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001075 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-26 | 2:45 | 2026-01-26 | 5:00 | 2h15m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001076 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-26 | 23:30 | 2026-01-27 | 2:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001077 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-27 | 2:00 | 2026-01-27 | 5:30 | 3h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001078 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-27 | 23:30 | 2026-01-28 | 2:30 | 3h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001079 | Budapest - Komárom | < > | Ferencváros | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-28 | 2:00 | 2026-01-28 | 5:30 | 3h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001080 | Budapest - Komárom | < > | Keleti pu. | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-30 | 0:30 | 2026-01-30 | 2:30 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001081 | Budapest - Komárom | < > | Ferencváros | Kőbánya felső | 2026 | 2026 | 5 | 5 | 2026-01-30 | 0:30 | 2026-01-30 | 2:30 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001082 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 5 | 5 | 2026-01-30 | 0:30 | 2026-01-30 | 2:30 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001083 | Budapest - Komárom | < > | Ferencváros | Soroksári út | 2026 | 2026 | 5 | 5 | 2026-01-30 | 0:30 | 2026-01-30 | 2:30 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001084 | Budapest - Komárom | < > | Ferencváros | Kőbánya-Kispest | 2026 | 2026 | 5 | 5 | 2026-01-30 | 0:30 | 2026-01-30 | 2:30 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001085 | Budapest - Komárom | < > | Keleti pu. | Ferencváros | 2026 | 2026 | 5 | 5 | 2026-01-30 | 2:30 | 2026-01-30 | 5:00 | 2h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001086 | Budapest - Komárom | < > | Ferencváros | Kőbánya felső | 2026 | 2026 | 5 | 5 | 2026-01-30 | 2:30 | 2026-01-30 | 5:00 | 2h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001087 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 5 | 5 | 2026-01-30 | 2:30 | 2026-01-30 | 5:00 | 2h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001088 | Budapest - Komárom | < > | Ferencváros | Soroksári út | 2026 | 2026 | 5 | 5 | 2026-01-30 | 2:30 | 2026-01-30 | 5:00 | 2h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001089 | Budapest - Komárom | < > | Ferencváros | Kőbánya-Kispest | 2026 | 2026 | 5 | 5 | 2026-01-30 | 2:30 | 2026-01-30 | 5:00 | 2h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001090 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 6 | 6 | 2026-02-02 | 9:00 | 2026-02-02 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001091 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 6 | 6 | 2026-02-03 | 9:00 | 2026-02-03 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001092 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 6 | 6 | 2026-02-04 | 9:00 | 2026-02-04 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001093 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 6 | 6 | 2026-02-05 | 9:00 | 2026-02-05 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001094 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 6 | 6 | 2026-02-06 | 9:00 | 2026-02-06 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001095 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 7 | 7 | 2026-02-09 | 9:00 | 2026-02-09 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001096 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 7 | 7 | 2026-02-10 | 9:00 | 2026-02-10 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001097 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 7 | 7 | 2026-02-11 | 9:00 | 2026-02-11 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001098 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 7 | 7 | 2026-02-12 | 9:00 | 2026-02-12 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001099 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 7 | 7 | 2026-02-13 | 9:00 | 2026-02-13 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001100 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 7 | 7 | 2026-02-16 | 9:00 | 2026-02-16 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001101 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 8 | 8 | 2026-02-17 | 9:00 | 2026-02-17 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001102 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 8 | 8 | 2026-02-18 | 9:00 | 2026-02-18 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001103 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 8 | 8 | 2026-02-19 | 9:00 | 2026-02-19 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001104 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 8 | 8 | 2026-02-20 | 9:00 | 2026-02-20 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001105 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 9 | 9 | 2026-02-23 | 9:00 | 2026-02-23 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001106 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 9 | 9 | 2026-02-24 | 9:00 | 2026-02-24 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001107 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 9 | 9 | 2026-02-25 | 9:00 | 2026-02-25 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001108 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 9 | 9 | 2026-02-26 | 9:00 | 2026-02-26 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001109 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 9 | 9 | 2026-02-27 | 9:00 | 2026-02-27 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001110 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 10 | 10 | 2026-03-02 | 9:00 | 2026-03-02 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001111 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 10 | 10 | 2026-03-03 | 9:00 | 2026-03-03 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001112 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 10 | 10 | 2026-03-04 | 9:00 | 2026-03-04 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001113 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 10 | 10 | 2026-03-05 | 9:00 | 2026-03-05 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001114 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 10 | 10 | 2026-03-06 | 9:00 | 2026-03-06 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001115 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 11 | 11 | 2026-03-09 | 9:00 | 2026-03-09 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001116 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 11 | 11 | 2026-03-10 | 9:00 | 2026-03-10 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001117 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 11 | 11 | 2026-03-11 | 9:00 | 2026-03-11 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001118 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 11 | 11 | 2026-03-12 | 9:00 | 2026-03-12 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001119 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 11 | 11 | 2026-03-13 | 9:00 | 2026-03-13 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001120 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 12 | 12 | 2026-03-16 | 9:00 | 2026-03-16 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001121 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 12 | 12 | 2026-03-17 | 9:00 | 2026-03-17 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001122 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 12 | 12 | 2026-03-18 | 9:00 | 2026-03-18 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001123 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 12 | 12 | 2026-03-19 | 9:00 | 2026-03-19 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001124 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 12 | 12 | 2026-03-20 | 9:00 | 2026-03-20 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001125 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 13 | 13 | 2026-03-23 | 9:00 | 2026-03-23 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001126 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 13 | 13 | 2026-03-24 | 9:00 | 2026-03-24 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001127 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 13 | 13 | 2026-03-25 | 9:00 | 2026-03-25 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001128 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 13 | 13 | 2026-03-26 | 9:00 | 2026-03-26 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001129 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 13 | 13 | 2026-03-27 | 9:00 | 2026-03-27 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001130 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 14 | 14 | 2026-03-30 | 9:00 | 2026-03-30 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001131 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 14 | 14 | 2026-03-31 | 9:00 | 2026-03-31 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001132 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 14 | 14 | 2026-04-01 | 9:00 | 2026-04-01 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001133 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 14 | 14 | 2026-04-02 | 9:00 | 2026-04-02 | 16:00 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001134 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 15 | 22 | 2026-04-07 | 8:00 | 2026-05-28 | 15:30 | 51d7h30m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001135 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 15 | 15 | 2026-04-07 | 23:00 | 2026-04-08 | 5:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001136 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 17 | 17 | 2026-04-20 | 23:30 | 2026-04-21 | 4:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001137 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 17 | 17 | 2026-04-21 | 23:30 | 2026-04-22 | 4:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001138 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 17 | 17 | 2026-04-21 | 23:30 | 2026-04-22 | 4:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001139 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 19 | 19 | 2026-05-05 | 0:30 | 2026-05-05 | 5:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001140 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 19 | 19 | 2026-05-06 | 0:30 | 2026-05-06 | 5:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001141 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 19 | 19 | 2026-05-07 | 0:30 | 2026-05-07 | 5:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001142 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 19 | 19 | 2026-05-08 | 0:30 | 2026-05-08 | 5:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001143 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 19 | 19 | 2026-05-09 | 0:30 | 2026-05-09 | 5:30 | 5h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001144 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 21 | 21 | 2026-05-19 | 9:00 | 2026-05-19 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001145 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 21 | 21 | 2026-05-20 | 9:00 | 2026-05-20 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001146 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 21 | 21 | 2026-05-20 | 9:00 | 2026-05-20 | 13:00 | 4h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001147 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 21 | 21 | 2026-05-21 | 9:00 | 2026-05-21 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001148 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 21 | 21 | 2026-05-21 | 9:00 | 2026-05-21 | 13:00 | 4h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001149 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 22 | 22 | 2026-05-26 | 9:00 | 2026-05-26 | 10:00 | 1h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001150 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 22 | 22 | 2026-05-26 | 10:00 | 2026-05-26 | 11:00 | 1h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001151 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 22 | 22 | 2026-05-26 | 11:00 | 2026-05-26 | 13:00 | 2h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001152 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 22 | 22 | 2026-05-26 | 9:00 | 2026-05-26 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001153 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 22 | 22 | 2026-05-27 | 9:00 | 2026-05-27 | 13:00 | 4h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001154 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 22 | 22 | 2026-05-27 | 9:00 | 2026-05-27 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001155 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 22 | 22 | 2026-05-28 | 9:00 | 2026-05-28 | 15:00 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001156 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 22 | 26 | 2026-05-28 | 15:00 | 2026-06-25 | 17:59 | 28d2h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001157 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 26 | 26 | 2026-06-24 | 9:00 | 2026-06-24 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001158 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 26 | 26 | 2026-06-25 | 9:00 | 2026-06-25 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001159 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 26 | 37 | 2026-06-25 | 18:00 | 2026-09-11 | 17:59 | 77d23h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001160 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 27 | 27 | 2026-06-30 | 8:00 | 2026-06-30 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001161 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 27 | 27 | 2026-07-01 | 8:00 | 2026-07-01 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001162 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 27 | 27 | 2026-07-02 | 8:00 | 2026-07-02 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001163 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 27 | 27 | 2026-07-03 | 8:00 | 2026-07-03 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001164 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 27 | 27 | 2026-07-04 | 8:00 | 2026-07-04 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001165 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 28 | 28 | 2026-07-07 | 8:00 | 2026-07-07 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001166 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 28 | 28 | 2026-07-08 | 8:00 | 2026-07-08 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001167 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 28 | 28 | 2026-07-09 | 8:00 | 2026-07-09 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001168 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 28 | 28 | 2026-07-10 | 8:00 | 2026-07-10 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001169 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 28 | 28 | 2026-07-11 | 8:00 | 2026-07-11 | 18:00 | 10h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001170 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 31 | 31 | 2026-07-27 | 9:00 | 2026-07-27 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001171 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 36 | 36 | 2026-08-31 | 9:00 | 2026-08-31 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001172 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 36 | 36 | 2026-09-01 | 23:30 | 2026-09-02 | 5:30 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001173 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 36 | 36 | 2026-09-02 | 23:30 | 2026-09-03 | 5:30 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001174 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 36 | 36 | 2026-09-03 | 23:30 | 2026-09-04 | 5:30 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001175 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 37 | 37 | 2026-09-08 | 23:30 | 2026-09-09 | 5:30 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001176 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 37 | 37 | 2026-09-09 | 23:30 | 2026-09-10 | 5:30 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001177 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 37 | 37 | 2026-09-10 | 23:30 | 2026-09-11 | 5:30 | 6h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001178 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 37 | 38 | 2026-09-11 | 18:00 | 2026-10-15 | 8:00 | 33d14h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001179 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 35 | 35 | 2026-08-30 | 8:00 | 2026-08-30 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001180 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 38 | 39 | 2026-09-14 | 8:00 | 2026-10-27 | 17:59 | 43d9h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001181 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 39 | 39 | 2026-09-27 | 8:00 | 2026-09-27 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001182 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 43 | 43 | 2026-10-19 | 8:00 | 2026-10-19 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001183 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 43 | 43 | 2026-10-20 | 8:00 | 2026-10-20 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001184 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 43 | 43 | 2026-10-21 | 8:00 | 2026-10-21 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001185 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 43 | 43 | 2026-10-22 | 8:00 | 2026-10-22 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001186 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 44 | 44 | 2026-10-26 | 8:00 | 2026-10-26 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001187 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 44 | 44 | 2026-10-27 | 8:00 | 2026-10-27 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001188 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 42 | 44 | 2026-10-15 | 8:00 | 2026-10-27 | 17:59 | 12d9h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001189 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 42 | 42 | 2026-10-15 | 8:00 | 2026-10-15 | 14:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001190 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 43 | 43 | 2026-10-21 | 22:00 | 2026-10-22 | 6:00 | 8h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001191 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 44 | 46 | 2026-10-27 | 18:00 | 2026-11-09 | 17:59 | 12d23h559m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001192 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 44 | 44 | 2026-10-27 | 18:00 | 2026-10-27 | 24:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001193 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 45 | 45 | 2026-11-02 | 23:30 | 2026-11-03 | 5:30 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001194 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 45 | 45 | 2026-11-03 | 23:30 | 2026-11-04 | 5:30 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001195 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 45 | 45 | 2026-11-04 | 23:30 | 2026-11-05 | 5:30 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001196 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 45 | 45 | 2026-11-06 | 23:30 | 2026-11-07 | 5:30 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001197 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 45 | 45 | 2026-11-07 | 23:30 | 2026-11-08 | 5:30 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001198 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 45 | 46 | 2026-11-08 | 23:30 | 2026-11-09 | 5:30 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001199 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 46 | 46 | 2026-11-09 | 23:30 | 2026-11-10 | 3:00 | 3h30m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001200 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 46 | 46 | 2026-11-10 | 3:00 | 2026-11-10 | 5:00 | 2h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001201 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 46 | 46 | 2026-11-09 | 18:00 | 2027-09-05 | 17:59 | 299d23h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001202 | Budapest - Komárom | > | Ferencváros | Kelenföld | 2026 | 2026 | 46 | 46 | 2026-11-11 | 9:30 | 2026-11-11 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001203 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 46 | 46 | 2026-11-12 | 9:30 | 2026-11-12 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001204 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 46 | 46 | 2026-11-13 | 9:30 | 2026-11-13 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001205 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 47 | 47 | 2026-11-16 | 9:30 | 2026-11-16 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001206 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 47 | 47 | 2026-11-17 | 9:30 | 2026-11-17 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001207 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 47 | 47 | 2026-11-18 | 9:30 | 2026-11-18 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001208 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 47 | 47 | 2026-11-19 | 9:30 | 2026-11-19 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001209 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 47 | 47 | 2026-11-20 | 9:30 | 2026-11-20 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001210 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 48 | 48 | 2026-11-23 | 9:30 | 2026-11-23 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001211 | Budapest - Komárom | > | Kelenföld | Kelenföld | 2026 | 2026 | 48 | 48 | 2026-11-24 | 9:30 | 2026-11-24 | 16:30 | 7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001212 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 49 | 49 | 2026-12-01 | 9:00 | 2026-12-01 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001213 | Budapest - Komárom | < > | Ferencváros | Kelenföld | 2026 | 2026 | 49 | 49 | 2026-12-02 | 9:00 | 2026-12-02 | 13:00 | 4h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001214 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 49 | 49 | 2026-12-03 | 21:30 | 2026-12-04 | 5:30 | 8h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526001215 | Budapest - Komárom | > | Ferencváros | Ferencváros | 2026 | 2026 | 49 | 49 | 2026-12-04 | 21:30 | 2026-12-05 | 5:30 | 8h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070001 | Budapest - Nové Zámky | > | Vác | Verőce | 2026 | 2026 | 7 | 7 | 2026-02-09 | 8:05 | 2026-02-13 | 19:00 | 4d10h55m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070002 | Budapest - Nové Zámky | > | Vác | Verőce | 2026 | 2026 | 8 | 8 | 2026-02-16 | 8:05 | 2026-02-17 | 19:00 | 1d10h55m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070003 | Budapest - Nové Zámky | > | Vác | Vác | 2026 | 2026 | 13 | 13 | 2026-03-28 | 23:35 | 2026-03-29 | 5:25 | 5h50m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070004 | Budapest - Nové Zámky | > | Nagymaros | Szob | 2026 | 2026 | 16 | 16 | 2026-04-13 | 9:00 | 2026-04-17 | 22:00 | 4d13h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070005 | Budapest - Nové Zámky | > | Szob | Szob | 2026 | 2026 | 16 | 16 | 2026-04-14 | 8:55 | 2026-04-14 | 14:10 | 5h15m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070006 | Budapest - Nové Zámky | > | Szob | Szob | 2026 | 2026 | 16 | 16 | 2026-04-15 | 8:55 | 2026-04-15 | 14:10 | 5h15m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070007 | Budapest - Nové Zámky | > | Verőce | Verőce | 2026 | 2026 | 16 | 17 | 2026-04-17 | 23:00 | 2026-04-20 | 5:00 | 2d6h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070008 | Budapest - Nové Zámky | > | Rákospalota-Újpest | Dunakeszi | 2026 | 2026 | 17 | 18 | 2026-04-24 | 22:00 | 2026-04-27 | 5:00 | 2d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070009 | Budapest - Nové Zámky | > | Göd | Vác | 2026 | 2026 | 19 | 19 | 2026-05-08 | 22:00 | 2026-05-10 | 1:00 | 1d3h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070010 | Budapest - Nové Zámky | > | Göd | Vác | 2026 | 2026 | 19 | 20 | 2026-05-10 | 1:00 | 2026-05-11 | 5:00 | 1d4h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070011 | Budapest - Nové Zámky | > | Göd | Vác | 2026 | 2026 | 20 | 20 | 2026-05-15 | 22:00 | 2026-05-17 | 1:00 | 1d3h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070012 | Budapest - Nové Zámky | > | Göd | Vác | 2026 | 2026 | 20 | 21 | 2026-05-17 | 1:00 | 2026-05-18 | 5:00 | 1d4h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070013 | Budapest - Nové Zámky | > | Nagymaros | Szob | 2026 | 2026 | 25 | 25 | 2026-06-15 | 9:00 | 2026-06-19 | 22:00 | 4d13h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070014 | Budapest - Nové Zámky | > | Rákospalota-Újpest | Dunakeszi | 2026 | 2026 | 28 | 29 | 2026-07-10 | 22:00 | 2026-07-18 | 23:59 | 8d2h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070015 | Budapest - Nové Zámky | > | Nagymaros | Szob | 2026 | 2026 | 33 | 33 | 2026-08-10 | 9:00 | 2026-08-14 | 22:00 | 4d13h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070016 | Budapest - Nové Zámky | > | Vác | Verőce | 2026 | 2026 | 35 | 36 | 2026-08-28 | 22:00 | 2026-08-31 | 5:00 | 2d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070017 | Budapest - Nové Zámky | > | Verőce | Nagymaros | 2026 | 2026 | 38 | 39 | 2026-09-18 | 22:00 | 2026-09-21 | 5:00 | 2d7h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070018 | Budapest - Nové Zámky | > | Vác | Vác | 2026 | 2026 | 40 | 40 | 2026-10-03 | 23:35 | 2026-10-04 | 5:25 | 5h50m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070019 | Budapest - Nové Zámky | > | Nagymaros | Szob | 2026 | 2026 | 42 | 42 | 2026-10-12 | 9:00 | 2026-10-16 | 22:00 | 4d13h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070020 | Budapest - Nové Zámky | > | Szob | Szob | 2026 | 2026 | 42 | 42 | 2026-10-13 | 8:55 | 2026-10-13 | 14:10 | 5h15m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526070021 | Budapest - Nové Zámky | > | Szob | Szob | 2026 | 2026 | 42 | 42 | 2026-10-14 | 8:55 | 2026-10-14 | 14:10 | 5h15m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030001 | Budapest-Székesfehérvár | < > | Budapest-Déli | Budapest-Kelenföld | 2026 | 2026 | 10 | 10 | 2026-03-07 | 0:00 | 2026-03-08 | 23:59 | 1d23h59m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030002 | Budapest-Székesfehérvár | > | Székesfehérvár | Szabadbattyán | 2026 | 2026 | 12 | 12 | 2026-03-16 | 3:00 | 2026-03-21 | 23:59 | 5d20h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030003 | Budapest-Székesfehérvár | < > | Szabadbattyán | Lepsény | 2026 | 2026 | 12 | 13 | 2026-03-16 | 6:00 | 2026-03-27 | 22:00 | 11d16h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030004 | Székesfehérvár-Murakeresztúr | < > | Lepsény | Balatonaliga | 2026 | 2026 | 12 | 12 | 2026-03-16 | 23:30 | 2026-03-17 | 4:30 | 5h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030005 | Székesfehérvár-Murakeresztúr | < > | Lepsény | Balatonaliga | 2026 | 2026 | 12 | 12 | 2026-03-16 | 23:30 | 2026-03-17 | 4:30 | 5h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030006 | Székesfehérvár-Murakeresztúr | < > | Lepsény | Balatonaliga | 2026 | 2026 | 12 | 12 | 2026-03-17 | 23:30 | 2026-03-18 | 4:30 | 5h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030007 | Székesfehérvár-Murakeresztúr | < > | Balatonaliga | Siófok | 2026 | 2026 | 12 | 12 | 2026-03-17 | 23:40 | 2026-03-18 | 4:20 | 4h40m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030008 | Székesfehérvár-Murakeresztúr | < > | Lepsény | Balatonaliga | 2026 | 2026 | 12 | 12 | 2026-03-18 | 23:30 | 2026-03-19 | 4:30 | 5h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030009 | Székesfehérvár-Murakeresztúr | < > | Balatonaliga | Siófok | 2026 | 2026 | 12 | 12 | 2026-03-18 | 23:40 | 2026-03-19 | 4:20 | 4h40m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030010 | Székesfehérvár-Murakeresztúr | < > | Balatonszemes | Balatonboglár | 2026 | 2026 | 12 | 12 | 2026-03-19 | 22:50 | 2026-03-20 | 4:25 | 5h35m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030011 | Székesfehérvár-Murakeresztúr | < > | Lepsény | Balatonaliga | 2026 | 2026 | 12 | 12 | 2026-03-19 | 23:30 | 2026-03-20 | 4:30 | 5h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030012 | Székesfehérvár-Murakeresztúr | < > | Balatonszemes | Balatonboglár | 2026 | 2026 | 12 | 12 | 2026-03-20 | 22:50 | 2026-03-21 | 4:25 | 5h35m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030013 | Székesfehérvár-Murakeresztúr | < > | Lepsény | Balatonaliga | 2026 | 2026 | 12 | 12 | 2026-03-20 | 23:30 | 2026-03-21 | 4:30 | 5h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030014 | Székesfehérvár-Murakeresztúr | < > | Kiscséripuszta | Lepsény | 2026 | 2026 | 12 | 12 | 2026-03-21 | 22:30 | 2026-03-22 | 5:00 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030015 | Székesfehérvár-Murakeresztúr | > | Székesfehérvár | Szabadbattyán | 2026 | 2026 | 12 | 13 | 2026-03-22 | 0:00 | 2026-03-27 | 23:59 | 5d23h59m | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030016 | Székesfehérvár-Murakeresztúr | < > | Kiscséripuszta | Lepsény | 2026 | 2026 | 13 | 13 | 2026-03-22 | 22:30 | 2026-03-23 | 5:00 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030017 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszemes | 2026 | 2026 | 13 | 13 | 2026-03-23 | 22:25 | 2026-03-24 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030018 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszárszó | 2026 | 2026 | 13 | 13 | 2026-03-23 | 22:25 | 2026-03-24 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030019 | Székesfehérvár-Murakeresztúr | < > | Kiscséripuszta | Lepsény | 2026 | 2026 | 13 | 13 | 2026-03-23 | 22:30 | 2026-03-24 | 5:00 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030020 | Székesfehérvár-Murakeresztúr | < > | Balatonszárszó | Balatonszemes | 2026 | 2026 | 13 | 13 | 2026-03-24 | 22:25 | 2026-03-25 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030021 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszemes | 2026 | 2026 | 13 | 13 | 2026-03-24 | 22:25 | 2026-03-25 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030022 | Székesfehérvár-Murakeresztúr | < > | Kiscséripuszta | Lepsény | 2026 | 2026 | 13 | 13 | 2026-03-24 | 22:30 | 2026-03-25 | 5:00 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030023 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszemes | 2026 | 2026 | 13 | 13 | 2026-03-25 | 22:25 | 2026-03-26 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030024 | Székesfehérvár-Murakeresztúr | < > | Kiscséripuszta | Lepsény | 2026 | 2026 | 13 | 13 | 2026-03-25 | 22:30 | 2026-03-26 | 5:00 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030025 | Székesfehérvár-Murakeresztúr | < > | Siófok | Zamárdi felső | 2026 | 2026 | 13 | 13 | 2026-03-25 | 23:40 | 2026-03-26 | 4:30 | 4h50m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030026 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszárszó | 2026 | 2026 | 13 | 13 | 2026-03-26 | 22:25 | 2026-03-27 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030027 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszemes | 2026 | 2026 | 13 | 13 | 2026-03-26 | 22:25 | 2026-03-27 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030028 | Székesfehérvár-Murakeresztúr | < > | Kiscséripuszta | Lepsény | 2026 | 2026 | 13 | 13 | 2026-03-26 | 22:30 | 2026-03-27 | 5:00 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030029 | Székesfehérvár-Murakeresztúr | < > | Zamárdi felső | Szántód | 2026 | 2026 | 13 | 13 | 2026-03-26 | 23:40 | 2026-03-27 | 4:25 | 4h45m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030030 | Székesfehérvár-Murakeresztúr | < > | Szántód | Balatonszemes | 2026 | 2026 | 13 | 13 | 2026-03-27 | 22:25 | 2026-03-28 | 5:20 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030031 | Budapest-Székesfehérvár | < > | Budapest-Déli | Budapest-Kelenföld | 2026 | 2026 | 13 | 13 | 2026-03-28 | 0:00 | 2026-03-29 | 23:59 | 1d23h59m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030032 | Székesfehérvár-Murakeresztúr | < > | Szabadbattyán | Lepsény | 2026 | 2026 | 13 | 14 | 2026-04-29 | 22:45 | 2026-04-30 | 5:15 | 6h30m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030033 | Székesfehérvár-Murakeresztúr | < > | Siófok | Szántód | 2026 | 2026 | 42 | 42 | 2026-10-12 | 0:00 | 2026-10-16 | 23:59 | 4d23h59m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030034 | Székesfehérvár-Murakeresztúr | > | Siófok | Siófok | 2026 | 2026 | 46 | 46 | 2026-11-13 | 22:00 | 2026-11-14 | 4:00 | 6h | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030035 | Székesfehérvár-Murakeresztúr | > | Balatonszentgyörgy | Balatonszentgyörgy | 2026 | 2026 | 47 | 47 | 2026-11-16 | 22:00 | 2026-11-17 | 4:00 | 6h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030036 | Székesfehérvár-Murakeresztúr | > | Balatonszentgyörgy | Balatonszentgyörgy | 2026 | 2026 | 47 | 47 | 2026-11-17 | 22:00 | 2026-11-18 | 4:00 | 6h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030037 | Székesfehérvár-Murakeresztúr | > | Balatonszentgyörgy | Balatonszentgyörgy | 2026 | 2026 | 47 | 47 | 2026-11-18 | 22:00 | 2026-11-19 | 4:00 | 6h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526030038 | Székesfehérvár-Murakeresztúr | > | Balatonszentgyörgy | Balatonszentgyörgy | 2026 | 2026 | 47 | 47 | 2026-11-20 | 7:00 | 2026-11-20 | 15:00 | 8h | continuous | Track & Rail |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040001 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Rétszilas | 2026 | 2026 | 15 | 15 | 2026-04-08 | 9:15 | 2026-04-08 | 10:40 | 1h25m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040002 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Rétszilas | 2026 | 2026 | 15 | 15 | 2026-04-08 | 11:30 | 2026-04-08 | 12:40 | 1h10m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040003 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Rétszilas | 2026 | 2026 | 16 | 16 | 2026-04-13 | 21:30 | 2026-04-14 | 5:30 | 8h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040004 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Rétszilas | 2026 | 2026 | 16 | 16 | 2026-04-14 | 21:30 | 2026-04-15 | 5:30 | 8h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040005 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Rétszilas | 2026 | 2026 | 16 | 16 | 2026-04-15 | 21:30 | 2026-04-16 | 5:30 | 8h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040006 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Rétszilas | 2026 | 2026 | 16 | 16 | 2026-04-16 | 21:30 | 2026-04-17 | 5:30 | 8h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040007 | Pusztaszabolcs-Dombóvár | < > | Pincehely | Keszőhidegkút-Gyönk | 2026 | 2026 | 17 | 17 | 2026-04-20 | 21:45 | 2026-04-21 | 6:15 | 8h30m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040008 | Pusztaszabolcs-Dombóvár | < > | Pincehely | Szakály-Hőgyész | 2026 | 2026 | 17 | 17 | 2026-04-21 | 21:45 | 2026-04-22 | 6:15 | 8h30m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040009 | Pusztaszabolcs-Dombóvár | < > | Keszőhidegkút-Gyönk | Kurd | 2026 | 2026 | 17 | 17 | 2026-04-22 | 21:45 | 2026-04-23 | 6:10 | 8h25m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040010 | Pusztaszabolcs-Dombóvár | < > | Szakály-Hőgyész | Kurd | 2026 | 2026 | 17 | 17 | 2026-04-23 | 21:50 | 2026-04-24 | 6:10 | 8h20m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040011 | Pusztaszabolcs-Dombóvár | < > | Szakály-Hőgyész | Döbrököz | 2026 | 2026 | 18 | 18 | 2026-04-27 | 21:50 | 2026-04-28 | 6:10 | 8h20m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040012 | Pusztaszabolcs-Dombóvár | < > | Kurd | Dombóvár | 2026 | 2026 | 18 | 18 | 2026-04-28 | 21:55 | 2026-04-29 | 6:00 | 8h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040013 | Pusztaszabolcs-Dombóvár | < > | Döbrököz | Dombóvár | 2026 | 2026 | 19 | 19 | 2026-05-04 | 21:55 | 2026-05-05 | 6:00 | 8h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040014 | Pusztaszabolcs-Dombóvár | < > | Rétszilas | Dombóvár | 2026 | 2026 | 22 | 26 | 2026-05-26 | 6:00 | 2026-06-23 | 22:00 | 28d16h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040015 | Pusztaszabolcs-Dombóvár | < > | Sárosd | Sárbogárd | 2026 | 2026 | 24 | 24 | 2026-07-13 | 21:40 | 2026-07-14 | 6:20 | 8h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040016 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Nagylók | 2026 | 2026 | 24 | 25 | 2026-07-14 | 21:40 | 2026-07-15 | 6:20 | 8h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040017 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Nagylók | 2026 | 2026 | 25 | 25 | 2026-07-15 | 21:40 | 2026-07-16 | 6:20 | 8h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040018 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Nagylók | 2026 | 2026 | 25 | 25 | 2026-07-16 | 21:40 | 2026-07-17 | 6:20 | 8h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040019 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Nagylók | 2026 | 2026 | 25 | 25 | 2026-07-17 | 21:40 | 2026-07-18 | 6:20 | 8h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040020 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Nagylók | 2026 | 2026 | 25 | 25 | 2026-07-20 | 21:40 | 2026-07-21 | 6:20 | 8h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040021 | Pusztaszabolcs-Dombóvár | < > | Rétszilas | Pincehely | 2026 | 2026 | 26 | 26 | 2026-07-27 | 21:30 | 2026-07-28 | 4:25 | 6h55m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040022 | Pusztaszabolcs-Dombóvár | < > | Pincehely | Dombóvár | 2026 | 2026 | 26 | 27 | 2026-07-28 | 21:55 | 2026-07-29 | 6:00 | 8h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040023 | Pusztaszabolcs-Dombóvár | < > | Pincehely | Dombóvár | 2026 | 2026 | 27 | 27 | 2026-07-29 | 21:55 | 2026-07-30 | 6:00 | 8h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040024 | Pusztaszabolcs-Dombóvár | > | Dombóvár | Dombóvár | 2026 | 2026 | 37 | 37 | 2026-09-07 | 8:10 | 2026-09-07 | 15:45 | 7h35m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040025 | Pusztaszabolcs-Dombóvár | > | Dombóvár | Dombóvár | 2026 | 2026 | 37 | 37 | 2026-09-08 | 8:10 | 2026-09-08 | 15:45 | 7h35m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040026 | Pusztaszabolcs-Dombóvár | > | Dombóvár | Dombóvár | 2026 | 2026 | 37 | 37 | 2026-09-09 | 8:10 | 2026-09-09 | 15:45 | 6h45m | continuous | other |  | LT | [8 empty] | Single line operation (closure of one track of a double track line) |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040027 | Pusztaszabolcs-Dombóvár | < > | Döbrököz | Dombóvár | 2026 | 2026 | 38 | 38 | 2026-09-14 | 23:15 | 2026-09-15 | 6:00 | 6h45m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040028 | Pusztaszabolcs-Dombóvár | < > | Kurd | Dombóvár | 2026 | 2026 | 38 | 38 | 2026-09-15 | 21:55 | 2026-09-16 | 6:00 | 8h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040029 | Pusztaszabolcs-Dombóvár | < > | Szakály-Hőgyész | Döbrököz | 2026 | 2026 | 38 | 38 | 2026-09-16 | 21:50 | 2026-09-17 | 6:10 | 8h20m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040030 | Pusztaszabolcs-Dombóvár | < > | Szakály-Hőgyész | Kurd | 2026 | 2026 | 38 | 38 | 2026-09-17 | 21:50 | 2026-09-18 | 6:10 | 8h20m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040031 | Pusztaszabolcs-Dombóvár | < > | Szentlőrinc | Pécs | 2026 | 2026 | 39 | 40 | 2026-09-21 | 6:00 | 2026-10-04 | 23:59 | 13d17h59m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040032 | Pusztaszabolcs-Dombóvár | < > | Keszőhidegkút-Gyönk | Kurd | 2026 | 2026 | 39 | 39 | 2026-09-21 | 21:45 | 2026-09-22 | 6:10 | 8h25m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040033 | Pusztaszabolcs-Dombóvár | < > | Pincehely | Szakály-Hőgyész | 2026 | 2026 | 39 | 39 | 2026-09-22 | 21:45 | 2026-09-23 | 6:15 | 8h30m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040034 | Pusztaszabolcs-Dombóvár | < > | Pincehely | Keszőhidegkút-Gyönk | 2026 | 2026 | 39 | 39 | 2026-09-23 | 21:45 | 2026-09-24 | 6:15 | 8h30m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040035 | Pusztaszabolcs-Dombóvár | < > | Tolnanémedi | Pincehely | 2026 | 2026 | 39 | 39 | 2026-09-24 | 21:30 | 2026-09-25 | 5:00 | 7h30m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040036 | Pusztaszabolcs-Dombóvár | < > | Rétszilas | Tolnanémedi | 2026 | 2026 | 40 | 40 | 2026-09-28 | 21:20 | 2026-09-29 | 4:00 | 6h40m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040037 | Pusztaszabolcs-Dombóvár | < > | Rétszilas | Simontornya | 2026 | 2026 | 40 | 40 | 2026-09-29 | 21:20 | 2026-09-30 | 4:50 | 7h30m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040038 | Pusztaszabolcs-Dombóvár | < > | Sárbogárd | Simontornya | 2026 | 2026 | 40 | 40 | 2026-09-30 | 21:30 | 2026-10-01 | 5:15 | 7h45m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040039 | Pusztaszabolcs-Dombóvár | < > | Nagylók | Rétszilas | 2026 | 2026 | 40 | 40 | 2026-10-01 | 21:40 | 2026-10-02 | 4:50 | 7h10m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040040 | Pusztaszabolcs-Dombóvár | < > | Dombóvár elágazás | Szentlőrinc | 2026 | 2026 | 41 | 43 | 2026-10-05 | 4:00 | 2026-10-21 | 23:59 | 16d19h59m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040041 | Pusztaszabolcs-Dombóvár | < > | Sárosd | Sárbogárd | 2026 | 2026 | 41 | 41 | 2026-10-05 | 21:50 | 2026-10-06 | 4:55 | 7h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040042 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Nagylók | 2026 | 2026 | 41 | 41 | 2026-10-06 | 21:50 | 2026-10-07 | 4:55 | 7h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040043 | Pusztaszabolcs-Dombóvár | < > | Szabadegyháza | Sárosd | 2026 | 2026 | 41 | 41 | 2026-10-07 | 21:50 | 2026-10-08 | 5:05 | 7h15m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040044 | Pusztaszabolcs-Dombóvár | < > | Pusztaszabolcs | Sárosd | 2026 | 2026 | 41 | 41 | 2026-10-08 | 22:00 | 2026-10-09 | 5:00 | 7h | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040045 | Pusztaszabolcs-Dombóvár | < > | Mecsekalja-Cserkút | Pécs | 2026 | 2026 | 44 | 44 | 2026-10-26 | 22:55 | 2026-10-27 | 5:00 | 6h5m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040046 | Pusztaszabolcs-Dombóvár | < > | Bicsérd | Mecsekalja-Cserkút | 2026 | 2026 | 44 | 44 | 2026-10-27 | 23:00 | 2026-10-28 | 5:00 | 6h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040047 | Pusztaszabolcs-Dombóvár | < > | Szentlőrinc | Mecsekalja-Cserkút | 2026 | 2026 | 44 | 44 | 2026-10-28 | 23:05 | 2026-10-29 | 5:00 | 5h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040048 | Pusztaszabolcs-Dombóvár | < > | Bükkösd | Bicsérd | 2026 | 2026 | 44 | 44 | 2026-10-29 | 23:05 | 2026-10-30 | 5:00 | 5h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040049 | Pusztaszabolcs-Dombóvár | < > | Abaliget | Szentlőrinc | 2026 | 2026 | 45 | 45 | 2026-11-02 | 22:30 | 2026-11-03 | 4:50 | 6h20m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040050 | Pusztaszabolcs-Dombóvár | < > | Godisa | Bükkösd | 2026 | 2026 | 45 | 45 | 2026-11-03 | 22:20 | 2026-11-04 | 5:00 | 6h40m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040051 | Pusztaszabolcs-Dombóvár | < > | Godisa | Abaliget | 2026 | 2026 | 45 | 45 | 2026-11-04 | 22:20 | 2026-11-05 | 5:10 | 6h50m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040052 | Pusztaszabolcs-Dombóvár | < > | Sásd | Abaliget | 2026 | 2026 | 45 | 45 | 2026-11-05 | 22:15 | 2026-11-06 | 5:10 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040053 | Pusztaszabolcs-Dombóvár | < > | Vásárosdombó | Godisa | 2026 | 2026 | 46 | 46 | 2026-11-09 | 22:10 | 2026-11-10 | 5:10 | 7h | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040054 | Pusztaszabolcs-Dombóvár | < > | Dombóvár elágazás | Godisa | 2026 | 2026 | 46 | 46 | 2026-11-10 | 22:15 | 2026-11-11 | 5:10 | 6h55m | continuous | other | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040055 | Pusztaszabolcs-Dombóvár | < > | Dombóvár | Szentlőrinc | 2026 | 2026 | 48 | 48 | 2026-11-23 | 22:45 | 2026-11-24 | 4:50 | 6h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 | 5526040056 | Pusztaszabolcs-Dombóvár | < > | Dombóvár | Szentlőrinc | 2026 | 2026 | 48 | 48 | 2026-11-24 | 22:45 | 2026-11-25 | 4:50 | 6h5m | continuous | Track & Rail | T | [9 empty] | Total closure |  |  |  | 2025-12-15 | [7 empty] | publication
0055 |  | Szentgál - Városlőd-Kislőd |  | Szentgál | Városlőd-Kislőd | 2026 | 2026 | 1 | 22 | 2026-01-01 |  | 2026-05-28 |  |  |  | Bridge | [10 empty] | bridge insulation, embankment construction
0055 |  | Csorna állomás |  | Csorna | Csorna | 2026 | 2026 | 16 | 16 | 2026-04-13 |  | 2026-04-18 |  |  |  | Maintenance | [10 empty] | VVF maintanance
0055 |  | Ajka-Devecser |  | Ajka | Devecser | 2026 | 2026 | 16 | 18 | 2026-04-18 |  | 2026-04-27 |  |  |  | other | [10 empty] | ballast screening, construction of level crossing
0055 |  | Győr-Csorna |  | Győr | Csorna | 2026 | 2026 | 17 | 17 | 2026-04-20 |  | 2026-04-24 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Csorna-Sopron |  | Csorna | Sopron | 2026 | 2026 | 20 | 20 | 2026-05-11 |  | 2026-05-15 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Porpác-Csorna |  | Porpác | Csorna | 2026 | 2026 | 21 | 21 | 2026-05-18 |  | 2026-05-21 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Szombathely-Zalaszentiván |  | Szombathely | Zalaszentiván | 2026 | 2026 | 22 | 22 | 2026-05-26 |  | 2026-05-31 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Szombathely pályaudvar |  | Szombathely | Szombathely | 2026 | 2026 | 22 | 22 | 2026-05-27 |  | 2026-05-31 |  |  |  | Maintenance | [10 empty] | replacement of turnout number 59
0055 |  | Pápa-Celldömölk |  | Pápa | Celldömölk | 2026 | 2026 | 23 | 23 | 2026-06-01 |  | 2026-06-07 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Sopron(bez)-Lövő (Harka) |  | Sopron(bez) | Lövő | 2026 | 2026 | 29 | 29 | 2026-07-17 |  | 2026-07-20 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Sopron (bez) - Ágfalva Oh. |  | Sopron(bez) | Ágfalva | 2026 | 2026 | 32 | 33 | 2026-08-03 |  | 2026-08-16 |  |  |  | Bridge | [10 empty] | bridge insulation, construction of level crossing
0055 |  | Murakeresztúr |  | Murakeresztúr | Murakeresztúr | 2026 | 2026 | 33 | 35 | 2026-08-17 |  | 2026-08-28 |  |  |  | Bridge | [10 empty] | bridge maintanance
0055 |  | Porpác-Csorna |  | Porpác | Csorna | 2026 | 2026 | 35 | 37 | 2026-08-25 |  | 2026-09-10 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Győr-Csorna |  | Győr | Csorna | 2026 | 2026 | 37 | 39 | 2026-09-11 |  | 2026-09-22 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Szombathely-Bük |  | Szombathely | Bük | 2026 | 2026 | 38 | 38 | 2026-09-14 |  | 2026-09-17 |  |  |  | Catenary | [10 empty] | catenary, maintanance
0055 |  | Újudvar-Nagykanizsa |  | Újudvar | Nagykanizsa | 2026 | 2026 | 38 | 38 | 2026-09-16 |  | 2026-09-18 |  |  |  | other | [10 empty] | construction of level crossing
0055 |  | Bősárkány-Jánossomorja |  | Bősárkány | Jánossomorja | 2026 | 2026 | 43 | 43 | 2026-10-19 |  | 2026-10-20 |  |  |  | Rail | [10 empty] | rail replacement
0055 |  | Győrszabadhegy-Pápa |  | Győrszabadhely | Pápa | 2026 | 2026 | 44 | 44 | 2026-10-26 |  | 2026-10-30 |  |  |  | Maintenance | [10 empty] | maintenance
0055 |  | Csorna-Sopron |  | Csorna | Sopron | 2027 | 2027 | 14 | 17 | 2027-04-07 |  | 2027-04-30 |  |  |  | Rail | [10 empty] | rail replacement
0055 |  | Csorna-Porpác |  | Csorna | Porpác | 2027 | 2027 | 18 | 19 | 2027-05-03 |  | 2027-05-14 |  |  |  | Maintenance | [10 empty] | rail replacement, maintenance
0055 |  | Zalaszentiván-Zalaegerszeg |  | Zalaszentiván | Zalaegerszeg | 2027 | 2027 | 18 | 18 | 2027-05-03 |  | 2027-05-09 |  |  |  | Maintenance | [10 empty] | construction of level crossing
0055 |  | Zalaegerszeg-Andráshida |  | Zalaegerszeg | Andráshida | 2027 | 2027 | 18 | 18 | 2027-05-03 |  | 2027-05-09 |  |  |  | Maintenance | [10 empty] | construction of level crossing
0055 |  | Porpác-Vép |  | Porpác | Vép | 2027 | 2027 | 20 | 22 | 2027-05-19 |  | 2027-06-06 |  |  |  | Maintenance | [10 empty] | embankment construction
0055 |  | Ajka-Devecser-Tüskevár |  | Devecser | Devecser | 2027 | 2027 | 24 | 25 | 2027-06-14 |  | 2027-06-27 |  |  |  | Maintenance | [10 empty] | replacement of turnouts, ballast screening in open line sections
0055 |  | Győrszabadhegy-Pápa |  | Győrszabadhely | Pápa | 2027 | 2027 | 25 | 25 | 2027-06-21 |  | 2027-06-25 |  |  |  | Maintenance | [10 empty] | rail replacement, maintenance
0055 |  | Hajmáskér-Veszprém-Herend |  | Hajmáskér | Herend | 2027 | 2027 | 26 | 26 | 2027-06-28 |  | 2027-07-02 |  |  |  | Rail | [10 empty] | rail replacement
0055 |  | Püspökmolnári-Vasvár |  | Püspökmolnári | Vasvár | 2027 | 2027 | 28 | 33 | 2027-07-12 |  | 2027-08-18 |  |  |  | Bridge | [10 empty] | replacement of bridge structure
0055 |  | Celldömölk-Tokorcs-Ostffyasszonyfa |  | Celldömölk | Ostffyasszonyfa | 2027 | 2027 | 34 | 34 | 2027-08-23 |  | 2027-08-27 |  |  |  | Rail | [10 empty] | rail replacement, construction of level crossing
0055 |  | Bősárkány-Jánossomorja |  | Bősárkány | Jánossomorja | 2027 | 2027 | 36 | 37 | 2027-09-06 |  | 2027-09-19 |  |  |  | Rail | [10 empty] | rail replacement (if not implemented in 2026)
0055 |  | Győr-Csorna |  | Győr | Csorna | 2027 | 2027 | 38 | 39 | 2027-09-20 |  | 2027-10-02 |  |  |  | Maintenance | [10 empty] | rail replacement, maintenance
0055 |  | Pápa-Celldömölk |  | Pápa | Celldömölk | 2027 | 2027 | 40 | 41 | 2027-10-03 |  | 2027-10-14 |  |  |  | Maintenance | [10 empty] | bridge reconstruction, rail replacement, maintenance, etc.
0079 | 7906 | Koper - Ljubljana | < > | Verd | Logatec | 2025 | 2025 | 42 | 50 | 2025-10-13 | 7:00 | 2025-12-10 | 14:00 | 58days 7h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7907 | Zidani Most - Dobova | < > | Sevnica | Sevnica | 2026 | 2026 | 25 | 53 | 2026-06-19 | 10:00 | 2026-12-31 | 19:00 | 195days 7h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7908 | Ljubljana - Celje | < > | Zagorje | Sava | 2026 | 2026 | 49 | 50 | 2026-12-04 | 11:00 | 2026-12-13 | 20:00 | 9days 9h | continuous | Track & Rail |  | ST | [8 empty] | maintenance |  | N |  | 2025-12-05
0079 | 7909 | Ljubljana - Celje | < > | Sava | Litija | 2026 | 2026 | 18 | 22 | 2026-05-04 | 7:00 | 2026-05-31 | 15:00 | 27days 8h | continuous | Track & Rail |  | ST | [8 empty] | maintenance |  | N |  | 2025-12-05
0079 | 7910 | Koper - Ljubljana | < > | Borovnica | Verd | 2026 | 2026 | 27 | 38 | 2026-07-01 | 7:00 | 2026-09-15 | 19:00 | 76days 12h | continuous | Track & Rail |  | ST |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7911 | Koper - Ljubljana | < > | Borovnica | Verd | 2026 | 2026 | 38 | 50 | 2026-09-16 | 7:00 | 2026-12-10 | 19:00 | 85days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7912 | Koper - Ljubljana | < > | Brezovica | Preserje | 2026 | 2026 | 15 | 19 | 2026-04-01 | 7:00 | 2026-05-10 | 19:00 | 39days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7913 | Koper - Ljubljana | < > | Brezovica | Brezovica | 2026 | 2026 | 2 | 27 | 2026-01-10 | 7:00 | 2026-06-29 | 19:00 | 170days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7914 | Koper - Ljubljana | < > | Preserje | Preserje | 2026 | 2026 | 2 | 26 | 2026-01-11 | 7:00 | 2026-06-25 | 19:00 | 165days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7915 | Koper - Ljubljana | < > | Divača | Koper | 2026 | 2026 | 2 10 18 33 | 2 10 18 33 | 7.2.2026, 7.3.2026, 1.5.2026, 15.8.2026 | 7:00 | 8.2.2026, 8.3.2026, 3.5.2026, 17.8.2026 | 19:00 | 1day 12h, 1day 12h, 2days 12h, 2 days 12 h | continuous | Track & Rail | T | [9 empty] | maintenance |  | N |  | 2025-12-05
0079 | 7922 | Koper - Ljubljana | < > | Divača | Koper | 2026 | 2026 | 32 | 34 | 2026-08-06 | 15:00 | 2026-08-17 | 19:00 | 11days 4h | continuous | Track & Rail | T | [9 empty] | maintenance |  | N |  | 2025-12-05
0079 | 7916 | Koper-Ljubljana | < > | Ljubljana | Ljubljana | 2023 | 2026 | 46 | 40 | 2024-11-10 | 7:00 | 2027-10-02 | 19:00 | 1056 days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7923 | Ljubljana - Jesenice | < > | Jesenice | Jesenice | 2026 | 2026 | 6 | 39 | 2026-02-06 | 7:00 | 2027-09-27 | 19:00 | 598days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7918 | Ljubljana - Jesenice | < > | Ljubljana Šiška | Kranj | 2026 | 2026 | 39 | 41 | 2026-09-25 | 7:00 | 2026-10-11 | 19:00 | 16days 12h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7919 | Ljubljana - Jesenice | < > | Ljubljana Šiška | Vižmarje | 2026 | 2026 | 6 | 6 | 2026-02-06 | 23:00 | 2026-02-09 | 4:00 | 2days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7920 | Ljubljana - Jesenice | < > | Ljubljana Šiška | Vižmarje | 2026 | 2026 | 10 | 10 | 2026-03-06 | 23:00 | 2026-03-09 | 4:00 | 2days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7921 | Ljubljana - Jesenice | < > | Ljubljana Šiška | Vižmarje | 2026 | 2026 | 12 | 13 | 2026-03-20 | 23:00 | 2026-03-23 | 4:00 | 2days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7919 | Ljubljana - Jesenice | < > | Lesce Bled | Jesenice d.m. | 2027 | 2027 | 12 | 12 | 2027-03-19 | 23:00 | 2027-03-22 | 4:00 | 2days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7920 | Ljubljana - Jesenice | < > | Lesce Bled | Jesenice d.m. | 2027 | 2027 | 16 | 18 | 2027-04-16 | 23:00 | 2027-04-28 | 4:00 | 12days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7921 | Ljubljana - Jesenice | < > | Lesce Bled | Jesenice d.m. | 2027 | 2027 | 38 | 38 | 2027-09-17 | 23:00 | 2027-09-20 | 4:00 | 2days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7922 | Ljubljana - Jesenice | < > | Lesce Bled | Jesenice d.m. | 2027 | 2027 | 39 | 39 | 2027-09-24 | 23:00 | 2027-09-27 | 4:00 | 2days 5h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7924 | Zidani Most - Dobova | < > | Krško | Krško | 2027 | 2027 | 4 | 38 | 2027-01-25 | 7:00 | 2027-09-20 | 19:00 | 238days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7925 | Zidani Most - Dobova | < > | Sevnica | Sevnica | 2027 | 2027 | 42 | 5 | 2027-10-18 | 8:00 | 2028-01-30 | 20:00 | 104days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-06
0079 | 7910 | Koper - Ljubljana | < > | Borovnica | Verd | 2027 | 2027 | 27 | 40 | 2027-07-01 | 7:00 | 2027-09-30 | 19:00 | 91days 12h | continuous | Track & Rail |  | ST |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7911 | Koper - Ljubljana | < > | Borovnica | Verd | 2027 | 2027 | 40 | 50 | 2027-10-01 | 7:00 | 2027-12-11 | 19:00 | 71days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7912 | Koper - Ljubljana | < > | Preserje | Borovnica | 2027 | 2027 | 51 | 5 | 2026-12-16 | 7:00 | 2027-01-24 | 19:00 | 39days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7913 | Koper - Ljubljana | < > | Ljubljana | Preserje | 2026 | 2026 | 51 | 5 | 2026-02-06 | 23:00 | 2026-02-09 | 4:00 | 2days 5h | continuous | Track & Rail | T |  |  |  |  | C |  | B |  |  | Station renewal |  | N |  | 2025-12-06
0079 | 7914 | Koper - Ljubljana | < > | Ljubljana | Preserje | 2026 | 2026 | 51 | 5 | 2026-03-06 | 23:00 | 2026-03-09 | 4:00 | 2days 5h | continuous | Track & Rail | T |  |  |  |  | C |  | B |  |  | Station renewal |  | N |  | 2025-12-07
0079 | 7915 | Koper - Ljubljana | < > | Ljubljana | Preserje | 2026 | 2026 | 51 | 5 | 2026-04-03 | 23:00 | 2026-04-06 | 4:00 | 2days 5h | continuous | Track & Rail | T |  |  |  |  | C |  | B |  |  | Station renewal |  | N |  | 2025-12-08
0078 |  | DG - S. Marof - Zagreb Gk | < > | S. Marof | Zaprešić | june 2026 | december 2026 | [7 empty] | periodically | Bridge |  | LT | S |  |  |  | R |  | Y |  | Reconstruction of the bridge in km 422+224.80 (Lužnica). 48 hours closure of the line during installation of the load bearing reinforced concrete span structure. | 78
0078 |  | Zagreb Gk - Dugo Selo | < > | Sesvete | Dugo Selo | november 2024 | june 2026 | [7 empty] | periodically | Station |  | LT | S |  |  |  | R |  | Y |  | Construction of railway stop Sesvetska Sela . For the construction of the underpass are planned closures in the intervals from 48 to 72 hours depending on the technology. | 78
0078 |  | Zagreb Gk - Dugo Selo | < > | Sesvete | Sesvete | october 2025 | december 2027 | [7 empty] | periodically | Switch |  | ST | S |  |  |  | R |  | Y |  | Replacement of the existing switches in Sesvete railway. The planned track closures for the replacement of switches are on weekends, Friday - Monday, lasting approximately 52 hours (starting on Friday after the last train until Monday before the first train) | 78
0078 |  | DG - Botovo - Dugo Selo | < > | Dugo Selo | Vrbovec | december 2019 | december 2026 | [7 empty] | periodically | Track | T |  | S |  |  |  | R |  | Y |  | Reconstruction of existing and construction of a second track. 8 hours day closures every working day (Monday - Saturday) from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the sections Dugo Selo- Sesvete, Dugo Selo - Ivanić Grad (8 hours closures from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours). | 78
0078 |  | DG - Botovo - Dugo Selo | < > | Križevci | Koprivnica | june 2020 | december 2026 | [7 empty] | periodically | Track | T |  | S |  |  |  | R |  | Y |  | Reconstruction of existing and construction of a second track. Works on the track. Daily closures (Monday- Saturday) of the line (8 hours closure in intervals from 6:00 am to 4:00 pm) and occasional closures at weekends for up to 72 hours. Possible closures on the section Koprivnica-Rasinja and Koprivnica-Bregi (8 hours closure in intervals from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours). | 78
0078 |  | DG - Botovo - Dugo Selo | < > | Koprivnica | State border | june 2020 | december 2026 | [7 empty] | periodically | Track | T |  | S |  |  |  | R |  | Y |  | Reconstruction of existing and construction of a second track. Works on the route will be performed. Daily closures (Monday- Saturday) of the line (8 hours closure in intervals from 6:00 am to 4:00 pm) and occasional closures for up to 72 hours. Possible closures on the section Koprivnica-Rasinja and Koprivnica-Bregi (8 hours closure in intervals from 7:00 am to 4:00 pm and occasional closures for up to 72 hours). | 78
0078 |  | DG - Botovo - Dugo Selo | < > | Dugo Selo | Križevci | january 2027 | december 2027 | [7 empty] | periodically | Track |  | LT | S |  |  |  | R |  | Y |  | One track closure (today of existing) on the sections Dugo Selo - Vrbovec, Vrbovec - Gradec, Gradec - Križevci at intervals of 36 hours . | 78
0078 |  | Zagreb Gk - Rijeka | < > | Jastrebarsko | Karlovac | november 2022 | november 2028 | [7 empty] | periodically | Track | T |  | S |  |  |  | R |  | Y |  | Reconstruction of existing and construction of a second track. Daily closures (Monday-Sunday) of the line (8 hours closure in interval from 7:00 am to 4:00 pm), occasional closures at weekends for up to 72 hours according to the needs of contractors, if needed, possible closures longer than 72 hours. Possible closures on the sections Karlovac- Kamanje and Karlovac-Mrzlo Polje (8 hours closure in interval from 7:00 am to 4:00 pm) | 78
0078 |  | Zagreb Gk - Rijeka | < > | Hrvatski Leskovac | Jastrebarsko | november 2022 | november 2028 | [7 empty] | periodically | Track | T |  | S |  |  |  | R |  | Y |  | Reconstruction of existing and construction of a second track. Daily closures (Monday-Sunday) of the line (8 hours closure in interval from 7:00 to 4:00 pm), occasional closures at weekends for up to 72 hours according to the needs of contractors, if needed, possible closures longer than 72 hours. Possible closures on the section Zagreb Delta- Hrvatski Leskovac (8 hours closure in interval from 7:00 am to 4:00 pm). | 78
0078 |  | Zagreb Gk - Rijeka | < > | Ogulin | Moravice | february 2023 | june 2026 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Works on substructure of the track. 3 weekend closures lasting up to 36 hours; periodical daily closures for 6 to 8 hours (Monday, Tuesday, Wednesday, Thursday, Friday) | 78
0078 |  | Zagreb Gk - Rijeka | < > | Zalesina | Delnice | october 2026 | august 2027 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Change of the culvert in km 588+327 and km 588+601. Daily track closures lasting min. 8 hours. | 78
0078 |  | Zagreb Gk - Rijeka | < > | Zalesina | Delnice | january 2027 | december 2027 | [7 empty] | periodically | Tunnel | T |  | S |  |  |  | R |  | Y |  | Rehabilitation of the tunnel Sušica.Daily track closures lasting min. 8 hours. | 78
0078 |  | Zagreb Gk - Rijeka | < > | Zalesina | Delnice | april 2027 | october 2027 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Replacement of the rail track, mechanical replacement of the sleepers, mechanical track regulation, machine planning of the ballast bed, unloading of the crushed stone. Work of the cutter. 3 to 4 hours for several days track closures, during daylight . | 78
0078 |  | Zagreb Gk - Rijeka | < > | Lokve - Fužine - Drivenik - Plase |  | may 2025 | october 2026 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Rehabilitation of the tunnel Sljeme, Kobiljak . 8 hours without interruption, five to six days a week . | 78
0078 |  | Zagreb Gk - Rijeka | < > | Lokve | Drivenik | april 2027 | october 2027 | [7 empty] | periodically | Miscellaneous | T |  | S |  |  |  | R |  | Y |  | * Rehabilitation of 10 railway cuts * Replacement of the rail track, mechanical replacement of the sleepers, mechanical track regulation, machine planning of the ballast bed, unloading of the crushed stone * Strengthening of the embankment Hreljin 2, 3, Vučnik, near the barrack, work of the cutter, rehabilitation of windbreak exit Meja I. 3 to 4 hours for several days track closures, during daylight . | 78
0078 |  | Zagreb Gk - Rijeka | < > | Sušak Pećine | Rijeka | march 2026 | july 2026 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Anti-corrosive protection of the trussed bridge Rječina. 4 to 6 hours without interruption, five days a week during daylight. | 78
0078 |  | Zagreb Gk - Rijeka | < > | Škrljevo | Rijeka | april 2027 | december 2027 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Replacement of the rail track, mechanical replacement of the sleepers, mechanical track regulation, machine planning of the ballast bed, unloading of the crushed. 3 to 4 hours for several days track closures, during daylight . | 78
0078 |  | Zagreb Gk - Rijeka | < > | Drivenik | Škrljevo | september 2027 | december 2028 | [7 empty] | periodically | Track | T |  | S |  |  |  | R |  | Y |  | Renewal of the line section (25 km).Monday - Friday: 8 to 10 hours daily closures of the line. As needed and according to possibilities closures of the line at weekends for 36 hours. | 78
0078 |  | Zagreb Gk - Rijeka | < > | Karlovac - Mrzlo Polje - Zvečaj |  | january 2027 | december 2027 | [7 empty] | periodically | Maintenance | T |  | S |  |  |  | R |  | Y |  | Regular maintenance works. Monday - Sunday: 8 to 10 hours daily closures of the line. As needed and according to possibilities closures of the line at weekends for 36 hours. | 78
0078 |  | Sava - Zagreb Klara | < > | Sava | Zagreb Klara | december 2024 | december 2027 | [7 empty] | periodically | Switch |  | ST | S |  |  |  | R |  | Y |  | Replacement of the switches in Zagreb RK railway station. Permanent 72-hour track closures of individual tracks with the possibility of using detours within the station . | 78
0078 |  | Oštarije - Knin - Split / Ogulin Krpelj | < > | Oštarije - Knin - Split |  | november 2025 | december 2027 | [7 empty] | periodically | Track | T |  | S | [5 empty] | Y |  | Modernisation and renewal of the line - works on reconstruction of stations and tracks, replacement of switches and rehabilitation of level crossing safety devices. Daily closures from 6 to 8 hours (from Monday to Sunday) and if necessary and depending on the complexity of the construction process, permanent line closures at weekends lasting for 36 hours | 78
0078 |  | Oštarije - Knin - Split / Ogulin Krpelj | < > | Oštarije - Gospić - Knin |  | september 2024 | june 2026 | [7 empty] | periodically | Tunnel | T |  | S | [5 empty] | Y |  | Rehabilitation of the tunnels Grabež and Ćulum. 8-hour closures are expected during the visible part of the day. | 78
83 | RFI-2025-25 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2024 | 2025 | 50 | 50 | 2024-12-15 | 23:00 | 2025-12-13 | 4:00 | 300' | periodical continuous | Others | T | [7 empty] | 60 |  | From Mo/Tu to Sun/Mo - late trains for the direction North-South at Tarvisio station for activities of others Ims must arrive to Trieste Campo Marzio before the 11:00 p.m. in order to respect this important works (ePIR ID 181_2025) | 79,80,81 | Y |  | 2023-07-11 | Minor |  | Tra 10% e 30%
83 | RFI-2025-02 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2024 | 2025 | 50 | 50 | 2024-12-15 | 0:00 | 2025-12-13 | 4:00 | 240' - 300' | periodical | Others | T | ST | [6 empty] | 120 |  | total closure of 240' ' Fri/Sat to Tue/Wed; station renewal (ePIR ID 182_2025) | 79 | Y |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2025-01 | Udine - Treviso | < > | Udine | Basiliano | 2024 | 2025 | 50 | 50 | 2024-12-15 | 0:00 | 2025-12-13 | 4:00 | 240' | periodical | Others | T | [5 empty] | R |  | 60 |  | single track Mon/Tue to Fri/Sat total closure of 240' Mon/Tue to Fri/Sat LDP, LDF re-routing via Gorizia | 80, 81 | Y |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2025-08 | Villach - Udine | < > | Tarvisio | Carnia | 2024 | 2025 | 50 | 50 | 2024-12-15 | 8:00 | 2025-12-13 | 11:00 | 180' | periodical continuous | Track & Rail | T |  | S | [5 empty] | 30 |  | single closure of 240' + total closure of 180' Mon - Fri; LDP, LDF pre/post timetable | 80, 81 | Y |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2024-14 | Villach - Udine | < > | Carnia | Gemona del Friuli | 2024 | 2025 | 50 | 50 | 2024-12-15 | 7:30 | 2025-12-13 | 12:30 | 25x240' | periodical | Track & Rail |  | LT | S | [5 empty] | 120 |  | From Monday to Friday in daytime with interruption of the adjacent track for 270' | 80, 81 | N |  | 2024-07-15 | Minor |  | Tra 10% e 30%
83 | RFI-VE-25-31 | Bologna - Padova | < > | Occhiobello | Monselice | 2024 | 2025 | 50 | 50 | 2024-12-15 |  | 2025-12-13 |  | 345x270' | periodical | Others | T | [9 empty] | with track closure of 300' - works for ACC-M |  |  |  | 2024-07-15 | Minor |  | <10%
83 | RFI-BO-25-01 | Bologna - Padova | < > | Castelmaggiore | Occhiobello | 2024 | 2025 | 50 | 50 | 2024-12-15 |  | 2025-12-13 |  | 345x270' | periodical | Others | T | [9 empty] | with track closure of 300' - works for ACC-M |  |  |  | 2024-07-15 | Minor |  | <10%
83 | RFI-VE-25-32 | Bologna - Padova | < > | Polesella | Polesella | 2024 | 2025 | 50 | 50 | 2025-01-07 |  | 2025-09-30 |  | 190x270' | periodical | Others |  | ST | S | [7 empty] | with track closure of 300' - works for PRG of Polesella (ID ePIR VE-25-32 e VE-25-33) |  |  |  | 2024-07-15 | Minor |  | <10%
83 | RFI-2025-42 | Udine - Treviso | < | Gemona del Friuli | Gemona del Friuli | 2025 | 2025 | 2 | 52 | 2025-01-08 | 07.30 | 31/12/2025 | 12.30 | 35 x 240' | periodical continuous | Switch |  |  | S | [5 empty] | 120 |  | 240' of track closure LDP, LDF (ePIR ID TS-25-02) | 80, 81 | N |  | 2023-12-14 | Minor |  | Tra 10% e 30%
83 | RFI-2025-40 | Milano - Venezia | < > | Venezia Marghera Scalo | Venezia Marghera Scalo | 2025 | 2025 | 19 | 44 | 2025-05-05 |  | 2025-10-31 |  | 240'/300' | periodical continuous | Others | [10 empty] | Upgrade station - phase 1 (ePIR VE-25-22) |  | N |  | 2024-07-15 | Minor |  | <10%
83 | RFI-TS-25-03 | Villach - Udine | < | Udine | Udine | 2025 | 2025 | 19 | 46 | 2025-05-10 |  | 2025-11-12 |  | 185 days | continuous | Others |  | ST | [8 empty] | track interruptions for phases for station renewal (ePIR ID TS-25-03) |  |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-2025-13 | Villach - Udine | < > | Carnia | Pontebba | 2025 | 2025 | 22 | 36 | 2025-05-30 | 8:00 | 2025-08-11 | 11:00 | 70 days (35 days even tracks and 35 days odd tracks) | continuous | Track & Rail |  |  | S | [5 empty] | 60 |  | 70 days track interruption part of traffic (ca. 15-20 trains per day) has to be re-routed via Brennero (ePIR ID 179_2025) | 80, 81 |  |  | 2023-12-14 | Major |  | >50%
83 | RFI-2025-14 | Villach - Udine | < > | Carnia | Ugovizza V. | 2025 | 2025 | 22 | 36 | 2025-05-30 | 8:00 | 2025-08-11 | 12:00 | 70 x 240´ | periodical | Track & Rail | T |  | S | [7 empty] | IPA track renewal (ePIR ID 179_2025) | 80, 81 |  |  | 2024-07-15 | Minor |  | Tra 10% e 30%
83 | RFI-2025-67 | Padova - Castelfranco | < > | Vigodarzere | Vigodarzere | 2025 | 2026 | 22 | 5 | 2025-06-01 |  | 2026-01-31 |  | 82x330' | periodical continuous | Bridge | T | [9 empty] | Line closure of 240' - (ePIR ID 175_2025) |  | N |  | 2024-07-15 | Minor |  | <10%
83 | RFI-TS-25-15 | Udine - Trieste | < > | Cormons | Gorizia C.le | 2025 | 2025 | 31 | 50 | 2025-08-01 |  | 2025-12-13 |  | 60x240' | periodical | Others | T | [9 empty] | with track closure of 370' - works for the new stop Mossa |  |  |  | 2024-07-15 | Minor |  | Tra 10% e 30%
83 | RFI-2025-56 | Venezia - Trieste | < > | Bivio D'Aurisina | Bivio D'Aurisina | 2025 | 2025 | 33 | 33 | 2025-08-14 |  | 2025-08-17 |  | 1 x 30 h | continuous | Track & Rail | T | [9 empty] | Bv. Viadotto (ePIR ID TS-25-21) | 79 | N |  | 2023-12-14 | Medium |  | >50%
83 | RFI-2025-24 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2025 | 2025 | 33 | 33 | 2025-08-14 | 0:00 | 2025-08-17 | 23:59 | 1 x 72h | continuous | Others | T |  |  |  |  | C |  |  |  |  | PRG & ACC - 1 total closure 72 h (ePIR ID TS-25-18) | 79,80,81 | N |  | 2023-07-11 | Medium |  | >50%
83 | RFI-2025-54 | Villach - Udine | < > | Udine Parco | Udine Parco | 2025 | 2025 | 36 | 40 | 2025-09-01 |  | 2025-10-03 |  | 15 x 270' | periodical continuous | Track & Rail | T | [9 empty] | 270' of total closure with 300' of track closure - Bv. Pradamano (ePIR ID 187_2025) | 79, 80, 81 | N |  | 2023-12-14 | Minor |  | Tra 10% e 30%
83 | RFI-TS-25-12 | Villach - Udine | < | Tarcento | PM Vat | 2025 | 2025 | 36 | 46 | 2025-09-01 |  | 2025-11-14 |  | 42x270' | periodical | Track & Rail | T |  | S | [7 empty] | track renewal, times are still to be specified | 80, 81 |  |  | 2024-07-15 | Minor |  | Tra 10% e 30%
83 | RFI-BO-25-24 | Castelbolognese - Ravenna | < > | Russi | Ravenna | 2025 | 2025 | 36 | 50 | 2025-09-01 |  | 2025-12-14 |  | 75x330-360' | periodical | Track & Rail | T |  | S | [7 empty] | nocturnal line interruptions of 300-360' |  |  |  | 2024-07-15 | Minor |  | Tra 30% e 50%
83 | RFI-BO-25-25 | Faenza - Ravenna | < > | Russi | Ravenna | 2025 | 2025 | 36 | 50 | 2025-09-01 |  | 2025-12-14 |  | 75x330-360' | periodical | Track & Rail | T |  | S | [7 empty] | nocturnal line interruptions of 300-360' |  |  |  | 2024-07-15 | Minor |  | Tra 30% e 50%
83 | RFI-2025-17b | Brennero - Verona | < > | Verona Quadrante Europa | Verona Quadrante Europa | 2025 | 2025 | 36 | 42 | 2025-09-01 |  | 2025-10-15 |  | 45 days of interruption of some track | continuous | Others | [5 empty] | C |  |  | Y |  | with nocturnal disalimentation (ePIR_VR-25-24) | 80, 81 | N |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-TS-25-25 | Venezia - Trieste | < | Cervignano Sm. | Cervignano Sm. | 2025 | 2025 | 37 | 43 | 2025-09-08 |  | 2025-10-25 |  | 35x300' | periodical | Switch |  | ST | S | [7 empty] | track interruption for switch renewal |  |  |  | 2024-07-15 | Minor |  | Tra 10% e 30%
83 | RFI-2025-70 | Aurisina - Villa Opicina | < > | Aurisina | Villa Opicina | 2025 | 2025 | 43 | 50 | 2025-10-26 |  | 2025-12-14 |  | 50x 240'-300' | periodical continuous | Others | T | [9 empty] | PRG + ACC Villa Opicina (ePIR ID 97_2025) | 79 | N |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2025-77 | Villach - Udine | < > | Udine | Udine Parco | 2025 | 2025 | 44 | 50 | 2025-11-01 |  | 2025-12-13 |  | 20X270' | periodical | Others | T | LT | [8 empty] | ACC Udine - fase 0: From Monday to Friday (ePIR ID TS-25-14) | 81 | N |  | 2024-07-15 | Medium |  | >50%
83 | RFI-2025-15 | Villach - Udine | < > | Carnia | Ugovizza | 2025 | 2025 | 45 | 49 | 2025-11-07 | 8:00 | 2025-12-01 | 11:00 | 2 x 52 hours | periodical continuous | Track & Rail |  | LT | S | [5 empty] | 120 |  | 2 weekends; LDP, LDF (ePIR ID TS-25-13) | 80, 81 | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2025-16 | Villach - Udine | < > | Carnia | Ugovizza | 2025 | 2025 | 45 | 49 | 2025-11-07 | 8:00 | 2025-12-01 | 11:00 | 10 x 180' | periodical continuous | Track & Rail | T |  | S | [5 empty] | 40 |  | 2 x weekends Sa/Sun/Mon; LDP, LDF (ePIR ID TS-25-13) | 80, 81 | N |  | 2025-08-01 | Minor |  | <10%
83 | RFI-2025-50 | Ferrara - Rimini | < > | Portomaggiore | Argenta | 2025 | 2025 | 47 | 48 | 2025-11-20 |  | 2025-11-24 |  | 1x77h | continuous | Bridge | T | [9 empty] | line interruption of 48h (ePIR ID BO-25-26) |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2025-62 | Milano - Venezia | < > | Venezia Mestre | Venezia Mestre | 2025 | 2026 | 50 | 24 | 01/11/2026 |  | 12/12/2026 |  | Station tracks interruption with different phases | continuous | Bridge |  | ST | [8 empty] | Station tracks interruption with different phases and different duration for each phases. This TCR impact only the passenger trains (regional and long distance trains also international trains) (ePIR ID VE-25-25) | 79, 81 | N |  | 2026-04-29 | Minor |  | Tra 30% e 50%
83 | RFI-VE-26-27 | Venezia - Trieste | < > | Venezia Mestre | Portogruaro | 2025 | 2026 | 50 | 50 | 2025-12-14 |  | 2026-12-12 |  | 7x360'-390' | periodical | Others | T | [9 empty] | Line upgrading (VE-26-27) |  |  |  | 2025-08-01
83 | RFI-2026-02 | Udine - Treviso | < > | Udine | Basiliano | 2025 | 2026 | 50 | 50 | 2025-12-14 | 0:00 | 2026-12-12 | 4:00 | 240' | periodical | Others | T | [5 empty] | R |  | 60 |  | IPO: single track Mon/Tue to Fri/Sat total closure of 240' Mon/Tue to Fri/Sat LDP, LDF re-routing via Gorizia | 80, 81 | Y |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2026-03 | Villach - Udine | < > | Tarvisio | Carnia | 2025 | 2026 | 50 | 50 | 2025-12-14 | 8:00 | 2026-12-12 | 11:00 | 180' | periodical continuous | Track & Rail | T |  | S | [5 empty] | 30 |  | IPO: single closure of 240' + total closure of 180' Mon - Fri; LDP, LDF pre/post timetable | 80, 81 | Y |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2026-08 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2025 | 2026 | 50 | 31 | 2025-12-14 | 0:00 | 2026-08-01 | 4:00 | 170x270' | periodical | Others | T | [9 empty] | UPGRADING LINEA VILLA OPICINA - BIVIO D AURISINA (ePIR_ID 92_2026) | 79, 81 | N |  | 2024-12-20 | Minor |  | <10%
83 | RFI-2026-12 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2025 | 2026 | 50 | 50 | 2025-12-14 | 23:00 | 2026-12-12 | 4:00 | 240' | periodical continuous | Others | T | [7 empty] | 60 |  | From Mo/Tu to Sun/Mo - late trains for the direction North-South at Tarvisio station for activities of others Ims must arrive to Trieste Campo Marzio before the 11:00 p.m. in order to respect this important works (PRG E ACC TRIESTE CAMPO MARZIO ePIR_ID 94_2026) | 79, 81 | Y |  | 2024-12-20 | Minor |  | <10%
83 | RFI-TS-26-18 | Villach - Udine | < | Udine | Udine | 2025 | 2026 | 50 | 50 | 2025-12-14 |  | 03/07/2026 |  | immobilisation of a switch | continuous | Others |  | LT | [8 empty] | impacts on trains to Basiliano and Bivio Cargnacco ACC Udine - fase 0 |  |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2026-20 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2025 | 2026 | 50 | 26 | 2025-12-14 |  | 2026-06-28 |  | 3x36h | continuous | Others | T | ST | [8 empty] | PRG E ACC VILLA OPICINA - ATTIVAZIONE FASE 2 (ePIR_ID TS-26-28) | 79, 81 | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2026-34 | Ljubljana - Udine | < > | Bivio Aurisina | Villa Opicina | 2025 | 2026 | 50 | 2 | 2025-12-15 |  | 2026-01-09 |  | 15x270' | periodical continuous | Others | T | [9 empty] | (ePIR_ID 95_2026) | 79 | N |  | 2023-12-14 | Minor |  | Tra 10% e 30%
83 | RFI-2025-76 | Bologna - Padova | < > | Ferrara | Ferrara | 2025 | 2025 | 51 | 51 | 2025-12-20 |  | 2025-12-21 |  | 12h | continuous | Others | T | [9 empty] | (ePIR ID BO-25-02) |  | N |  | 2025-08-01 | Minor |  | <10%
83 | RFI-2026-35 | Ljubljana - Udine | < > | Bivio Aurisina | Villa Opicina | 2025 | 2026 | 52 | 1 | 2025-12-27 |  | 2026-01-03 |  | 30h | continuous | Others | T | [9 empty] | Switch renewal at Bivio Galleria (ePIR_ID TS-26-21) | 79 | N |  | 2024-12-20 | Medium |  | >50%
83 | RFI-TS-26-04 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2025 | 2025 | 52 | 1 | 2025-12-28 |  | 2026-01-03 |  | 96h | continuous | Others | T | ST | [6 empty] | Y |  | PRG Trieste Campo Marzio - phase 4 | 81 | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-TS-26-16 | Venezia - Trieste | < | Cervignano Sm. | Cervignano Sm. | 2026 | 2026 | 1 | 44 | 2026-01-01 |  | 2026-10-30 |  | 240x240' | periodical | Others |  | ST | [8 empty] | ACC CERVIGNANO SMISTAMENTO FACIO ARRIVI E FASCIO ESTRAZIONI |  |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-2026-46 | Villach - Udine | < > | Ugovizza V. | Pontebba | 2026 | 2026 | 2 | 50 | 2026-01-08 |  | 2026-12-12 |  | 180x180' | periodical | Others | T | [9 empty] | GALLERIA SAN LEOPOLDO - POSA FO PER REALIZZAZIONE STES - with track closure of 240' |  |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2024-16 | Villach - Udine | < > | Tarvisio | Ugovizza V. | 2026 | 2026 | 2 | 50 | 2026-01-08 | 7:30 | 2026-12-12 | 12:30 | 240' | periodical | Track & Rail | T |  | S | [5 empty] | 120 |  | 300´ track closure in Mon - Fri LDP, LDF | 80, 81 | N |  | 2024-12-20 | Minor |  | <10%
83 | RFI-2026-17 | Venezia - Trieste | < > | Cervignano Sm. | Cervignano A.G. | 2026 | 2026 | 3 | 8 | 2026-01-12 |  | 2026-02-19 |  | 30x240' | periodical | Bridge | T |  | S | [7 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-26-22) | 79, 81 |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2026-18 | Venezia - Trieste | < > | Torviscosa | Cervignano A.G. | 2026 | 2026 | 3 | 8 | 2026-01-12 |  | 2026-02-19 |  | 30x240' | periodical | Bridge | T |  | S | [7 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-26-22) | 79, 81 |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-BO-26-98 | Ferrara - Rimini | < > | Ravenna | Ravenna | 2026 | 2026 | 9 | 9 | 2026-01-17 |  | 2026-01-18 |  | 55h | continuous | Switch |  | ST | [8 empty] | 55h interruption of the Candiano terminal for switch renewal on tracks 302, 303, 304, 305 E 307 |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2026-47 | Villach - Udine | < > | Udine | Pontebba | 2026 | 2026 | 5 | 14 | 2026-02-01 |  | 2026-03-31 |  | 40x240' | periodical | Track & Rail | T | [9 empty] | RINCALZATURA SISTEMATICA BINARI (ID TS-26-13) |  |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2026-05 | Villach - Udine | < > | Carnia | Pontebba | 2026 | 2026 | 8 | 14 | 2026-02-16 | 8:00 | 2026-03-30 | 11:00 | 56 x 180' | periodical continuous | Track & Rail | T |  | S | [5 empty] | 40 |  | Sa/Sun/Mon; LDP, LDF (ePIR ID TS-26-12) | 80, 81 | N |  | 2024-12-20 | Minor |  | <10%
83 | RFI-2026-21 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 8 | 8 | 2026-02-18 |  | 2026-02-19 |  | 6h | continuous | Others | T | [9 empty] | (ePIR_ID 94_2026) | 79, 81 | N |  | 2023-12-14 | Minor |  | <10%
83 | RFI-2026-13 | Venezia - Trieste | < > | Cervignano Sm. | Cervignano A.G. | 2026 | 2026 | 8 | 13 | 2026-02-19 |  | 2026-03-22 |  | 1 x 30 days | continuous | Bridge | T |  | S | [5 empty] | 120 |  | Maintenance of Cervignano viaduct (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Major |  | >50%
83 | RFI-2026-19 | Venezia - Trieste | < | Torviscosa | Cervignano A.G. | 2026 | 2026 | 8 | 13 | 2026-02-19 |  | 2026-03-22 |  | 30x240' | periodical continuous | Bridge | T |  | S | [5 empty] | 120 |  | Maintenance of Cervignano viaduct (ePIR ID TS-26-22) | 79, 81 |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-2026-04 | Villach - Udine | < > | Carnia | Pontebba | 2026 | 2026 | 9 | 13 | 2026-02-28 | 8:00 | 2026-03-23 | 11:00 | 2 x 52 hours | periodical continuous | Track & Rail |  | LT | S | [5 empty] | 120 |  | 2 weekends; LDP, LDF (ePIR ID TS-26-01) | 80, 81 | N |  | 2024-12-20 | Medium |  | >50%
83 | RFI-2025-43 | Villach - Udine | < > | Udine | Udine Parco | 2026 | 2026 | 12 | 12 | 2026-03-21 |  | 2026-03-22 |  | 24h Interruption of some Station tracks (simultaneously of Udine and Udine Parco) | continuous | Others |  | LT | [6 empty] | 120 |  | ACC Udine - fase 0: From Monday to Friday (ePIR ID TS-26-45) | 81 | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-VE-26-21 | Padova - Castelfranco | < > | Vigodarzere | Padova | 2026 | 2026 | 13 | 13 | 2026-03-23 |  | 2026-03-27 |  | 5 days | continuous | Bridge |  | LT | [8 empty] | doubling of the line on the Brenta bridge - even track closure |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2026-24 | Venezia - Trieste | < | Torviscosa | Cervignano A.G. | 2026 | 2026 | 13 | 19 | 2026-03-23 |  | 2026-05-10 |  | 45 days | continuous | Bridge |  | LT | [8 empty] | Even track interruption - FASE 2 (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Major |  | >50%
83 | RFI-2026-24b | Venezia - Trieste | < | Cervignano Sm. | Cervignano A.G. | 2026 | 2026 | 13 | 19 | 2026-03-23 |  | 2026-05-10 |  | 45 days | continuous | Bridge | T | [9 empty] | Even track interruption - FASE 2 (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Major |  | >50%
83 | RFI-2026-25 | Venezia - Trieste | > | Torviscosa | Cervignano A.G. | 2026 | 2026 | 13 | 19 | 2026-03-23 |  | 2026-05-10 |  | 45x240' | periodical continuous | Bridge |  | LT | [8 empty] | Even track interruption - FASE 2 (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-TS-26-19 | Udine - Trieste | < > | Cormons | Gorizia C.le | 2026 | 2026 | 16 | 20 | 2026-04-13 |  | 2026-05-11 |  | 25x270' | periodical | Track & Rail | T | [9 empty] | renewal of the even track |  |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2025-74 | Bologna - Padova | < > | S. Pietro in C. | Occhiobello | 2027 | 2027 | 16 | 16 | 01/06/2027 |  | 31/07/2027 |  | 24h | continuous | Others | T | [9 empty] | ACC-M (ePIR ID BO-25-04) |  | N |  | 2026-04-29 | Minor |  | Tra 10% e 30%
83 | RFI-2026-38 | Villach - Udine | < > | Carnia | Carnia | 2026 | 2026 | 18 | 28 | 2026-05-01 |  | 2026-07-10 |  | 35x270' | periodical continuous | Switch | T |  |  |  |  | C |  |  | Y |  | Carnia - rinnovo deviatoi (ePIR_ID 98_2026) | 81 | N |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2026-15 | Venezia - Trieste | < | Torviscosa | Cervignano A.G. | 2026 | 2026 | 19 | 24 | 2026-05-11 |  | 2026-06-12 |  | 30 days | continuous | Bridge |  | LT | [8 empty] | Odd track interruption - FASE 3 (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Major |  | >50%
83 | RFI-2026-26 | Venezia - Trieste | > | Torviscosa | Cervignano A.G. | 2026 | 2026 | 19 | 24 | 2026-05-11 |  | 2026-06-12 |  | 30x240' | periodical continuous | Bridge |  | LT | [8 empty] | Odd track interruption - FASE 3 (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-2026-27 | Venezia - Trieste | < > | Cervignano Sm. | Cervignano A.G. | 2026 | 2026 | 19 | 24 | 2026-05-11 |  | 2026-06-12 |  | 30x240' | periodical continuous | Bridge |  | LT | [8 empty] | Single track interruption - FASE 3 (ePIR ID TS-26-10) | 79, 81 |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-TS-26-43 | Venezia - Trieste | < > | Latisana | Portogruaro | 2026 | 2026 | 21 | 21 | 2026-05-18 |  | 2026-05-24 |  | 6 days | continuous | Track & Rail | T | LT | [8 empty] | Renewal of the metal girders on the Latisana Bridge, km 72 (TS-26-43) |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2025-49 | Venezia - Trieste | < > | Latisana | Quarto D'Altino | 2026 | 2026 | 21 | 47 | 2026-05-22 |  | 29/11/2026 |  | 2x48h | continuous | Track & Rail | T | LT | [8 empty] | 2 x 48 3x30 of line interruption (ePIR ID VE-26-26 + TS-26-23) |  | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-26-42 | Venezia - Trieste | < > | Ronchi dei Legionari sud | Cervignano | 2026 | 2026 | 21 | 47 | 2026-05-22 |  | 29/11/2026 |  | 30h | continuous | Track & Rail | T | LT | [8 empty] | 3x24h of line interruption (ePIR ID TS-26-42) - in shadow of ID RFI-2025-49 |  | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-2026-47 | Villach - Udine | < | Udine | Udine | 2026 | 2026 | 25 | 27 | 2026-06-15 |  | 2026-07-02 |  | 40x270' | periodical | Others |  | LT | [8 empty] | with track closure of 300' ACC Udine - fase 0 (TS-26-72) |  |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-2026-43 | Bologna - Padova | < > | S. Pietro in C. | Castelmaggiore | 2026 | 2026 | 24 | 24 | 2026-06-13 |  | 2026-06-14 |  | 20h | continuous | Others | T | [9 empty] | (ePIR_ID BO-26-14) |  | N |  | 2023-12-14 | Medium |  | >50%
83 | RFI-2025-43b | Villach - Udine | < > | Udine | Udine Parco | 2026 | 2026 | 25 | 25 | 17/10/2026 |  | 17/10/2026 |  | 36h Interruption of some Station tracks (simultaneously of Udine and Udine Parco) | continuous | Others |  | LT | [6 empty] | 120 |  | ACC Udine - fase 0: From Monday to Friday (ePIR ID TS-26-17) | 81 | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-26-11 | Villach - Udine | < > | Udine | Udine Parco | 2026 | 2026 | 27 | 28 | 14/11/2026 |  | 15/11/2026 |  | 48h | continuous | Others | T |  |  |  |  | C | R |  | Y |  | 48h total closure of Udine and Udine Parco stations: ACC di Udine fase 0 - Activation (ePIR ID TS-26-11) | 81 | N |  | 2024-12-20 | Medium |  | >50%
83 | RFI-2026-45 | Bologna - Padova | < > | Ferrara | Poggio Renatico | 2028 | 2028 | 27 | 28 | 2028 |  | 2028 |  | 48h | continuous | Others | T | [9 empty] | (ePIR_ID BO-26-15) |  | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-VE-26-34 | Bologna - Padova | < > | Padova Campo Marte | Monselice | 2026 | 2026 | 28 | 35 | 2026-07-06 |  | 23/08/2026 |  | 40x270' | periodical | Track & Rail | T | [9 empty] | except for the period of the Verona-Vicenza closure from 1 to 15 august. Track renewal - with track closure of 300' |  |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-TS-25-19 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2026 | 2026 | 9 | 17 | 2026-07-11 |  | 2026-07-12 |  | 12h | continuous | Others | T | [9 empty] | works on overpass to eliminate level crossing near Prosecco (TS-26-27) |  |  |  | 2025-08-01 | Medium |  | Tra 10% e 30%
83 | RFI-2025-72 | Bologna - Padova | < > | Rovigo | Occhiobello | 2028 | 2028 | 28 | 28 | 2028 |  | 2028 |  | 24h | continuous | Others | T | [9 empty] | ACC (ePIR ID VE-26-18) |  | N |  | 2026-04-29 | Minor |  | Tra 10% e 30%
83 | RFI-2026-42 | Bologna - Padova | < > | Rovigo | Occhiobello | 2028 | 2028 | 28 | 28 | 2028 |  | 2028 |  | 24h | continuous | Others | T | [9 empty] | ACC-M Activation (ePIR_ID VE-26-18) |  | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-26-20 | Villach - Udine | < | Udine | Udine | 2027 | 2027 | 29 | 37 | 04/01/2027 |  | 14/03/2027 |  | 50 days | continuous | Others |  | ST | [8 empty] | Interruption of 2 tracks in Udine station fo works on the elevators (TS-26-69) |  |  |  | 2026-04-29 | Major |  | Tra 30% e 50%
83 | RFI-VR-26-09 | Brennero - Verona | < | Verona Quadrante Europa | Verona Quadrante Europa | 2026 | 2026 | 29 | 33 | 2026-07-18 |  | 2026-08-31 |  | 45 days | continuous | Switch |  | ST |  |  |  | C | R |  | Y |  | Switch and track renewal - track interruptions for phases (VR-26-94 (ex VR-26-09)) interruption of III, IV, V FASCIO TERMINAL | 80 |  |  | 2025-08-01 | Minor |  | Tra 10% e 30%
83 | RFI-VE-26-35 | Bologna - Padova | < > | Padova Campo Marte | Monselice | 2026 | 2026 | 33 | 40 | 2026-08-10 |  | 2026-10-04 |  | 40x270' | periodical | Track & Rail | T | [9 empty] | Track renewal - with track closure of 300' |  |  |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-2026-22 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 33 | 34 | 2026-08-14 |  | 2026-08-19 |  | 96h | continuous | Others | T | [9 empty] | PRG e ACC Trieste CM (ePIR_ID TS-26-24) |  | N |  | 2025-08-01 | Minor |  | <10%
83 | RFI-2025-59 | Padova - Castelfranco | < > | Vigodarzere | Padova | 2026 | 2026 | 34 | 36 | 2026-08-20 |  | 2026-09-03 |  | 15 days | continuous | Bridge | T | [9 empty] | total closure for 15 days - Bridge over Brenta (ePIR ID VE-26-06) |  | N |  | 2024-07-15 | High |  | >50%
83 | RFI-2026-40 | Villach - Udine | < > | P.M. Vat | Tarcento | 2026 | 2026 | 34 | 38 | 2026-08-22 |  | 2026-09-20 |  | 300' | periodical continuous | Track & Rail | T | [9 empty] | Track closure of 300' (ePIR_ID 101_2026) | 81 | N |  | 2025-08-01 | Minor |  | <10%
83 | RFI-2026-01 | Villach - Udine | < > | Carnia | Tarvisio Boscoverde | 2026 | 2026 | 34 | 38 | 2026-08-22 |  | 2026-09-20 |  | 30 days | continuous | Others | T |  | S |  |  |  | R |  |  |  | Re-routed Brennero and Slovenia (ePIR_ID 102_2026) (ePIR_ID 103_2026) | 80, 81 |  |  | 2023-12-14 | Major |  | >50%
83 | RFI-2026-31 | Tarvisio - Venezia | < > | Treviso | Spresiano | 2026 | 2026 | 36 | 39 | 2026-09-01 |  | 2026-09-25 |  | 21x240' | periodical continuous | Others | T | [9 empty] | (ePIR_ID VE-26-07) SOSTITUZIONE SOTTOVIA KM 24+170 |  | N |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-BO-26-28 | Ferrara - Ravenna | < > | Lavezzola | Ravenna | 2026 | 2026 | 39 | 40 | 2026-09-26 |  | 2026-09-27 |  | 48h 55h | continuous | Bridge | T | [9 empty] | maintenance works on a bridge KM 56+014 |  |  |  | 2024-12-20 | Medium |  | >50%
83 | RFI-2026-39 | Villach - Udine | < > | Gemona del Friuli | Gemona del Friuli | 2026 | 2026 | 40 | 48 | 2026-09-28 |  | 2026-11-27 |  | 40x270' | periodical continuous | Switch | T | [9 empty] | Gemona del Friuli switch renewal (ePIR_ID 99_2026) | 81 | N |  | 2024-12-20 | Minor |  | Tra 10% e 30%
83 | RFI-BO-26-27 | Ferrara - Ravenna | < > | Lavezzola | Ravenna | 2026 | 2026 | 40 | 40 | 2026-10-03 |  | 2026-10-04 |  | 55h | continuous | Bridge | T | [9 empty] | maintenance works on a bridge KM 51+450 |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-BO-26-19 | Ferrara - Rimini | < > | Ravenna | Igea Marina | 2026 | 2026 | 41 | 41 | 2026-10-10 |  | 2026-10-11 |  | 55h | continuous | Bridge | T | [9 empty] | bridge substitution KM 101+595 |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-BO-26-28 | Ferrara - Rimini | < > | Ravenna | Milano Marittima | 2026 | 2026 | 42 | 42 | 2026-10-17 |  | 2026-10-18 |  | 55h | continuous | Bridge | T | [9 empty] | bridge waterproofing KM 75+106 |  | N |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2026-06 | Villach - Udine | < > | Ugovizza | Pontebba | 2026 | 2026 | 43 | 49 | 2026-10-19 | 8:00 | 2026-11-30 | 11:00 | 2 x 52 hours | periodical continuous | Track & Rail |  | LT | S | [5 empty] | 120 |  | Resinatura piaste IPA (ID TS-26-03) 2 weekends; LDP, LDF | 80, 81 | N |  | 2024-07-15 | Medium |  | >50%
83 | RFI-2026-07 | Villach - Udine | < > | Ugovizza | Pontebba | 2026 | 2026 | 43 | 49 | 2026-10-19 | 8:00 | 2026-11-30 | 11:00 | 56 x 180' | periodical continuous | Track & Rail | T |  | S | [5 empty] | 40 |  | Resinatura piaste IPA (ID TS-26-14) LDP, LDF | 80, 81 | N |  | 2024-12-20 | Minor |  | <10%
83 | RFI-TS-26-09 | Venezia - Trieste | < > | Portogruaro C. | Ronchi dei L. Sud | 2027 | 2027 | 48 | 48 | 31/10/2027 |  | 01/11/2027 |  | 48h | continuous | Others | T | [9 empty] | tecnological upgrade of the line (TS-26-09) + connection with the Venice airport of 12h (VE-26-71) |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-VE-26-71 | Venezia - Trieste | < > | Quarto D'Altino | Venezia Mestre | 2026 | 2026 | 48 | 48 | 2026-11-27 |  | 2026-11-29 |  | 12h | continuous | Others | T | [9 empty] | Connection with the Venice airport of 12h (VE-26-71) - in shadow of RFI-TS-26-09 |  |  |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2026-22 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 52 | 52 | 2026-12-28 |  | 2026-12-31 |  | 96h | continuous | Others | T | [9 empty] | PRG e ACC Trieste CM |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-27-06 | Udine - Trieste | < > | Cervignano Sm. | Cervignano Sm. | 2028 | 2028 | 1 | 1 | 01/10/2028 |  | 02/10/2028 |  | 48h | continuous | Others | T | [9 empty] | ACC CERVIGNANO SMISTAMENTO FASCIO ARRIVI E FASCIO ESTRAZIONI - Activation |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-27-03 | Villach - Udine | < | Pontebba | Carnia | 2027 | 2027 | 7 | 12 | 16/01/2027 |  | 08/02/2027 |  | 2x52h | continuous | Others |  | LT | [8 empty] | Resinatura piastre IPA |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-27-11 | Udine - Trieste | < | Cervignano Sm. | Cervignano A.G. | 2027 | 2027 | 11 | 17 | 2027-03-15 |  | 2027-05-02 |  | 41 days | continuous | Bridge |  | LT | [8 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-27-11) | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-2027-01 | Udine - Trieste | < > | Gorizia | Redipuglia | 2027 | 2027 | 11 | 11 | 2027-03-19 |  | 2027-03-21 |  | 48h | continuous | Others | T | [9 empty] | Lunetta di Gorizia |  |  |  | 2024-12-20 | Medium |  | >50%
83 | RFI-2027-03 | Venezia - Trieste | < > | Monfalcone | Ronchi dei L. Sud / Ronchi dei L. Nord | 2027 | 2027 | 9 | 17 | 04/09/2027 |  | 05/09/2027 |  | 1x45h | continuous | Others | T | [9 empty] | switch reneal (ePIR ID TS-27-23) |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-VR-26-32 | Brennero - Verona | < | Verona Quadrante Europa | Verona Quadrante Europa | 2027 | 2027 | 13 | 21 | 2027-04-01 |  | 2027-05-30 |  | 60 days | continuous | Track & Rail |  | ST |  |  |  | C | R |  | Y |  | track renewal - track interruptions for phases (VR-26-32)) interruption of III, IV, V FASCIO TERMINAL | 80 |  |  | 2025-08-01 | Major |  | Tra 30% e 50%
83 | RFI-BO-27-13 | Bologna - Padova | < > | Occhiobello | Ferrara | 2027 | 2027 | 14 | 14 | 17/04/2027 |  | 18/04/2027 |  | 55h | continuous | Bridge | T | [9 empty] | Seismic adjustments on a bridge km 50+125 |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-27-10 | Udine - Trieste | < > | Torviscosa | Cervignano A.G. | 2027 | 2027 | 18 | 23 | 2027-05-03 |  | 2027-06-12 |  | 35 days | continuous | Bridge |  | LT | [8 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-27-10) | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-TS-27-07 | Udine - Trieste | < | Torviscosa | Cervignano A.G. | 2027 | 2027 | 18 | 30 | 13/06/2027 |  | 18/07/2027 |  | 36 days | continuous | Bridge |  | LT | [8 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-27-10) | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-TS-27-13 | Udine - Trieste | < > | Cervignano sm | Cervignano A.G. | 2027 | 2027 | 18 | 30 | 2027-05-03 |  | 13/06/2027 |  | 41 days | continuous | Bridge | T | [9 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-27-11) | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-TS-27-04 | Villach - Udine | < > | Pontebba | Carnia | 2027 | 2027 | 21 | 27 | 2027-05-26 |  | 2027-07-09 |  | 45 days | continuous | Others | T |  |  |  |  | C | R |  | Y |  | works on the Zuc dal Bor tunnel - re-routing via Brennero and Villa Opicina | 79 |  |  | 2024-12-20 | Major |  | >50%
83 | RFI-VE-27-10 | Bologna - Padova | < | Terme Euganee | Monselice | 2027 | 2027 | 22 | 30 | 01/06/2028 |  | 30/07/2028 |  | 60 days | continuous | Others |  | LT | [8 empty] | odd track closure for works on Catajo tunnel |  |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-TS-25-20 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2027 | 2027 | 22 | 26 | 16/07/2027 |  | 18/07/2027 |  | 40h | continuous | Others | T | [9 empty] | PRG + ACC Villa Opicina (ePIR_ID TS-25-20) |  |  |  | 2026-04-29 | Medium |  | >50%
83 | RFI-TS-27-15 | Venezia - Trieste | < | Casarsa | Casarsa | 2027 | 2027 | 28 | 33 | 2027-07-12 |  | 2027-08-22 |  | 80 days | continuous | Others |  | ST | [8 empty] | interrupion of some track in Casarsa station for renewal works |  |  |  | 2025-08-01 | Major |  | Tra 30% e 50%
83 | RFI-TS-27-12 | Udine - Trieste | < | Cervignano Sm. | Cervignano A.G. | 2027 | 2027 | 30 | 43 | 2027-08-01 |  | 2027-10-31 |  | 35 days | continuous | Bridge |  | LT | [8 empty] | Maintenance of Cervignano viaduct (ePIR ID TS-27-12) | 79, 81 |  |  | 2025-08-01 | Major |  | >50%
83 | RFI-2027-04 | Venezia - Trieste | < > | San Giorgio di Nogaro | Torviscosa | 2027 | 2027 | 35 | 43 | 2027-09-01 |  | 2027-11-30 |  | 4x30h | continuous | Track & Rail | T | [9 empty] | track maintenance |  |  |  | 15/12/025 | Medium |  | >50%
83 | RFI-TS-27-05 | Villach - Udine | < | Ugovizza V. | Pontebba | 2027 | 2027 | 42 | 47 | 2027-10-18 |  | 2027-11-28 |  | 2x52h | continuous | Others |  | LT | [8 empty] | Resinatura piastre IPA |  |  |  | 2024-12-20 | Medium |  | >50%
83 | RFI-VE-26-19 | Bologna - Padova | < | S. Elena | Rovigo | 2027 | 2027 | 42 | 43 | 2027-10-24 |  | 2027-10-25 |  | 48h | continuous | Bridge |  | LT | S | [7 empty] | Adige bridge (ID VE-26-19) |  |  |  | 2025-08-01 | Medium |  | >50%
83 | RFI-2026-30 | Tarvisio - Venezia | < > | Treviso | Spresiano | 2028 | 2028 | 44 | 50 | 2028 |  | 2028 |  | 48h | continuous | Others | T | [9 empty] | (ePIR_ID VE-26-07) |  | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-2027-02 | Venezia - Trieste | < > | Venezia Mestre | Portogruaro | 2027 | 2027 | 47 | 47 | 2027-11-27 |  | 2028-11-28 |  | 20h | continuous | Others | T | [9 empty] | Line upgrading -phase 2 activation |  |  |  | 15/12/025 | Medium |  | >50%
83 | RFI-2026-33 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2028 | 2028 | 48 | 48 | 2028 |  | 2028 |  | 1x40h | continuous | Others | T | ST | [8 empty] | PRG + ACC Villa Opicina (ePIR_ID TS-27-08) | 79 | N |  | 2026-04-29 | Medium |  | >50%
83 | RFI-2028-04 | Udine - Trieste | < | Cervignano Sm. | Cervignano A.G. | 2028 | 2028 | 5 | 11 | 2028-01-31 |  | 2028-03-16 |  | 45 days | continuous | Bridge |  | LT | [8 empty] | Maintenance of Cervignano viaduct - track interruption of the 2 tracks line | 79, 81 |  |  | 2026-04-29 | High |  | Tra 30% e 50%
83 | RFI-2028-05 | Udine - Trieste | < | Cervignano Sm. | Cervignano A.G. | 2028 | 2028 | 11 | 17 | 2028-03-17 |  | 2028-04-30 |  | 41 days | continuous | Bridge |  | LT | [8 empty] | Maintenance of Cervignano viaduct - track interruption of the 2 tracks line | 79, 81 |  |  | 2026-04-29 | High |  | Tra 30% e 50%
83 | RFI-2028-06 | Udine - Trieste | < > | Cervignano Sm. | Cervignano A.G. | 2028 | 2028 | 11 | 17 | 2028-03-17 |  | 2028-04-30 |  | 45 days | continuous | Bridge | T | [9 empty] | Maintenance of Cervignano viaduct - total interruption of the single track line | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-2028-07 | Udine - Trieste | < | Torviscosa | Cervignano A.G. | 2028 | 2028 | 11 | 17 | 2028-03-17 |  | 2028-04-30 |  | 45 days | continuous | Bridge | T | [9 empty] | total closure of the single track line - Maintenance of Cervignano viaduct (ePIR ID TS-27-13) | 79, 81 |  |  | 2026-04-29 | High |  | Tra 30% e 50%
83 | RFI-2028-08 | Udine - Trieste | < | Torviscosa | Cervignano A.G. | 2028 | 2028 | 18 | 23 | 2027-05-01 |  | 2027-06-30 |  | 40 days | continuous | Bridge | T | [9 empty] | total closure of the single track line - Maintenance of Cervignano viaduct (ePIR ID TS-27-13) | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-2026-29 | Camposampiero - Vigodarzere | < > | Camposampiero | Vigodarzere | 2026 | 2026 | 34 | 36 | 20/08/2026 28/08/2028 |  | 03/09/2026 18/09/2028 |  | 14 days | continuous | Bridge | T | [9 empty] | extraordinary maintenance of a bridge (ePIR_ID VE-26-06) |  | N |  | 2023-12-14 | High |  | >50%
83 | RFI-2028-01 | Ljubljana - Udine | < > | Udine | Udine | 2028 | 2028 | 35 | 48 | 2028-09-01 |  | 2028-11-30 |  | 30 days | continuous | Others |  | ST | [8 empty] | PRG UDINE |  |  |  | 15/12/025 | Major |  | >50%
83 | RFI-2028-03 | Tarvisio - Venezia | < > | Thorl Magler | Gemona del Friuli | 2028 | 2028 | 35 | 48 | 2028-09-01 |  | 2028-11-30 |  | 90 days | continuous | Others | T | [9 empty] | PRG UDINE |  |  |  | 15/12/025 | Major |  | >50%
83 | RFI-2028-02 | Camposampiero - Vigodarzere | < > | Vigodarzere | Padova | 2028 | 2028 | 48 | 52 | 2028-12-01 |  | 2028-12-31 |  | 8 days | continuous | Others | T | [9 empty] | line doubling on the Brenta bridge |  |  |  | 15/12/025 | Major |  | >50%
83 | RFI-2027-05 | Venezia - Trieste | < | Venezia Mestre | Venezia Mestre | 2027 | 2027 | 51 | 50 | 2026-12-13 |  | 2027-12-11 |  | 2x180 days | continuous |  |  | ST | [8 empty] | Station works: two Continuous interruption of two Tracks for six moth each other | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-2028-09 | Venezia - Trieste | < | Trieste Campo Marzio | Trieste Campo Marzio | 2028 | 2028 | 2 | 2 | 03/01/2028 |  | 30/06/2028 |  | 179 days | continuous |  |  | ST | [8 empty] | San Pantaleone Tunnel Consolidation: Phased interruption of tracks at the Aquilinia yard with partial freight traffic limitation (TS-28-05) | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
83 | RFI-2027-06 | Venezia - Trieste | < | Venezia Mestre | Venezia Mestre | 2028 | 2028 | 51 | 51 | 2027-12-12 |  | 2028-12-10 |  | 2x180 days | continuous |  |  | ST | [8 empty] | Station works: two Continuous interruption of two Tracks for six moth each other | 79, 81 |  |  | 2026-04-29 | Major |  | >50%
0054 | V-000165/26 | Czechowice Dziedzice - Ostrava | < > | Bohumín-Vrbice | Bohumín-Vrbice st.hr | 2026 | 2026 | 22 | 22 | 2026-05-25 | 7:00 | 2026-05-25 | 15:00 | 1 x 8 hours | periodical | Track & Rail | T | LT | [8 empty] | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-000349/26 | Wroclaw - Breclav | < > | Blansko | Rájec-Jestřebí | 2026 | 2026 | 21 | 21 | 2026-05-20 | 23:45 | 2026-05-21 | 3:20 | 1 x 4 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4
0054 | V-000770/26 | Wroclaw - Breclav | < > | Dolní Lipka | Lichkov | 2026 | 2026 | 19 | 21 | 2026-05-06 | 8:00 | 2026-05-24 | 18:00 | 18 days + 10 hours | continuous | Track & Rail | T | LT | [5 empty] | ,X,X |  |  | traťová bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-000775/26 | Czechowice Dziedzice - Ostrava | < > | Bohumín-Vrbice | Ostrava hl.n. | 2026 | 2026 | 2 | 4 | 2026-01-05 | 7:00 | 2026-01-19 | 17:00 | 5 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-000829/26 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 9 | 20 | 2026-02-24 | 8:00 | 2026-05-15 | 17:00 | 8 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-006052/26 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 15 | 27 | 2026-04-08 | 8:00 | 2026-07-04 | 17:00 | 9 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-006056/26 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 16 | 29 | 2026-04-14 | 8:00 | 2026-07-17 | 17:00 | 13 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-006067/26 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 16 | 31 | 2026-04-17 | 8:00 | 2026-07-31 | 17:00 | 14 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-000834/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 21 | 22 | 2026-05-21 | 8:00 | 2026-05-25 | 17:00 | 5 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 4. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,4,5,6,7
0054 | V-000834/26 | Wroclaw - Breclav | < > | Česká Třebová | Dlouhá Třebová | 2026 | 2026 | 21 | 22 | 2026-05-21 | 8:00 | 2026-05-25 | 17:00 | 5 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,4,5,6,7
0054 | V-002685/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 26 | 27 | 2026-06-23 | 8:00 | 2026-06-30 | 17:00 | 8 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-000839/26 | Wroclaw - Breclav | < > | Dlouhá Třebová | Česká Třebová | 2026 | 2026 | 17 | 20 | 2026-04-21 | 8:00 | 2026-05-17 | 17:00 | 9 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-000841/26 | Wroclaw - Breclav | < > | Dlouhá Třebová | Česká Třebová | 2026 | 2026 | 21 | 21 | 2026-05-18 | 8:00 | 2026-05-20 | 17:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3
0054 | V-002717/26 | Wroclaw - Breclav | < > | Dlouhá Třebová | Česká Třebová | 2026 | 2026 | 25 | 26 | 2026-06-16 | 8:00 | 2026-06-22 | 17:00 | 7 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-000841/26 | Wroclaw - Breclav | < > | Odb Parník | Česká Třebová | 2026 | 2026 | 21 | 21 | 2026-05-18 | 8:00 | 2026-05-20 | 17:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3
0054 | V-000844/26 | Wroclaw - Breclav | < > | Odb Parník | Česká Třebová | 2026 | 2026 | 20 | 20 | 2026-05-11 | 8:00 | 2026-05-15 | 17:00 | 5 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-000879/26 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 20 | 48 | 2026-05-14 | 7:00 | 2026-11-25 | 18:00 | 195 days + 11 hours | continuous | Miscellaneous |  | LT | [8 empty] | 4. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-000881/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 21 | 21 | 2026-05-20 | 23:00 | 2026-05-24 | 4:00 | 4 x 5 hours | periodical | Maintenance | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-000885/26 | Wroclaw - Breclav | < > | Odb Zádulka | Česká Třebová | 2026 | 2026 | 20 | 22 | 2026-05-14 | 7:00 | 2026-05-28 | 18:00 | 14 days + 11 hours | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-001124/26 | Czechowice Dziedzice - Ostrava | < > | Petrovice u K.st.hr. | Petrovice u Karviné | 2026 | 2026 | 5 | 10 | 2026-01-26 | 7:00 | 2026-03-07 | 17:00 | 40 days + 10 hours | continuous | Others |  | LT | [8 empty] | 2. bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-001127/26 | Czechowice Dziedzice - Ostrava | < > | Petrovice u K.st.hr. | Petrovice u Karviné | 2026 | 2026 | 5 | 9 | 2026-01-26 | 7:00 | 2026-02-24 | 7:00 | 29 days + 0 hours | continuous | Others |  | LT | [8 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-001187/26 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 12 | 12 | 2026-03-16 | 8:00 | 2026-03-20 | 18:00 | 5 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 4. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-001341/26 | Wroclaw - Breclav | < > | Česká Třebová | Opatov | 2026 | 2026 | 15 | 15 | 2026-04-08 | 8:00 | 2026-04-10 | 17:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-001344/26 | Wroclaw - Breclav | < > | Odb Zádulka | Česká Třebová | 2026 | 2026 | 16 | 16 | 2026-04-18 | 8:00 | 2026-04-18 | 17:00 | 1 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-001345/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 16 | 17 | 2026-04-19 | 23:30 | 2026-04-20 | 3:45 | 1 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,7
0054 | V-001377/26 | Ostrava - Breclav | < > | Staré Město u U.H. | Staré Město u U.H. | 2026 | 2026 | 24 | 24 | 2026-06-13 | 22:50 | 2026-06-14 | 3:00 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 6,7
0054 | V-001394/26 | Czechowice Dziedzice - Ostrava | < > | Petrovice u K.st.hr. | Petrovice u Karviné | 2026 | 2026 | 9 | 9 | 2026-02-24 | 7:00 | 2026-02-28 | 17:00 | 5 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5,6
0054 | V-002037/26 | Wroclaw - Breclav | < > | Modřice | Křenovice horní n. | 2026 | 2026 | 21 | 22 | 2026-05-18 | 8:40 | 2026-05-26 | 13:30 | 12 x 5 hours | periodical | Catenary |  | LT | [12 empty] | 2026-04-29 10:03 |  | 1,2
0054 | V-002052/26 | Wroclaw - Breclav | < > | Svitavy | Česká Třebová | 2026 | 2026 | 25 | 25 | 2026-06-15 | 8:10 | 2026-06-16 | 13:30 | 4 x 6 hours | periodical | Catenary |  | LT | [12 empty] | 2026-04-29 10:03 |  | 1,2
0054 | V-002042/26 | Wroclaw - Breclav | < > | Modřice | Křenovice horní n. | 2026 | 2026 | 22 | 22 | 2026-05-27 | 8:30 | 2026-05-28 | 13:30 | 10 x 5 hours | periodical | Catenary |  | LT | [12 empty] | 2026-04-29 10:03 |  | 3,4
0054 | V-002054/26 | Wroclaw - Breclav | < > | Svitavy | Česká Třebová | 2026 | 2026 | 25 | 25 | 2026-06-17 | 8:10 | 2026-06-18 | 13:30 | 4 x 6 hours | periodical | Catenary |  | LT | [12 empty] | 2026-04-29 10:03 |  | 3,4
0054 | V-002117/26 | Wroclaw - Breclav | < > | Hrušovany u Brna | Hrušovany u Brna | 2026 | 2026 | 23 | 25 | 2026-06-01 | 23:35 | 2026-06-16 | 3:50 | 2 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-002124/26 | Wroclaw - Breclav | < > | Rájec-Jestřebí | Rájec-Jestřebí | 2026 | 2026 | 24 | 24 | 2026-06-08 | 23:45 | 2026-06-09 | 4:10 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-003981/26 | Wroclaw - Breclav | < > | Skalice nad Svitavou | Skalice nad Svitavou | 2026 | 2026 | 30 | 30 | 2026-07-20 | 23:55 | 2026-07-21 | 4:00 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-008450/26 | Wroclaw - Breclav | < > | Zaječí | Zaječí | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:05 | 2026-08-11 | 3:35 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-002596/26 | Ostrava - Breclav | < > | Drahotuše | Lipník nad Bečvou | 2026 | 2026 | 24 | 25 | 2026-06-10 | 0:20 | 2026-06-15 | 4:20 | 6 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,3,4,5,6,7
0054 | V-002602/26 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 25 | 27 | 2026-06-17 | 7:00 | 2026-06-29 | 17:00 | 12 days + 10 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-002680/26 | Wroclaw - Breclav | < > | Opatov | Česká Třebová | 2026 | 2026 | 24 | 24 | 2026-06-13 | 7:30 | 2026-06-14 | 17:00 | 4 x 10 hours | periodical | Miscellaneous |  | LT | [12 empty] | 2026-04-29 10:03 |  | 6,7
0054 | V-002693/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 23 | 24 | 2026-06-01 | 8:00 | 2026-06-11 | 17:00 | 11 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-002724/26 | Wroclaw - Breclav | < > | Česká Třebová | Třebovice v Čechách | 2026 | 2026 | 23 | 23 | 2026-06-01 | 8:00 | 2026-06-07 | 18:00 | 7 x 10 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-002732/26 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 24 | 24 | 2026-06-08 | 8:00 | 2026-06-12 | 18:00 | 5 x 10 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-002739/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 23 | 26 | 2026-06-03 | 8:00 | 2026-06-22 | 18:00 | 19 days + 10 hours | continuous | Miscellaneous |  | LT | [8 empty] | 3. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-003051/26 | Czechowice Dziedzice - Ostrava | < > | Bohumín-Vrbice | Bohumín-Vrbice | 2026 | 2026 | 20 | 20 | 2026-05-13 | 7:00 | 2026-05-13 | 13:00 | 1 x 6 hours | periodical | Signal |  | ST |  |  | X | [5 empty] | 610.,612. bez TV, 610.-620.,606a jen TV. zab. zař. náv. Sc612. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003218/26 | Wroclaw - Breclav | < > | Jablonné nad Orlicí | Letohrad | 2026 | 2026 | 9 | 9 | 2026-02-26 | 10:10 | 2026-02-26 | 11:10 | 1 x 1 hours | periodical | Others | T | LT | [8 empty] | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 4
0054 | V-003886/26 | Detmarovice - Cadca | < > | Návsí | Mosty u Jablunkova | 2026 | 2026 | 28 | 28 | 2026-07-08 | 10:20 | 2026-07-08 | 14:05 | 1 x 4 hours | periodical | Catenary |  | LT |  |  | X |  |  | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003889/26 | Detmarovice - Cadca | < > | Bystřice | Návsí | 2026 | 2026 | 29 | 29 | 2026-07-15 | 10:30 | 2026-07-15 | 14:25 | 1 x 4 hours | periodical | Catenary |  | LT |  |  | X |  |  | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003886/26 | Detmarovice - Cadca | < > | Mosty u Jablunkova | Mosty u Jablunkova | 2026 | 2026 | 28 | 28 | 2026-07-08 | 10:20 | 2026-07-08 | 14:05 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | 1. bez TV, celá jen TV. záhlaví a zhlaví 1. traťové koleje směr Návsí od náv. 1S po nám. výh. č. 8. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003886/26 | Detmarovice - Cadca | < > | Mosty u Jablunkova | Návsí | 2026 | 2026 | 28 | 28 | 2026-07-08 | 10:20 | 2026-07-08 | 14:05 | 1 x 4 hours | periodical | Catenary |  | LT |  |  | X |  |  | ,X,X |  |  | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003889/26 | Detmarovice - Cadca | < > | Návsí | Bystřice | 2026 | 2026 | 29 | 29 | 2026-07-15 | 10:30 | 2026-07-15 | 14:25 | 1 x 4 hours | periodical | Catenary |  | LT |  |  | X |  |  | ,X,X |  |  | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003889/26 | Detmarovice - Cadca | < > | Návsí | Návsí | 2026 | 2026 | 29 | 29 | 2026-07-15 | 10:30 | 2026-07-15 | 14:25 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | 1. bez TV, celá jen TV. záhlaví a zhlaví 1. traťové koleje směr Bystřice od náv. 1S po nám. výh. č. 26. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-003891/26 | Detmarovice - Cadca | < > | Český Těšín | Český Těšín st.hr. | 2026 | 2026 | 30 | 30 | 2026-07-21 | 8:15 | 2026-07-21 | 13:00 | 1 x 5 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-003891/26 | Detmarovice - Cadca | < > | Český Těšín | Albrechtice u Č.T. | 2026 | 2026 | 30 | 30 | 2026-07-21 | 8:15 | 2026-07-21 | 13:00 | 1 x 5 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-003899/26 | Detmarovice - Cadca | < > | Český Těšín | Český Těšín | 2026 | 2026 | 31 | 31 | 2026-07-28 | 10:05 | 2026-07-28 | 14:10 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | 100.,101.,101a,103.-107.,102.-124.,104a,110a,110b jen TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-003899/26 | Detmarovice - Cadca | < > | Český Těšín | Třinec | 2026 | 2026 | 31 | 31 | 2026-07-28 | 10:05 | 2026-07-28 | 14:10 | 1 x 5 hours | periodical | Catenary |  | LT |  |  | X |  |  | ,X,X |  |  | 1. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-003899/26 | Detmarovice - Cadca | < > | Třinec-Konská z | Český Těšín | 2026 | 2026 | 31 | 31 | 2026-07-28 | 10:05 | 2026-07-28 | 14:10 | 1 x 5 hours | periodical | Catenary |  | LT |  |  | X |  |  | ,X,X |  |  | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-004594/26 | Detmarovice - Cadca | < > | Karviná hl.n. | Odb Karviná-Darkov z | 2026 | 2026 | 12 | 12 | 2026-03-16 | 7:15 | 2026-03-21 | 17:00 | 10 x 10 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,6
0054 | V-005140/26 | Wroclaw - Breclav | < > | Vranovice | Šakvice | 2026 | 2026 | 19 | 27 | 2026-05-08 | 7:30 | 2026-07-05 | 11:00 | 3 x 4 hours | periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 5,6,7
0054 | V-005142/26 | Wroclaw - Breclav | < > | Vranovice | Vranovice | 2026 | 2026 | 19 | 28 | 2026-05-04 | 23:50 | 2026-07-09 | 4:20 | 2 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-005854/26 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 29 | 49 | 2026-07-17 | 19:00 | 2026-12-03 | 17:00 | 138 days + 22 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-005864/26 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 28 | 28 | 2026-07-10 | 0:20 | 2026-07-10 | 4:20 | 2 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 5
0054 | V-005871/26 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 29 | 29 | 2026-07-16 | 0:20 | 2026-07-16 | 4:20 | 2 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 4
0054 | V-005878/26 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 29 | 29 | 2026-07-18 | 0:20 | 2026-07-18 | 4:20 | 2 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-006021/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 27 | 30 | 2026-07-02 | 8:00 | 2026-07-21 | 18:00 | 19 days + 10 hours | continuous | Miscellaneous |  | LT | [8 empty] | 4. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-006023/26 | Wroclaw - Breclav | < > | Opatov | Česká Třebová | 2026 | 2026 | 27 | 28 | 2026-07-01 | 8:00 | 2026-07-07 | 17:00 | 7 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-006032/26 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 30 | 30 | 2026-07-22 | 7:00 | 2026-07-25 | 18:00 | 3 days + 11 hours | continuous | Miscellaneous |  | LT | [8 empty] | 97. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-006034/26 | Wroclaw - Breclav | < > | Česká Třebová | Dlouhá Třebová | 2026 | 2026 | 28 | 28 | 2026-07-08 | 0:10 | 2026-07-11 | 3:10 | 4 x 3 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6
0054 | V-006034/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 28 | 28 | 2026-07-08 | 0:10 | 2026-07-11 | 3:10 | 4 x 3 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6
0054 | V-006039/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 28 | 28 | 2026-07-07 | 23:00 | 2026-07-10 | 4:00 | 3 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-006042/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 31 | 31 | 2026-07-27 | 23:00 | 2026-07-30 | 4:00 | 3 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-006039/26 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 28 | 28 | 2026-07-07 | 23:00 | 2026-07-10 | 4:00 | 3 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 3. bez TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-006042/26 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 31 | 31 | 2026-07-27 | 23:00 | 2026-07-30 | 4:00 | 3 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 3. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-006039/26 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 28 | 28 | 2026-07-07 | 23:00 | 2026-07-10 | 4:00 | 3 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 96.,96a + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-006042/26 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 31 | 31 | 2026-07-27 | 23:00 | 2026-07-30 | 4:00 | 3 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 96.,96a + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-006320/26 | Ostrava - Breclav | < > | Rohatec | Hodonín | 2026 | 2026 | 13 | 13 | 2026-03-28 | 20:30 | 2026-03-29 | 3:30 | 1 x 7 hours | periodical | Others | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 6,7
0054 | V-006536/26 | Ostrava - Breclav | < > | Otrokovice | Nedakonice | 2026 | 2026 | 18 | 18 | 2026-04-28 | 7:00 | 2026-04-29 | 15:00 | 4 x 8 hours | periodical | Maintenance |  | LT | [12 empty] | 2026-04-29 10:03 |  | 2,3
0054 | V-007149/26 | Opole - Bohumin | < > | Bohumín os.n. | Bohumín st.hr. | 2026 | 2026 | 19 | 19 | 2026-05-06 | 7:30 | 2026-05-06 | 17:30 | 1 x 10 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-007565/26 | Ostrava - Breclav | < > | Hranice na Moravě | Hranice na Moravě | 2026 | 2026 | 34 | 34 | 2026-08-23 | 5:40 | 2026-08-23 | 8:40 | 1 x 3 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007567/26 | Ostrava - Breclav | < > | Staré Město u U.H. | Huštěnovice | 2026 | 2026 | 37 | 37 | 2026-09-08 | 1:30 | 2026-09-10 | 10:00 | 3 x 9 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. bez TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-007572/26 | Ostrava - Breclav | < > | Nedakonice | Staré Město u U.H. | 2026 | 2026 | 33 | 34 | 2026-08-16 | 1:30 | 2026-08-18 | 10:00 | 3 x 9 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,7
0054 | V-007613/26 | Czechowice Dziedzice - Ostrava | < > | Ostrava hl.n. | Ostrava hl.n. | 2026 | 2026 | 26 | 27 | 2026-06-22 | 21:30 | 2026-06-30 | 3:50 | 8 x 7 hours | periodical | Bridge |  | ST |  |  | X | [5 empty] | 1. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-007613/26 | Czechowice Dziedzice - Ostrava | < > | Ostrava hl.n. | Ostrava hl.n. | 2026 | 2026 | 26 | 27 | 2026-06-22 | 21:30 | 2026-06-30 | 3:50 | 8 x 7 hours | periodical | Bridge |  | ST |  |  | X | [5 empty] | 1. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-007631/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-08 | 9:20 | 2026-08-08 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | ost. zař.: napájecí převěsy mezi ÚO 3, ÚO 411, ÚO 411A a ÚO 13, ÚO 13, ÚO 412, ÚO 412A . |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007631/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-08 | 9:20 | 2026-08-08 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví 2. traťové koleje směr Brno hlavní nádraží, od návěstidla L ponámezník výhybky č. 5 |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007631/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-08 | 9:20 | 2026-08-08 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví severní koleje č. 905, jeho část od hrotů jazyků výhybky č. 1XA po izlovaný styk výhybky č. 2. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007631/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-08 | 9:20 | 2026-08-08 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007631/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-08 | 9:20 | 2026-08-08 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 2a,2b jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007631/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-08 | 9:20 | 2026-08-08 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 905. bez TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007632/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-15 | 9:20 | 2026-08-15 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví severní koleje č. 905, jeho část od hrotů jazyků výhybky č. 1XA po izlovaný styk výhybky č. 2. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007632/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-15 | 9:20 | 2026-08-15 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007632/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-15 | 9:20 | 2026-08-15 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 2a,2b jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007632/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-15 | 9:20 | 2026-08-16 | 20:20 | 2 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 905. bez TV. |  |  |  | 2026-04-29 10:03 |  | 6,7
0054 | V-007632/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-15 | 9:20 | 2026-08-15 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | ost. zař.: napájecí převěsy mezi ÚO 3, ÚO 411, ÚO 411A a ÚO 13, ÚO 13, ÚO 412, ÚO 412A . |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007632/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-15 | 9:20 | 2026-08-15 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví 2. traťové koleje směr Brno hlavní nádraží, od návěstidla L ponámezník výhybky č. 5 |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-007633/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-09 | 9:20 | 2026-08-09 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | ost. zař.: napájecí převěs mezi ÚO 3, ÚO 411 a ÚO 411A. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007633/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-09 | 9:20 | 2026-08-09 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví 1. traťové koleje směr Brno hlavní nádraží, jeho část od izolovaného styku mezi výhybkami č. 1 a 9 po návěstidlo 1L. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007633/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-09 | 9:20 | 2026-08-09 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví severní koleje č. 905, jeho část od hrotů jazyků výhybky č. 1XA po námezník výhybky č. 2. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007633/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-09 | 9:20 | 2026-08-09 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1. jen TV. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007633/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-09 | 9:20 | 2026-08-09 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1a,1b jen TV. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007633/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 32 | 32 | 2026-08-09 | 9:20 | 2026-08-09 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 905. bez TV. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007634/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-16 | 9:20 | 2026-08-16 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | ost. zař.: napájecí převěs mezi ÚO 3, ÚO 411 a ÚO 411A. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007634/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-16 | 9:20 | 2026-08-16 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví 1. traťové koleje směr Brno hlavní nádraží, jeho část od izolovaného styku mezi výhybkami č. 1 a 9 po návěstidlo 1L. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007634/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-16 | 9:20 | 2026-08-16 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví severní koleje č. 905, jeho část od hrotů jazyků výhybky č. 1XA po námezník výhybky č. 2. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007634/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-16 | 9:20 | 2026-08-16 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1. jen TV. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007634/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-16 | 9:20 | 2026-08-16 | 20:20 | 1 x 11 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1a,1b jen TV. |  |  |  | 2026-04-29 10:03 |  | 7
0054 | V-007641/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví 1. traťové koleje směr Brno hlavní nádraží, jeho část od izolovaného styku mezi výhybkami č. 1 a 9 po návěstidlo 1L. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007641/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví 1. traťové koleje směr Brno-Černovice zhlaví Táborská, jeho část od izolovaného styku mezi výhybkou č. 13 a kolejovým křížením po návěstidlo 1CL. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007641/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví severní koleje č. 905, jeho část od hrotů jazyků výhybky č. 1XA po námezník výhybky č. 2. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007641/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1.,1a,1b,2.,2a,2b,6. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007641/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 905. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007641/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007642/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno hl.n. | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 2. jen TV, 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007643/26 | Wroclaw - Breclav | < > | Brno-Černov.zhl.Táb. | Brno-Černov.zhl.Táb. | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví směr Odb Brno-Židenice a směr Brno dolní nádraží, od návěstidla S po návěstidlo 1L. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007643/26 | Wroclaw - Breclav | < > | Brno-Černov.zhl.Táb. | Brno-Černov.zhl.Táb. | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007643/26 | Wroclaw - Breclav | < > | Brno-Černov.zhl.Táb. | Brno dolní n. | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 2 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007643/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno dolní n. | 2026 | 2026 | 33 | 33 | 2026-08-10 | 23:20 | 2026-08-11 | 4:25 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-007644/26 | Wroclaw - Breclav | < > | Brno hl.n. | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. jen TV, 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007645/26 | Wroclaw - Breclav | < > | Brno-Černov.zhl.Táb. | Brno-Černov.zhl.Táb. | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007645/26 | Wroclaw - Breclav | < > | Brno dolní n. | Brno-Černov.zhl.Táb. | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 2 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 2. bez TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007645/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno dolní n. | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007646/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví 2. traťové koleje směr Brno hlavní nádraží, jeho část od návěstidla L po izolovaný styk výhybky č. 5. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007646/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví 2. traťové koleje směr Brno-Černovice zhlaví Táborská, jeho část od návěstidla CLpo izolovaný styk mezi výhybkami č. 4 a 7. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007646/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví severní koleje č. 905, jeho část od hrotů jazyků výhybky č. 1XA po námezník výhybky č. 2. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007646/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1.,1a,1b,2.,2a,2b,6. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007646/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 905. bez TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007646/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 33 | 33 | 2026-08-11 | 23:20 | 2026-08-12 | 4:25 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-007676/26 | Wroclaw - Breclav | < > | Jablonné nad Orlicí | Letohrad | 2026 | 2026 | 14 | 14 | 2026-03-30 | 10:10 | 2026-03-30 | 11:10 | 1 x 1 hours | periodical | Others | T | LT | [8 empty] | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-007677/26 | Wroclaw - Breclav | < > | Jablonné nad Orlicí | Letohrad | 2026 | 2026 | 14 | 14 | 2026-03-31 | 10:10 | 2026-03-31 | 11:10 | 1 x 1 hours | periodical | Others | T | LT | [8 empty] | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-007693/26 | Wroclaw - Breclav | < > | Opatov | Svitavy | 2026 | 2026 | 30 | 30 | 2026-07-22 | 7:00 | 2026-07-23 | 19:00 | 1 days + 12 hours | continuous | Switch |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-007694/26 | Wroclaw - Breclav | < > | Svitavy | Opatov | 2026 | 2026 | 30 | 30 | 2026-07-24 | 7:00 | 2026-07-25 | 19:00 | 1 days + 12 hours | continuous | Switch |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-007699/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 37 | 37 | 2026-09-07 | 7:30 | 2026-09-11 | 17:30 | 5 x 10 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-007704/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2026 | 2026 | 38 | 38 | 2026-09-14 | 7:30 | 2026-09-18 | 17:30 | 5 x 10 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 6. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-007711/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 39 | 39 | 2026-09-21 | 7:30 | 2026-09-22 | 17:30 | 1 days + 10 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-007711/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2026 | 2026 | 39 | 39 | 2026-09-21 | 7:30 | 2026-09-22 | 17:30 | 1 days + 10 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 6. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-007712/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 39 | 39 | 2026-09-23 | 7:30 | 2026-09-25 | 17:30 | 2 days + 10 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-007712/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Odb Brno-Židenice z | 2026 | 2026 | 39 | 39 | 2026-09-23 | 7:30 | 2026-09-25 | 17:30 | 2 days + 10 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 6. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-007713/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 39 | 40 | 2026-09-26 | 8:35 | 2026-09-28 | 16:45 | 2 days + 9 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-007713/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice St.3 | 2026 | 2026 | 39 | 40 | 2026-09-26 | 8:35 | 2026-09-28 | 16:45 | 2 days + 9 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 2K jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-007713/26 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice St.3 | 2026 | 2026 | 39 | 40 | 2026-09-26 | 8:35 | 2026-09-28 | 16:45 | 2 days + 9 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 2K bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-007714/26 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 40 | 40 | 2026-09-29 | 7:30 | 2026-09-30 | 17:30 | 1 days + 10 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-008005/26 | Ostrava - Breclav | < > | Moravský Písek | Bzenec přívoz | 2026 | 2026 | 32 | 33 | 2026-08-07 | 7:20 | 2026-08-14 | 14:35 | 7 days + 8 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-008012/26 | Ostrava - Breclav | < > | Bzenec přívoz | Rohatec | 2026 | 2026 | 35 | 36 | 2026-08-29 | 7:20 | 2026-09-04 | 13:25 | 6 days + 7 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-008024/26 | Wroclaw - Breclav | < > | Jablonné nad Orlicí | Letohrad | 2026 | 2026 | 15 | 15 | 2026-04-09 | 10:10 | 2026-04-09 | 11:10 | 1 x 1 hours | periodical | Others | T | LT | [8 empty] | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 4
0054 | V-008051/26 | Ostrava - Breclav | < > | Rohatec | Bzenec přívoz | 2026 | 2026 | 34 | 35 | 2026-08-21 | 7:20 | 2026-08-28 | 13:25 | 7 days + 7 hours | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-008155/26 | Wroclaw - Breclav | < > | Zaječí | Podivín | 2026 | 2026 | 32 | 32 | 2026-08-03 | 8:20 | 2026-08-05 | 14:35 | 3 x 7 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3
0054 | V-008472/26 | Wroclaw - Breclav | < > | Letovice | Letovice | 2026 | 2026 | 32 | 32 | 2026-08-04 | 0:15 | 2026-08-04 | 3:40 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-008653/26 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 32 | 33 | 2026-08-03 | 8:00 | 2026-08-14 | 17:00 | 12 x 9 hours | periodical | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-008666/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 6 | 35 | 2026-02-05 | 8:00 | 2026-08-28 | 17:00 | 16 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-008678/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 36 | 36 | 2026-09-01 | 8:00 | 2026-09-03 | 17:00 | 3 x 9 hours | periodical | Catenary |  | LT | [8 empty] | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-008681/26 | Wroclaw - Breclav | < > | Česká Třebová | Dlouhá Třebová | 2026 | 2026 | 35 | 36 | 2026-08-29 | 0:10 | 2026-08-31 | 4:00 | 3 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,6,7
0054 | V-008681/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 35 | 36 | 2026-08-29 | 0:10 | 2026-08-31 | 4:00 | 3 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,6,7
0054 | V-008681/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 35 | 36 | 2026-08-29 | 0:10 | 2026-08-31 | 4:00 | 3 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 4. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,6,7
0054 | V-008684/26 | Wroclaw - Breclav | < > | Česká Třebová | Dlouhá Třebová | 2026 | 2026 | 36 | 36 | 2026-09-01 | 0:10 | 2026-09-01 | 4:00 | 1 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-008684/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 36 | 36 | 2026-09-01 | 0:10 | 2026-09-01 | 4:00 | 1 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-008684/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 36 | 36 | 2026-09-01 | 0:10 | 2026-09-01 | 4:00 | 1 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 4. + TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-008685/26 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 33 | 34 | 2026-08-14 | 23:00 | 2026-08-19 | 4:00 | 5 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,5,6,7
0054 | V-008685/26 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 33 | 34 | 2026-08-14 | 23:00 | 2026-08-19 | 4:00 | 5 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 96.,96a + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,5,6,7
0054 | V-008685/26 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 33 | 34 | 2026-08-14 | 23:00 | 2026-08-19 | 4:00 | 5 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 3. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,5,6,7
0054 | V-009096/26 | Ostrava - Breclav | < > | Jistebník | Jistebník | 2026 | 2026 | 29 | 30 | 2026-07-19 | 21:15 | 2026-07-25 | 2:15 | 6 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-009108/26 | Ostrava - Breclav | < > | Jistebník | Jistebník | 2026 | 2026 | 31 | 31 | 2026-07-29 | 21:15 | 2026-07-31 | 2:15 | 2 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-009096/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 29 | 30 | 2026-07-19 | 21:15 | 2026-07-25 | 2:15 | 6 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | zhlaví od nám. výh. č. 9 po nám. výh. č. 10,11. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-009096/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 29 | 30 | 2026-07-19 | 21:15 | 2026-07-25 | 2:15 | 6 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | záhlaví a zhlaví 2. traťové koleje směr Ostrava-Svinov, jeho část od nám. výh. č. 13,15 po náv. 2L. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-009096/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 29 | 30 | 2026-07-19 | 21:15 | 2026-07-25 | 2:15 | 6 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | záhlaví a zhlaví traťové koleje směr Odb Odra, jeho část od nám. výh. č. 2 po náv. OL. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-009096/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 29 | 30 | 2026-07-19 | 21:15 | 2026-07-25 | 2:15 | 6 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | 1.,2.,3.,3a,6. bez TV, celá jen TV. záhlaví a zhlaví 1. traťové koleje směr Ostrava-Svinov, jeho část od nám. výh. č. 8 po náv. 1L . |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-009096/26 | Ostrava - Breclav | < > | Jistebník | Studénka | 2026 | 2026 | 29 | 30 | 2026-07-19 | 21:15 | 2026-07-25 | 2:15 | 12 x 5 hours | periodical | Catenary | T | LT |  |  | X |  |  | ,X,X |  |  | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-009108/26 | Ostrava - Breclav | < > | Jistebník | Studénka | 2026 | 2026 | 31 | 31 | 2026-07-29 | 21:15 | 2026-07-31 | 2:15 | 4 x 5 hours | periodical | Catenary | T | LT |  |  | X |  |  | ,X,X |  |  | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-009103/26 | Ostrava - Breclav | < > | Jistebník | Jistebník | 2026 | 2026 | 30 | 31 | 2026-07-25 | 21:15 | 2026-07-29 | 2:15 | 4 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-009103/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 30 | 31 | 2026-07-25 | 21:15 | 2026-07-29 | 2:15 | 4 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | záhlaví a zhlaví 1. traťové koleje směr Jistebník od nám. výh. č. 19,26 po náv. 1S. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-009103/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 30 | 31 | 2026-07-25 | 21:15 | 2026-07-29 | 2:15 | 4 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | záhlaví a zhlaví 2. traťové koleje směr Jistebník, jeho část od nám. výh. č. 22,23,27,30 po náv. 2S. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-009103/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 30 | 31 | 2026-07-25 | 21:15 | 2026-07-29 | 2:15 | 4 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | 2.,7. bez TV, celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-009103/26 | Ostrava - Breclav | < > | Jistebník | Studénka | 2026 | 2026 | 30 | 31 | 2026-07-25 | 21:15 | 2026-07-29 | 2:15 | 4 x 5 hours | periodical | Catenary | T | LT |  |  | X |  |  | ,X,X |  |  | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-009103/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Jistebník | 2026 | 2026 | 30 | 31 | 2026-07-25 | 21:15 | 2026-07-29 | 2:15 | 4 x 5 hours | periodical | Catenary | T | LT |  |  | X |  |  | ,X,X |  |  | 1.,2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-009108/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 31 | 31 | 2026-07-29 | 21:15 | 2026-07-31 | 2:15 | 2 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | záhlaví a zhlaví 1. traťové koleje směr Jistebník od nám. výh. č. 19,26 po náv. 1S. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-009108/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 31 | 31 | 2026-07-29 | 21:15 | 2026-07-31 | 2:15 | 2 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | záhlaví a zhlaví 2. traťové koleje směr Jistebník, jeho část od nám. výh. č. 22,23,27,30 po náv. 2S. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-009108/26 | Ostrava - Breclav | < > | Výh Polanka n.Odrou | Výh Polanka n.Odrou | 2026 | 2026 | 31 | 31 | 2026-07-29 | 21:15 | 2026-07-31 | 2:15 | 2 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | 2.,7. bez TV, celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-009115/26 | Ostrava - Breclav | < > | Studénka | Jistebník | 2026 | 2026 | 30 | 31 | 2026-07-25 | 7:30 | 2026-07-29 | 19:30 | 4 days + 12 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-009128/26 | Ostrava - Breclav | < > | Nedakonice | Staré Město u U.H. | 2026 | 2026 | 39 | 40 | 2026-09-26 | 7:30 | 2026-09-30 | 16:30 | 4 days + 9 hours | continuous | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-009314/26 | Ostrava - Breclav | < > | Přerov přednádraží | Říkovice | 2026 | 2026 | 40 | 41 | 2026-09-29 | 8:10 | 2026-10-08 | 17:50 | 9 days + 10 hours | continuous | Switch |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-009315/26 | Ostrava - Breclav | < > | Říkovice | Přerov přednádraží | 2026 | 2026 | 41 | 42 | 2026-10-09 | 8:10 | 2026-10-18 | 17:50 | 9 days + 10 hours | continuous | Switch |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-009349/26 | Detmarovice - Cadca | < > | Český Těšín | Albrechtice u Č.T. | 2026 | 2026 | 45 | 45 | 2026-11-04 | 7:00 | 2026-11-07 | 18:00 | 3 days + 11 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-009554/26 | Ostrava - Breclav | < > | Hodonín | Holíč nad Moravou | 2026 | 2026 | 36 | 36 | 2026-09-05 | 8:00 | 2026-09-05 | 14:00 | 1 x 6 hours | periodical | Catenary | T | LT | [8 empty] | část traťové koleje bez TV, od návěstidla HS v ŽST Hodonín po státní hranici ČR/SR v km 3,009 |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-009555/26 | Ostrava - Breclav | < > | Hodonín | Rohatec | 2026 | 2026 | 37 | 38 | 2026-09-11 | 7:45 | 2026-09-18 | 13:10 | 7 days + 6 hours | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-009560/26 | Ostrava - Breclav | < > | Rohatec | Hodonín | 2026 | 2026 | 38 | 39 | 2026-09-19 | 7:45 | 2026-09-25 | 13:10 | 6 days + 6 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-009661/26 | Wroclaw - Breclav | < > | Svitavy | Březová nad Svitavou | 2026 | 2026 | 39 | 40 | 2026-09-26 | 8:40 | 2026-09-28 | 16:00 | 3 x 8 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,6,7
0054 | V-009763/26 | Wroclaw - Breclav | < > | Jablonné nad Orlicí | Letohrad | 2026 | 2026 | 20 | 20 | 2026-05-14 | 10:10 | 2026-05-14 | 11:10 | 1 x 1 hours | periodical | Others | T | LT | [8 empty] | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 4
0054 | V-015313/25 | Detmarovice - Cadca | < > | Louky nad Olší | Odb Karviná-Darkov z | 2025 | 2026 | 50 | 39 | 2025-12-14 | 0:00 | 2026-09-21 | 17:00 | 281 days + 17 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-015621/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2025 | 2026 | 50 | 18 | 2025-12-14 | 0:00 | 2026-04-30 | 18:00 | 137 days + 18 hours | continuous | Miscellaneous |  | ST |  |  | X | [5 empty] | 700.,701.,705. bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-016509/25 | Detmarovice - Cadca | < > | Albrechtice u Č.T. | Odb Chotěbuz | 2026 | 2026 | 1 | 3 | 2026-01-03 | 7:20 | 2026-01-16 | 16:00 | 3 x 9 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 5,6,7
0054 | V-016587/25 | Ostrava - Breclav | < > | Prosenice | Prosenice | 2026 | 2026 | 2 | 2 | 2026-01-07 | 8:35 | 2026-01-07 | 12:30 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-016608/25 | Ostrava - Breclav | < > | Hranice na Moravě | Drahotuše | 2026 | 2026 | 5 | 5 | 2026-01-27 | 7:30 | 2026-01-29 | 16:00 | 3 x 9 hours | periodical | Track & Rail |  | LT | [8 empty] | 4. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-016614/25 | Ostrava - Breclav | < > | Drahotuše | Hranice na Moravě | 2026 | 2026 | 4 | 4 | 2026-01-19 | 7:30 | 2026-01-21 | 16:00 | 3 x 9 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3
0054 | V-017569/25 | Wroclaw - Breclav | < > | Podivín | Břeclav přednádraží | 2026 | 2026 | 4 | 5 | 2026-01-22 | 7:10 | 2026-01-28 | 13:05 | 4 x 6 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-017571/25 | Wroclaw - Breclav | < > | Zaječí | Šakvice | 2026 | 2026 | 4 | 4 | 2026-01-19 | 7:10 | 2026-01-21 | 13:35 | 3 x 7 hours | periodical | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3
0054 | V-017655/25 | Breclav - Wien | < > | Břeclav os.n. | Lanžhot | 2026 | 2026 | 3 | 3 | 2026-01-12 | 7:00 | 2026-01-16 | 14:30 | 5 x 8 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-017681/25 | Wroclaw - Breclav | < > | Odb Parník | Česká Třebová | 2026 | 2026 | 2 | 3 | 2026-01-10 | 8:00 | 2026-01-14 | 17:00 | 5 x 9 hours | periodical | Catenary |  | LT | [8 empty] | 3. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-017688/25 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2026 | 2026 | 4 | 4 | 2026-01-22 | 8:00 | 2026-01-25 | 17:00 | 4 x 9 hours | periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 4,5,6,7
0054 | V-017695/25 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 2 | 4 | 2026-01-10 | 8:00 | 2026-01-19 | 17:00 | 10 x 9 hours | periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-017954/25 | Wroclaw - Breclav | < > | Ústí nad Orlicí | Odb Bezpráví | 2026 | 2026 | 2 | 3 | 2026-01-10 | 8:00 | 2026-01-12 | 18:00 | 3 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,6,7
0054 | V-017970/25 | Ostrava - Breclav | < > | Přerov přednádraží | Říkovice | 2026 | 2026 | 2 | 3 | 2026-01-10 | 7:00 | 2026-01-15 | 17:00 | 3 x 10 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,6
0054 | V-017973/25 | Ostrava - Breclav | < > | Říkovice | Přerov přednádraží | 2026 | 2026 | 4 | 4 | 2026-01-22 | 23:10 | 2026-01-23 | 3:30 | 1 x 5 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 4,5
0054 | V-017992/25 | Ostrava - Breclav | < > | Přerov přednádraží | Přerov přednádraží | 2026 | 2026 | 4 | 4 | 2026-01-22 | 23:10 | 2026-01-23 | 3:30 | 1 x 5 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 4,5
0054 | V-018347/25 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2026 | 2026 | 7 | 8 | 2026-02-13 | 7:10 | 2026-02-18 | 17:00 | 3 x 10 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,5
0054 | V-020478/25 | Wroclaw - Breclav | < > | Podivín | Břeclav přednádraží | 2026 | 2026 | 13 | 13 | 2026-03-24 | 7:25 | 2026-03-26 | 13:05 | 3 x 6 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. bez TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-018978/25 | Ostrava - Breclav | < > | Nedakonice | Otrokovice | 2026 | 2026 | 7 | 8 | 2026-02-09 | 7:00 | 2026-02-22 | 17:00 | 13 days + 10 hours | continuous | Miscellaneous |  | LT | [12 empty] | 2026-04-29 10:03
0054 | V-018978/25 | Ostrava - Breclav | < > | Nedakonice | Rohatec | 2026 | 2026 | 7 | 8 | 2026-02-09 | 7:00 | 2026-02-22 | 17:00 | 13 days + 10 hours | continuous | Miscellaneous |  | LT | [12 empty] | 2026-04-29 10:03
0054 | V-019062/25 | Ostrava - Breclav | < > | Výh Dluhonice | Prosenice | 2026 | 2026 | 5 | 6 | 2026-01-31 | 20:00 | 2026-02-03 | 5:00 | 4 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2S + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-019062/25 | Ostrava - Breclav | < > | Prosenice | Výh Dluhonice | 2026 | 2026 | 5 | 6 | 2026-01-31 | 20:00 | 2026-02-03 | 5:00 | 4 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1S jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-019067/25 | Ostrava - Breclav | < > | Prosenice | Výh Dluhonice | 2026 | 2026 | 6 | 6 | 2026-02-03 | 20:00 | 2026-02-06 | 5:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1S + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-019083/25 | Ostrava - Breclav | < > | Prosenice | Výh Dluhonice | 2026 | 2026 | 7 | 7 | 2026-02-09 | 20:00 | 2026-02-12 | 5:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1S + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-019083/25 | Ostrava - Breclav | < > | Přerov os.n. | Výh Dluhonice | 2026 | 2026 | 7 | 7 | 2026-02-09 | 20:00 | 2026-02-12 | 5:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-019083/25 | Ostrava - Breclav | < > | Výh Dluhonice | Přerov os.n. | 2026 | 2026 | 7 | 7 | 2026-02-09 | 20:00 | 2026-02-12 | 5:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4
0054 | V-019089/25 | Ostrava - Breclav | < > | Výh Dluhonice | Přerov os.n. | 2026 | 2026 | 7 | 7 | 2026-02-12 | 20:00 | 2026-02-15 | 5:00 | 3 x 9 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 4,5,6,7
0054 | V-019508/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 5 | 6 | 2026-02-01 | 8:00 | 2026-02-04 | 17:00 | 4 x 9 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví 4. TK směr Odbočka Parník, včetně částí kolejí číslo 13, 15 (nové značení 417, 419) od návěstidel L13, L15 (nové značení Sc417, Sc419) po návěstidlo Se474. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,7
0054 | V-019508/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 5 | 6 | 2026-01-31 | 8:00 | 2026-02-04 | 17:00 | 5 x 9 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | 11.,13.,15.,17. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-019508/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 5 | 6 | 2026-01-31 | 8:00 | 2026-02-04 | 17:00 | 5 x 9 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | 13.,15. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,6,7
0054 | V-019513/25 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 9 | 9 | 2026-02-24 | 8:00 | 2026-02-27 | 17:00 | 4 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 96.,96a + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-019513/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 9 | 9 | 2026-02-24 | 8:00 | 2026-02-27 | 17:00 | 4 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 3. jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,5
0054 | V-019519/25 | Wroclaw - Breclav | < > | Česká Třebová | Opatov | 2026 | 2026 | 6 | 6 | 2026-02-04 | 23:00 | 2026-02-08 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-019519/25 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 6 | 6 | 2026-02-04 | 23:00 | 2026-02-08 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 96.,96a jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-019519/25 | Wroclaw - Breclav | < > | Opatov | Česká Třebová | 2026 | 2026 | 6 | 6 | 2026-02-04 | 23:00 | 2026-02-08 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-019519/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 6 | 6 | 2026-02-04 | 23:00 | 2026-02-08 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-019519/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 6 | 6 | 2026-02-04 | 23:00 | 2026-02-08 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 3. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6,7
0054 | V-019523/25 | Wroclaw - Breclav | < > | Česká Třebová | Opatov | 2026 | 2026 | 6 | 7 | 2026-02-08 | 23:00 | 2026-02-11 | 4:30 | 3 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,7
0054 | V-019523/25 | Wroclaw - Breclav | < > | Odb Zádulka | Odb Zádulka | 2026 | 2026 | 6 | 7 | 2026-02-08 | 23:00 | 2026-02-11 | 4:30 | 3 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [9 empty] | 2026-04-29 10:03 |  | 1,2,3,7
0054 | V-019526/25 | Wroclaw - Breclav | < > | Opatov | Česká Třebová | 2026 | 2026 | 9 | 9 | 2026-02-23 | 23:00 | 2026-02-25 | 4:30 | 2 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3
0054 | V-019526/25 | Wroclaw - Breclav | < > | Odb Zádulka | Odb Zádulka | 2026 | 2026 | 9 | 9 | 2026-02-23 | 23:00 | 2026-02-25 | 4:30 | 2 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [9 empty] | 2026-04-29 10:03 |  | 1,2,3
0054 | V-019528/25 | Wroclaw - Breclav | < > | Česká Třebová | Opatov | 2026 | 2026 | 9 | 9 | 2026-02-26 | 8:00 | 2026-03-01 | 17:00 | 4 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 4,5,6,7
0054 | V-019528/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 9 | 9 | 2026-02-26 | 8:00 | 2026-03-01 | 17:00 | 4 x 9 hours | periodical | Miscellaneous |  | LT | [8 empty] | 3. bez TV. |  |  |  | 2026-04-29 10:03 |  | 4,5,6,7
0054 | V-019814/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 2 | 3 | 2026-01-10 | 23:15 | 2026-01-13 | 4:45 | 3 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví 1. TK směr Odbočka Zádulka, včetně části koleje číslo 5 od návěstidla S5 po návěstidlo Se1. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-019814/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 2 | 3 | 2026-01-10 | 23:15 | 2026-01-13 | 4:45 | 3 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | záhlaví 2. TK směr Odbočka Zádulka, jeho část od návěstidla ZL po návěstidlo Se21 |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-019814/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 2 | 3 | 2026-01-10 | 23:15 | 2026-01-13 | 4:45 | 3 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | záhlaví 2. TK směr Třebovice v Čechách, jeho část od návěstidla L po návěstidlo Se754 |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-019814/25 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2026 | 2026 | 2 | 3 | 2026-01-10 | 23:15 | 2026-01-13 | 4:45 | 6 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-019814/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 2 | 3 | 2026-01-10 | 23:15 | 2026-01-15 | 4:45 | 5 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | 1.,2.,3a,4a,5.,6.,7.,8.,9.,9c,12.,14.,16.,18. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,6,7
0054 | V-019817/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 3 | 3 | 2026-01-13 | 23:15 | 2026-01-15 | 4:45 | 2 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | záhlaví 1. TK směr Odbočka Zádulka, jeho část od návěstidla 1ZL po návěstidlo Se16 |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-019817/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 3 | 3 | 2026-01-13 | 23:15 | 2026-01-15 | 4:45 | 2 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | záhlaví 1. TK směr Třebovice v Čechách, jeho část od návěstidla 1L po návěstidlo Se17 |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-019817/25 | Wroclaw - Breclav | < > | Česká Třebová | Třebovice v Čechách | 2026 | 2026 | 3 | 3 | 2026-01-13 | 23:15 | 2026-01-15 | 4:45 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4
0054 | V-019822/25 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 4 | 5 | 2026-01-25 | 23:00 | 2026-01-26 | 4:30 | 1 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,7
0054 | V-019822/25 | Wroclaw - Breclav | < > | Odb Zádulka | Česká Třebová | 2026 | 2026 | 4 | 5 | 2026-01-25 | 23:00 | 2026-01-26 | 4:30 | 1 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,7
0054 | V-019823/25 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 5 | 5 | 2026-01-26 | 23:00 | 2026-01-30 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-019823/25 | Wroclaw - Breclav | < > | Č.Třebová vjezd.sk. | Česká Třebová | 2026 | 2026 | 5 | 5 | 2026-01-26 | 23:00 | 2026-01-30 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 96.,96a jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-019823/25 | Wroclaw - Breclav | < > | Odb Zádulka | Česká Třebová | 2026 | 2026 | 5 | 5 | 2026-01-26 | 23:00 | 2026-01-30 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 2. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-019823/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 5 | 5 | 2026-01-26 | 23:00 | 2026-01-30 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 3. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-019823/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 5 | 5 | 2026-01-26 | 23:00 | 2026-01-30 | 4:30 | 4 x 6 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-019831/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 5 | 5 | 2026-01-31 | 8:00 | 2026-01-31 | 17:00 | 1 x 9 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví 4. TK směr Odbočka Parník, včetně částí kolejí číslo 13, 15 od návěstidel L13, L15 po návěstidlo Se474. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-019882/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2026 | 2026 | 11 | 11 | 2026-03-14 | 7:30 | 2026-03-14 | 16:30 | 1 x 9 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 8. + TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-019891/25 | Wroclaw - Breclav | < > | Brno-Maloměřice St.6 | Odb Svitava | 2026 | 2026 | 13 | 13 | 2026-03-28 | 9:25 | 2026-03-29 | 11:40 | 3 x 3 hours | periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 6,7
0054 | V-019893/25 | Wroclaw - Breclav | < > | Adamov | Adamov | 2026 | 2026 | 11 | 11 | 2026-03-09 | 23:45 | 2026-03-10 | 4:30 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-021929/25 | Ostrava - Breclav | < > | Moravský Písek | Moravský Písek | 2026 | 2026 | 16 | 18 | 2026-04-18 | 22:20 | 2026-04-30 | 4:15 | 3 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 2,3,4,6,7
0054 | V-019916/25 | Ostrava - Breclav | < > | Tlumačov | Tlumačov | 2026 | 2026 | 12 | 12 | 2026-03-21 | 8:15 | 2026-03-21 | 12:00 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-019921/25 | Ostrava - Breclav | < > | Nedakonice | Nedakonice | 2026 | 2026 | 13 | 13 | 2026-03-28 | 8:00 | 2026-03-28 | 12:00 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-021863/25 | Ostrava - Breclav | < > | Říkovice | Říkovice | 2026 | 2026 | 16 | 16 | 2026-04-18 | 8:20 | 2026-04-18 | 12:30 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-020037/25 | Ostrava - Breclav | < > | Ostrava-Svinov | Výh Polanka n.Odrou | 2026 | 2026 | 11 | 12 | 2026-03-14 | 7:30 | 2026-03-17 | 19:00 | 3 days + 12 hours | continuous | Switch |  | LT | [8 empty] | 2. bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-020153/25 | Detmarovice - Cadca | < > | Louky nad Olší | Odb Karviná-Darkov z | 2026 | 2026 | 13 | 13 | 2026-03-23 | 7:15 | 2026-03-27 | 17:00 | 5 x 10 hours | periodical | Track & Rail |  | LT | [8 empty] | 0. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-020153/25 | Detmarovice - Cadca | < > | Odb Karviná-Darkov z | Louky nad Olší | 2026 | 2026 | 13 | 13 | 2026-03-23 | 7:15 | 2026-03-27 | 17:00 | 5 x 10 hours | periodical | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-020532/25 | Wroclaw - Breclav | < > | Odb Rajhrad | Hrušovany u Brna | 2026 | 2026 | 10 | 11 | 2026-03-05 | 9:00 | 2026-03-13 | 13:20 | 4 x 5 hours | periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 4,5
0054 | V-020534/25 | Wroclaw - Breclav | < > | Hrušovany u Brna | Odb Rajhrad | 2026 | 2026 | 10 | 11 | 2026-03-03 | 9:00 | 2026-03-11 | 13:20 | 4 x 5 hours | periodical | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 2,3
0054 | V-021084/25 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 13 | 13 | 2026-03-28 | 0:20 | 2026-03-28 | 4:20 | 2 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-021141/25 | Wroclaw - Breclav | < > | Česká Třebová | Odb Zádulka | 2026 | 2026 | 10 | 14 | 2026-03-08 | 8:00 | 2026-03-31 | 18:00 | 9 x 10 hours | periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,6,7
0054 | V-021165/25 | Ostrava - Breclav | < > | Přerov přednádraží | Přerov přednádraží | 2026 | 2026 | 11 | 12 | 2026-03-15 | 22:20 | 2026-03-19 | 4:00 | 4 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X |  |  | ,X,X |  |  | zhlaví směr Věžky - od námezníku výh. 106 po návěstidlo Se113. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,7
0054 | V-021165/25 | Ostrava - Breclav | < > | Přerov přednádraží | Přerov přednádraží | 2026 | 2026 | 11 | 12 | 2026-03-15 | 22:20 | 2026-03-19 | 4:00 | 4 x 6 hours | periodical | Miscellaneous |  | ST |  |  | X |  |  | ,X,X |  |  | 102.,106.,108. bez TV, 101.,102.,103.,104.,106.,108. jen TV. zhlaví směr Říkovice - od námezníku výh. 108 po námezník výh. 128. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,7
0054 | V-021385/25 | Wroclaw - Breclav | < > | Jablonné nad Orlicí | Letohrad | 2026 | 2026 | 12 | 12 | 2026-03-16 | 9:10 | 2026-03-20 | 17:00 | 19 x 8 hours | periodical | Track & Rail | T | LT | [5 empty] | ,X,X |  |  | traťová + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-021385/25 | Wroclaw - Breclav | < > | Lichkov | Lichkov st.hr. | 2026 | 2026 | 12 | 12 | 2026-03-16 | 9:10 | 2026-03-20 | 17:00 | 5 x 8 hours | periodical | Track & Rail | T | LT | [5 empty] | ,X,X |  |  | traťová jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5
0054 | V-021529/25 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 13 | 17 | 2026-03-26 | 7:00 | 2026-04-23 | 15:00 | 28 days + 8 hours | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-021680/25 | Detmarovice - Cadca | < > | Český Těšín | Český Těšín | 2026 | 2026 | 16 | 16 | 2026-04-18 | 7:00 | 2026-04-18 | 17:00 | 1 x 10 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 100.,102.-124.,104a,110a,101a,101.-103. jen TV, 105.,107. + TV. zhlaví ze směr Třinec od nám. výh. č. 122, 129 po nám. výh. č. 114. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-021682/25 | Detmarovice - Cadca | < > | Karviná hl.n. | Odb Karviná-Darkov z | 2026 | 2026 | 17 | 17 | 2026-04-22 | 7:15 | 2026-04-24 | 17:00 | 6 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-021685/25 | Detmarovice - Cadca | < > | Karviná hl.n. | Odb Karviná-Darkov z | 2026 | 2026 | 17 | 18 | 2026-04-26 | 7:15 | 2026-04-27 | 17:00 | 4 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,7
0054 | V-021704/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 13 | 14 | 2026-03-28 | 8:00 | 2026-03-31 | 17:00 | 4 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví střední, jeho část od námezníku výhybky číslo 277 po námezník výhybky číslo 285XB. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-021704/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 13 | 14 | 2026-03-28 | 8:00 | 2026-03-31 | 17:00 | 4 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 214. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-021704/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 13 | 14 | 2026-03-28 | 8:00 | 2026-03-31 | 17:00 | 4 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 97. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-021704/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 13 | 14 | 2026-03-28 | 8:00 | 2026-03-31 | 17:00 | 4 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 211.-222. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-021708/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 14 | 14 | 2026-04-01 | 8:00 | 2026-04-01 | 17:00 | 1 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví střední, jeho část od námezníku výhybky číslo 277 po námezník výhybky číslo 285XB. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-021708/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 14 | 14 | 2026-04-01 | 8:00 | 2026-04-01 | 17:00 | 1 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 97. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-021708/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 14 | 14 | 2026-04-01 | 8:00 | 2026-04-01 | 17:00 | 1 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 214. bez TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-021708/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 14 | 14 | 2026-04-01 | 8:00 | 2026-04-01 | 17:00 | 1 x 9 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 211.-222. jen TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-021791/25 | Detmarovice - Cadca | < > | Albrechtice u Č.T. | Odb Chotěbuz | 2026 | 2026 | 14 | 15 | 2026-04-01 | 8:30 | 2026-04-12 | 15:00 | 11 days + 7 hours | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-021792/25 | Detmarovice - Cadca | < > | Český Těšín | Albrechtice u Č.T. | 2026 | 2026 | 15 | 17 | 2026-04-12 | 15:00 | 2026-04-23 | 18:00 | 11 days + 3 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-021870/25 | Ostrava - Breclav | < > | Napajedla | Napajedla | 2026 | 2026 | 17 | 17 | 2026-04-25 | 8:10 | 2026-04-25 | 12:00 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-023091/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 16 | 16 | 2026-04-13 | 7:30 | 2026-04-13 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | výh.: 302 (staré značení, nové značení 401). |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023092/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 17 | 17 | 2026-04-20 | 7:30 | 2026-04-20 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | výh.: 302 (staré značení, nové značení 401). |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023091/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 16 | 16 | 2026-04-13 | 7:30 | 2026-04-13 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | 230.,231. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023092/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 17 | 17 | 2026-04-20 | 7:30 | 2026-04-20 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | 230.,231. bez TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023091/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 16 | 16 | 2026-04-13 | 7:30 | 2026-04-13 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví střední od hrotů jazyků výhybky číslo 250 po námezníky výhybek číslo 253, 254, 255, 256. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023092/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 17 | 17 | 2026-04-20 | 7:30 | 2026-04-20 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví střední od hrotů jazyků výhybky číslo 250 po námezníky výhybek číslo 253, 254, 255, 256. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023091/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 16 | 16 | 2026-04-13 | 7:30 | 2026-04-13 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví střední od návěstidel Sp1, Sp2 po námezníky výhybek číslo 225, 226, 233, 234, 235, 236, 243, 244, 245, 246. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023092/25 | Wroclaw - Breclav | < > | Česká Třebová | Česká Třebová | 2026 | 2026 | 17 | 17 | 2026-04-20 | 7:30 | 2026-04-20 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X | [5 empty] | zhlaví střední od návěstidel Sp1, Sp2 po námezníky výhybek číslo 225, 226, 233, 234, 235, 236, 243, 244, 245, 246. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023091/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 16 | 16 | 2026-04-13 | 7:30 | 2026-04-13 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023092/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 17 | 17 | 2026-04-20 | 7:30 | 2026-04-20 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023091/25 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 16 | 16 | 2026-04-13 | 7:30 | 2026-04-13 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 97. + TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023092/25 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová vjezd.sk. | 2026 | 2026 | 17 | 17 | 2026-04-20 | 7:30 | 2026-04-20 | 15:00 | 1 x 8 hours | periodical | Miscellaneous |  | LT |  |  | X | [5 empty] | 97. + TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023097/25 | Wroclaw - Breclav | < > | Česká Třebová | Č.Třebová kol.96,96a | 2026 | 2026 | 15 | 20 | 2026-04-08 | 9:00 | 2026-05-13 | 19:00 | 35 days + 10 hours | continuous | Miscellaneous |  | LT | [8 empty] | 96.,96a + TV. |  |  |  | 2026-04-29 10:03
0054 | V-023097/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 15 | 20 | 2026-04-08 | 9:00 | 2026-05-13 | 19:00 | 35 days + 10 hours | continuous | Miscellaneous |  | LT | [8 empty] | 3. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-023101/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 18 | 20 | 2026-04-27 | 8:00 | 2026-05-13 | 19:00 | 16 days + 11 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-023305/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2026 | 2026 | 13 | 15 | 2026-03-23 | 8:00 | 2026-04-07 | 18:00 | 15 days + 10 hours | continuous | Miscellaneous |  | LT | [8 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-023416/25 | Wroclaw - Breclav | < > | Brno-Maloměřice St.6 | Odb Svitava | 2026 | 2026 | 21 | 21 | 2026-05-21 | 23:45 | 2026-05-22 | 3:05 | 2 x 4 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 4,5
0054 | V-023480/25 | Breclav - Wien | < > | Lanžhot st.hr. | Břeclav os.n. | 2026 | 2026 | 20 | 20 | 2026-05-11 | 8:00 | 2026-05-12 | 13:30 | 8 x 6 hours | periodical | Catenary |  | LT | [12 empty] | 2026-04-29 10:03 |  | 1,2
0054 | V-023482/25 | Breclav - Wien | < > | Lanžhot st.hr. | Břeclav os.n. | 2026 | 2026 | 20 | 20 | 2026-05-13 | 8:00 | 2026-05-14 | 13:30 | 8 x 6 hours | periodical | Catenary |  | LT | [12 empty] | 2026-04-29 10:03 |  | 3,4
0054 | V-023550/25 | Ostrava - Breclav | < > | Huštěnovice | Huštěnovice | 2026 | 2026 | 21 | 21 | 2026-05-18 | 8:35 | 2026-05-18 | 12:25 | 1 x 4 hours | periodical | Catenary |  | ST |  |  | X |  |  | ,X,X |  |  | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023571/25 | Detmarovice - Cadca | < > | Třinec | Třinec | 2026 | 2026 | 19 | 19 | 2026-05-06 | 7:40 | 2026-05-06 | 13:00 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví směr Bystřice od nám. výh. č. 7 po nám. výh. č. 11. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-023571/25 | Detmarovice - Cadca | < > | Třinec | Třinec | 2026 | 2026 | 19 | 19 | 2026-05-06 | 7:40 | 2026-05-06 | 13:00 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1b,3.,3a,5.,5a,5b,7.,9.,11.,13.,13a,15. jen TV, 1.,1a + TV. záhlaví a zhlaví 1. traťové koleje směr Bystřice, jeho část od náv. 1L po hrot výh. č. 2. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-023571/25 | Detmarovice - Cadca | < > | Třinec | Bystřice | 2026 | 2026 | 19 | 19 | 2026-05-06 | 7:40 | 2026-05-06 | 13:00 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3
0054 | V-023573/25 | Detmarovice - Cadca | < > | Třinec | Třinec | 2026 | 2026 | 22 | 22 | 2026-05-25 | 7:40 | 2026-05-25 | 13:00 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví směr Český Těšín od náv. Sc1c po náv. Se31. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023573/25 | Detmarovice - Cadca | < > | Třinec | Třinec | 2026 | 2026 | 22 | 22 | 2026-05-25 | 7:40 | 2026-05-25 | 13:00 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | zhlaví směr Český Těšín od nám. výh. č. 39 po nám. výh. č. 31. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023573/25 | Detmarovice - Cadca | < > | Třinec | Třinec | 2026 | 2026 | 22 | 22 | 2026-05-25 | 7:40 | 2026-05-25 | 13:00 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1.,1b,1c,1d + TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023573/25 | Detmarovice - Cadca | < > | Třinec | Třinec | 2026 | 2026 | 22 | 22 | 2026-05-25 | 7:40 | 2026-05-25 | 13:00 | 1 x 6 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1a,3.,3a,5.,5a,5b,7.,9.,11.,13.,13a,15.,301. jen TV. záhlaví a zhlaví 1. traťové koleje směr Český Těšín od náv. 1S po náv. L1d. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023573/25 | Detmarovice - Cadca | < > | Český Těšín | Třinec | 2026 | 2026 | 22 | 22 | 2026-05-25 | 7:40 | 2026-05-25 | 13:00 | 1 x 6 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1
0054 | V-023608/25 | Ostrava - Breclav | < > | Hodonín | Hodonín | 2026 | 2026 | 20 | 20 | 2026-05-11 | 23:50 | 2026-05-12 | 4:00 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-023609/25 | Ostrava - Breclav | < > | Lužice | Lužice | 2026 | 2026 | 20 | 21 | 2026-05-17 | 23:40 | 2026-05-18 | 4:05 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,7
0054 | V-023611/25 | Ostrava - Breclav | < > | Moravská Nová Ves | Moravská Nová Ves | 2026 | 2026 | 22 | 22 | 2026-05-25 | 23:35 | 2026-05-26 | 4:10 | 1 x 5 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  | 2026-04-29 10:03 |  | 1,2
0054 | V-023730/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2026 | 2026 | 18 | 18 | 2026-05-01 | 7:30 | 2026-05-01 | 15:30 | 1 x 8 hours | periodical | Track & Rail |  | LT |  |  | X | [5 empty] | 6. jen TV. |  |  |  | 2026-04-29 10:03 |  | 5
0054 | V-023733/25 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 18 | 18 | 2026-05-02 | 7:30 | 2026-05-02 | 15:30 | 1 x 8 hours | periodical | Track & Rail |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03 |  | 6
0054 | V-005435/25 | Breclav - Wien | < > | Břeclav os.n. | Boří les | 2026 | 2026 | 6 | 6 | 2026-02-03 | 7:50 | 2026-02-03 | 13:15 | 1 x 6 hours | periodical | Track & Rail | T | LT | [5 empty] | ,X,X |  |  | traťová bez TV. |  |  |  | 2026-04-29 10:03 |  | 2
0054 | V-003316/25 | Ostrava - Breclav | < > | Moravský Písek | Nedakonice | 2026 | 2026 | 15 | 16 | 2026-04-12 | 15:30 | 2026-04-16 | 15:30 | 4 days + 0 hours | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-003317/25 | Ostrava - Breclav | < > | Nedakonice | Moravský Písek | 2026 | 2026 | 15 | 15 | 2026-04-07 | 7:15 | 2026-04-12 | 15:30 | 5 days + 9 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-003488/25 | Wroclaw - Breclav | < > | Odb Zádulka | Opatov | 2026 | 2026 | 24 | 24 | 2026-06-10 | 7:00 | 2026-06-11 | 19:00 | 1 days + 12 hours | continuous | Switch |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-003491/25 | Wroclaw - Breclav | < > | Opatov | Odb Zádulka | 2026 | 2026 | 24 | 24 | 2026-06-08 | 7:00 | 2026-06-09 | 19:00 | 1 days + 12 hours | continuous | Switch |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-003846/25 | Wroclaw - Breclav | < > | Skalice nad Svitavou | Rájec-Jestřebí | 2026 | 2026 | 15 | 19 | 2026-04-07 | 9:30 | 2026-05-10 | 17:30 | 33 days + 8 hours | continuous | Track & Rail |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-004047/24 | Ostrava - Breclav | < > | Moravský Písek | Nedakonice | 2026 | 2026 | 28 | 29 | 2026-07-07 | 7:20 | 2026-07-14 | 13:30 | 7 days + 7 hours | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-004048/24 | Ostrava - Breclav | < > | Nedakonice | Moravský Písek | 2026 | 2026 | 30 | 31 | 2026-07-21 | 13:30 | 2026-07-29 | 13:30 | 8 days + 0 hours | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-004053/24 | Ostrava - Breclav | < > | Bzenec přívoz | Moravský Písek | 2026 | 2026 | 31 | 32 | 2026-07-30 | 7:20 | 2026-08-06 | 14:35 | 7 days + 8 hours | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-004278/25 | Ostrava - Breclav | < > | Rohatec | Hodonín | 2026 | 2026 | 32 | 32 | 2026-08-05 | 20:30 | 2026-08-07 | 2:30 | 2 x 6 hours | periodical | Others | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5
0054 | V-004305/25 | Breclav - Wien | < > | Břeclav os.n. | Boří les | 2026 | 2026 | 16 | 18 | 2026-04-13 | 7:50 | 2026-04-30 | 12:00 | 17 days + 5 hours | continuous | Bridge | T | LT | [5 empty] | ,X,X |  |  | traťová bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-004366/25 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 6 | 9 | 2026-02-05 | 7:30 | 2026-02-24 | 19:30 | 19 days + 12 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-004366/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2026 | 2026 | 6 | 9 | 2026-02-05 | 7:30 | 2026-02-24 | 19:30 | 19 days + 12 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 6. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-005231/24 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 6 | 6 | 2026-02-04 | 0:20 | 2026-02-07 | 4:20 | 8 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6
0054 | V-005235/24 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 8 | 9 | 2026-02-21 | 0:20 | 2026-02-24 | 4:20 | 8 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,6,7
0054 | V-005239/24 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 9 | 9 | 2026-02-25 | 0:20 | 2026-02-28 | 4:20 | 8 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03 |  | 3,4,5,6
0054 | V-008443/25 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 9 | 9 | 2026-02-25 | 7:30 | 2026-02-26 | 19:30 | 1 days + 12 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. bez TV. |  |  |  | 2026-04-29 10:03
0054 | V-008443/25 | Wroclaw - Breclav | < > | Brno-Maloměřice | Odb Brno-Židenice z | 2026 | 2026 | 9 | 9 | 2026-02-25 | 7:30 | 2026-02-26 | 19:30 | 1 days + 12 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. jen TV. |  |  |  | 2026-04-29 10:03
0054 | V-009145/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2026 | 2026 | 9 | 9 | 2026-02-27 | 7:30 | 2026-02-28 | 19:30 | 1 days + 12 hours | continuous | Catenary |  | LT |  |  | X | [5 empty] | 6. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-012815/25 | Wroclaw - Breclav | < > | Skalice nad Svitavou | Rájec-Jestřebí | 2026 | 2026 | 14 | 14 | 2026-03-30 | 9:30 | 2026-04-02 | 17:30 | 3 days + 8 hours | continuous | Track & Rail |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-017125/24 | Ostrava - Breclav | < > | Rohatec | Hodonín | 2026 | 2026 | 14 | 15 | 2026-04-03 | 4:25 | 2026-04-06 | 4:25 | 3 days + 0 hours | continuous | Others | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-018423/23 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 3 | 4 | 2026-01-14 | 0:20 | 2026-01-25 | 4:20 | 24 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,2,3,4,5,6,7
0054 | V-018467/23 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 5 | 7 | 2026-02-01 | 7:00 | 2026-02-12 | 17:00 | 11 days + 10 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-018467/23 | Ostrava - Breclav | < > | Odb Jezernice A | Drahotuše | 2026 | 2026 | 5 | 7 | 2026-02-01 | 7:00 | 2026-02-12 | 17:00 | 11 days + 10 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-018468/23 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2026 | 2026 | 6 | 7 | 2026-02-07 | 22:30 | 2026-02-09 | 4:30 | 4 x 6 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03 |  | 1,6,7
0054 | V-018470/23 | Ostrava - Breclav | < > | Odb Jezernice B | Lipník nad Bečvou | 2026 | 2026 | 7 | 28 | 2026-02-13 | 7:00 | 2026-07-09 | 17:00 | 146 days + 10 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-018471/23 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2026 | 2026 | 28 | 29 | 2026-07-09 | 17:00 | 2026-07-17 | 19:00 | 8 days + 2 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-018471/23 | Ostrava - Breclav | < > | Odb Jezernice A | Drahotuše | 2026 | 2026 | 28 | 29 | 2026-07-09 | 17:00 | 2026-07-17 | 19:00 | 8 days + 2 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-018473/23 | Ostrava - Breclav | < > | Odb Jezernice A | Drahotuše | 2026 | 2026 | 35 | 39 | 2026-08-26 | 7:00 | 2026-09-23 | 15:00 | 28 days + 8 hours | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:03
0054 | V-016656/24 | Ostrava - Breclav | < > | Suchdol nad Odrou | Polom | 2027 | 2027 | 28 | 38 | 2027-07-12 | 0:00 | 2027-09-26 | 23:59 | 77 x 8 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6,7
0054 | V-016601/25 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2027 | 2027 | 36 | 38 | 2027-09-12 | 0:00 | 2027-09-24 | 23:59 | 13 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016599/25 | Ostrava - Breclav | < > | Lipník nad Bečvou | Odb Jezernice B | 2027 | 2027 | 35 | 36 | 2027-09-01 | 0:00 | 2027-09-12 | 23:59 | 12 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016207/25 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2027 | 2027 | 32 | 33 | 2027-08-09 | 0:00 | 2027-08-16 | 23:59 | 8 days | continuous | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016206/25 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2027 | 2027 | 31 | 32 | 2027-08-02 | 0:00 | 2027-08-09 | 23:59 | 8 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016018/25 | Ostrava - Breclav | < > | Tlumačov | Otrokovice | 2027 | 2027 | 12 | 12 | 2027-03-22 | 0:00 | 2027-03-24 | 23:59 | 3 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016017/25 | Ostrava - Breclav | < > | Otrokovice | Tlumačov | 2027 | 2027 | 11 | 11 | 2027-03-19 | 0:00 | 2027-03-21 | 23:59 | 3 days | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016016/25 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2027 | 2027 | 21 | 21 | 2027-05-24 | 0:00 | 2027-05-26 | 23:59 | 3 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016015/25 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2027 | 2027 | 20 | 20 | 2027-05-21 | 0:00 | 2027-05-23 | 23:59 | 3 days | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016014/25 | Ostrava - Breclav | < > | Hulín | Tlumačov | 2027 | 2027 | 19 | 20 | 2027-05-11 | 0:00 | 2027-05-20 | 23:59 | 10 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-016013/25 | Ostrava - Breclav | < > | Tlumačov | Hulín | 2027 | 2027 | 17 | 19 | 2027-05-01 | 0:00 | 2027-05-10 | 23:59 | 10 days | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-015925/24 | Ostrava - Breclav | < > | Studénka | Suchdol nad Odrou | 2027 | 2027 | 22 | 26 | 2027-06-01 | 0:00 | 2027-06-30 | 23:59 | 30 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-015924/24 | Ostrava - Breclav | < > | Suchdol nad Odrou | Studénka | 2027 | 2027 | 18 | 22 | 2027-05-03 | 0:00 | 2027-06-01 | 23:59 | 30 days | continuous | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-015331/24 | Ostrava - Breclav | < > | Lipník nad Bečvou | Prosenice | 2027 | 2027 | 40 | 43 | 2027-10-10 | 0:00 | 2027-10-26 | 23:59 | 17 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-015330/24 | Ostrava - Breclav | < > | Prosenice | Lipník nad Bečvou | 2027 | 2027 | 38 | 40 | 2027-09-25 | 0:00 | 2027-10-10 | 23:59 | 16 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-008786/26 | Ostrava - Breclav | < > | Drahotuše | Odb Jezernice A | 2027 | 2027 | 2 | 2 | 2027-01-11 | 18:00 | 2027-01-12 | 6:00 | 2 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | zab. zař. TZZ TK 1.,2.. |  |  |  | 2026-04-29 10:06 |  | 1,2
0054 | V-004881/26 | Ostrava - Breclav | < > | Lužice | Moravská Nová Ves | 2027 | 2027 | 9 | 9 | 2027-03-01 | 0:00 | 2027-03-06 | 23:59 | 6 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6
0054 | V-004887/26 | Ostrava - Breclav | < > | Moravská Nová Ves | Lužice | 2027 | 2027 | 9 | 10 | 2027-03-07 | 0:00 | 2027-03-12 | 23:59 | 6 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,7
0054 | V-006593/26 | Ostrava - Breclav | < > | Břeclav os.n. | Břeclav os.n. | 2027 | 2027 | 13 | 13 | 2027-04-04 | 0:00 | 2027-04-04 | 23:59 | 1 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 3.,3a,3b,3c,3d,3e,5.,5a,5b,5c,7.,7a,7b,7c,7d,9a,11.,11a,13.,509. jen TV. záhlaví 1. traťové koleje směr Bernhadsthal |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-006005/25 | Ostrava - Breclav | < > | Drahotuše | Lipník nad Bečvou | 2027 | 2027 | 9 | 10 | 2027-03-06 | 0:00 | 2027-03-10 | 23:59 | 5 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2 + TV. |  |  |  | 2026-04-29 10:06
0054 | V-006004/25 | Ostrava - Breclav | < > | Lipník nad Bečvou | Drahotuše | 2027 | 2027 | 9 | 9 | 2027-03-01 | 0:00 | 2027-03-05 | 23:59 | 5 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1 + TV. |  |  |  | 2026-04-29 10:06
0054 | V-004810/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2027 | 2028 | 50 | 52 | 2027-12-15 | 18:00 | 2028-01-01 | 6:00 | 17 x 1 hours | periodical | Bridge | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6,7
0054 | V-005135/26 | Ostrava - Breclav | < > | Moravská Nová Ves | Lužice | 2027 | 2027 | 15 | 16 | 2027-04-18 | 18:00 | 2027-04-19 | 6:00 | 1 x 6 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,7
0054 | V-004927/26 | Ostrava - Breclav | < > | Břeclav přednádraží | Břeclav přednádraží | 2027 | 2027 | 9 | 9 | 2027-03-07 | 0:00 | 2027-03-07 | 23:59 | 1 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | sudá jen TV. |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-005085/26 | Ostrava - Breclav | < > | Břeclav os.n. | Břeclav os.n. | 2027 | 2027 | 11 | 11 | 2027-03-21 | 0:00 | 2027-03-21 | 23:59 | 2 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | sudá jen TV. |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-004930/26 | Ostrava - Breclav | < > | Břeclav přednádraží | Výh Hrušky | 2027 | 2027 | 10 | 10 | 2027-03-14 | 0:00 | 2027-03-14 | 23:59 | 1 x 8 hours | periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-004930/26 | Ostrava - Breclav | < > | Břeclav přednádraží | Břeclav přednádraží | 2027 | 2027 | 10 | 10 | 2027-03-14 | 0:00 | 2027-03-14 | 23:59 | 1 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 202.,202a,204.,204a,204b,206.,208.,210.,212.,214.,216.,218.,418.,420a,420b,420c jen TV. |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-004930/26 | Ostrava - Breclav | < > | Břeclav přednádraží | Břeclav přednádraží | 2027 | 2027 | 10 | 10 | 2027-03-14 | 0:00 | 2027-03-14 | 23:59 | 1 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | záhlaví 1. traťové koleje směr Hrušky, jeho část od návěstidla Se249 po návěstidlo 1HS |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-004928/26 | Ostrava - Breclav | < > | Břeclav os.n. | Břeclav os.n. | 2027 | 2027 | 9 | 9 | 2027-03-06 | 0:00 | 2027-03-06 | 23:59 | 2 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | lichá jen TV. |  |  |  | 2026-04-29 10:06 |  | 6
0054 | V-004927/26 | Ostrava - Breclav | < > | Břeclav přednádraží | Břeclav přednádraží | 2027 | 2027 | 9 | 9 | 2027-03-07 | 0:00 | 2027-03-07 | 23:59 | 1 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 201 jen TV. |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-004925/26 | Ostrava - Breclav | < > | Břeclav os.n. | Břeclav os.n. | 2027 | 2027 | 11 | 11 | 2027-03-21 | 0:00 | 2027-03-21 | 23:59 | 1 x 8 hours | periodical | Catenary |  | ST |  |  | X | [5 empty] | 1.,1a,1b,3.,3a,3b,3c,3d,3e,5.,5a,5b,5c,7.,7a,7b,7c,7d,9a,11.,11a,13.,509. jen TV. |  |  |  | 2026-04-29 10:06 |  | 7
0054 | V-004729/26 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2027 | 2027 | 50 | 52 | 2027-12-15 | 0:00 | 2027-12-31 | 23:59 | 17 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-004546/26 | Ostrava - Breclav | < > | Jistebník | Studénka | 2027 | 2027 | 33 | 33 | 2027-08-18 | 18:00 | 2027-08-19 | 6:00 | 1 x 6 hours | periodical | Catenary | T | LT | [5 empty] | ,X,X |  |  | 1.,2. + TV. |  |  |  | 2026-04-29 10:06 |  | 3,4
0054 | V-004527/26 | Ostrava - Breclav | < > | Studénka | Jistebník | 2027 | 2027 | 27 | 28 | 2027-07-10 | 0:00 | 2027-07-15 | 23:59 | 6 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,6,7
0054 | V-004519/26 | Ostrava - Breclav | < > | Jistebník | Studénka | 2027 | 2027 | 26 | 27 | 2027-07-04 | 0:00 | 2027-07-09 | 23:59 | 6 x 10 hours | periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,7
0054 | V-003178/26 | Ostrava - Breclav | < > | Prosenice | Lipník nad Bečvou | 2027 | 2027 | 43 | 44 | 2027-10-27 | 18:00 | 2027-11-02 | 6:00 | 6 x 4 hours | periodical | Bridge | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6,7
0054 | V-003178/26 | Ostrava - Breclav | < > | Lipník nad Bečvou | Prosenice | 2027 | 2027 | 43 | 44 | 2027-10-27 | 18:00 | 2027-11-02 | 6:00 | 6 x 4 hours | periodical | Bridge | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6,7
0054 | V-003172/26 | Ostrava - Breclav | < > | Prosenice | Lipník nad Bečvou | 2027 | 2027 | 34 | 35 | 2027-08-25 | 18:00 | 2027-08-31 | 6:00 | 6 x 4 hours | periodical | Bridge | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6,7
0054 | V-003172/26 | Ostrava - Breclav | < > | Lipník nad Bečvou | Prosenice | 2027 | 2027 | 34 | 35 | 2027-08-25 | 18:00 | 2027-08-31 | 6:00 | 6 x 4 hours | periodical | Bridge | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:06 |  | 1,2,3,4,5,6,7
0054 | V-003169/26 | Ostrava - Breclav | < > | Prosenice | Lipník nad Bečvou | 2027 | 2027 | 38 | 40 | 2027-09-21 | 0:00 | 2027-10-08 | 23:59 | 18 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-003009/26 | Ostrava - Breclav | < > | Huštěnovice | Staré Město u U.H. | 2027 | 2027 | 21 | 21 | 2027-05-24 | 0:00 | 2027-05-26 | 23:59 | 3 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-003008/26 | Ostrava - Breclav | < > | Staré Město u U.H. | Huštěnovice | 2027 | 2027 | 20 | 20 | 2027-05-21 | 0:00 | 2027-05-23 | 23:59 | 3 days | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:06
0054 | V-000968/26 | Ostrava - Breclav | < > | Otrokovice | Otrokovice | 2027 | 2027 | 26 | 26 | 2027-07-03 | 18:00 | 2027-07-04 | 6:00 | 1 x 8 hours | periodical | Miscellaneous |  | ST |  |  | X |  |  | ,X,X |  |  | 5b,5c bez TV, 4.-14.,116 jen TV, 1.,2.,3. + TV. |  |  |  | 2026-04-29 10:06 |  | 6,7
0054 | V-017494/25 | Wroclaw - Breclav | < > | Odb Zádulka | Č.Třebová vjezd.sk. | 2028 | 2028 | 49 | 52 | 2028-12-10 | 0:00 | 2028-12-31 | 23:59 | 22 days | continuous | Miscellaneous |  | LT | [8 empty] | 4 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-017492/25 | Wroclaw - Breclav | < > | Třebovice v Čechách | Česká Třebová | 2028 | 2028 | 52 | 49 | 2028-01-01 | 0:00 | 2028-12-09 | 23:59 | 344 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2,1 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-017492/25 | Wroclaw - Breclav | < > | Odb Zádulka | Česká Třebová | 2028 | 2028 | 52 | 49 | 2028-01-01 | 0:00 | 2028-12-09 | 23:59 | 344 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2,1 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-017492/25 | Wroclaw - Breclav | < > | Česká Třebová | Odb Parník | 2028 | 2028 | 52 | 49 | 2028-01-01 | 0:00 | 2028-12-09 | 23:59 | 344 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2,1 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-017218/25 | Detmarovice - Cadca | < > | Odb Karviná-Darkov z | Louky nad Olší | 2028 | 2028 | 52 | 45 | 2028-01-01 | 0:00 | 2028-11-07 | 23:59 | 312 days | continuous | Track & Rail |  | LT | [8 empty] | 0. bez TV. |  |  |  | 2026-04-29 10:07
0054 | V-016755/25 | Wroclaw - Breclav | < > | Brno hl.n. | Odb Brno-Židenice z | 2028 | 2028 | 48 | 48 | 2028-11-27 | 0:00 | 2028-11-29 | 23:59 | 3 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016754/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno hl.n. | 2028 | 2028 | 10 | 10 | 2028-03-06 | 0:00 | 2028-03-08 | 23:59 | 3 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 1 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016753/25 | Wroclaw - Breclav | < > | Brno hl.n. | Odb Brno-Židenice z | 2028 | 2028 | 13 | 13 | 2028-03-27 | 0:00 | 2028-03-29 | 23:59 | 3 days | continuous | Miscellaneous |  | LT | [5 empty] | ,X,X |  |  | 2 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016751/25 | Wroclaw - Breclav | < > | Brno-Černov.zhl.Táb. | Odb Brno-Židenice z | 2028 | 2028 | 10 | 10 | 2028-03-06 | 0:00 | 2028-03-08 | 23:59 | 3 days | continuous | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016751/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2028 | 2028 | 10 | 10 | 2028-03-06 | 0:00 | 2028-03-08 | 23:59 | 3 days | continuous | Miscellaneous | T | LT | [5 empty] | ,X,X | [6 empty] | 2026-04-29 10:07
0054 | V-016748/25 | Wroclaw - Breclav | < > | Odb Brno-Židenice z | Brno-Maloměřice | 2028 | 2028 | 47 | 47 | 2028-11-20 | 0:00 | 2028-11-22 | 23:59 | 3 days | continuous | Miscellaneous | T | LT | [5 empty] | ,X,X | [6 empty] | 2026-04-29 10:07
0054 | V-016661/25 | Breclav - Wien | < > | Břeclav st.hr. | Břeclav os.n. | 2028 | 2028 | 15 | 16 | 2028-04-12 | 0:00 | 2028-04-22 | 23:59 | 11 days | continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016660/25 | Breclav - Wien | < > | Břeclav os.n. | Břeclav st.hr. | 2028 | 2028 | 14 | 15 | 2028-04-03 | 0:00 | 2028-04-12 | 23:59 | 10 days | continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016593/24 | Ostrava - Breclav | < > | Otrokovice | Otrokovice | 2028 | 2028 | 18 | 49 | 2028-05-01 | 0:00 | 2028-12-10 | 23:59 | 224 days | continuous | Miscellaneous |  | ST |  |  | X | [5 empty] | 3a,5,5a,5b,5c,7,9 jen TV, 1,3 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016591/24 | Ostrava - Breclav | < > | Otrokovice | Tlumačov | 2028 | 2028 | 7 | 12 | 2028-02-16 | 0:00 | 2028-03-21 | 23:59 | 35 days | continuous | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016590/24 | Ostrava - Breclav | < > | Tlumačov | Otrokovice | 2028 | 2028 | 12 | 17 | 2028-03-22 | 0:00 | 2028-04-30 | 23:59 | 40 days | continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016485/24 | Wroclaw - Breclav | < > | Odb Rajhrad | Hrušovany u Brna | 2028 | 2028 | 32 | 45 | 2028-08-12 | 0:00 | 2028-11-09 | 23:59 | 90 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016484/24 | Wroclaw - Breclav | < > | Odb Rajhrad | Hrušovany u Brna | 2028 | 2028 | 20 | 32 | 2028-05-15 | 0:00 | 2028-08-12 | 23:59 | 90 days | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016324/23 | Wroclaw - Breclav | < > | Letovice | Skalice nad Svitavou | 2028 | 2028 | 15 | 26 | 2028-04-11 | 0:00 | 2028-06-26 | 23:59 | 77 days | continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016323/23 | Wroclaw - Breclav | < > | Skalice nad Svitavou | Letovice | 2028 | 2028 | 26 | 37 | 2028-06-27 | 0:00 | 2028-09-11 | 23:59 | 77 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016136/25 | Ostrava - Breclav | < > | Hustopeče nad Bečvou | Hranice na Moravě | 2028 | 2028 | 40 | 44 | 2028-10-02 | 0:00 | 2028-10-31 | 23:59 | 30 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-016135/25 | Ostrava - Breclav | < > | Hranice na Moravě | Hustopeče nad Bečvou | 2028 | 2028 | 35 | 39 | 2028-09-02 | 0:00 | 2028-10-01 | 23:59 | 30 days | continuous | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-015483/25 | Wroclaw - Breclav | < > | Lichkov | Dolní Lipka | 2028 | 2028 | 22 | 24 | 2028-05-29 | 0:00 | 2028-06-17 | 23:59 | 20 days | continuous | Track & Rail | T | LT | [5 empty] | ,X,X |  |  | 1 bez TV. |  |  |  | 2026-04-29 10:07
0054 | V-009072/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2028 | 2028 | 41 | 41 | 2028-10-10 | 18:00 | 2028-10-11 | 6:00 | 1 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:07 |  | 2,3
0054 | V-009068/26 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2028 | 2028 | 41 | 41 | 2028-10-10 | 0:00 | 2028-10-11 | 23:59 | 2 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-009057/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2028 | 2028 | 41 | 42 | 2028-10-10 | 18:00 | 2028-10-17 | 6:00 | 7 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:07 |  | 1,2,3,4,5,6,7
0054 | V-007883/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2028 | 2028 | 10 | 15 | 2028-03-11 | 18:00 | 2028-04-16 | 6:00 | 36 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:07 |  | 1,2,3,4,5,6,7
0054 | V-007909/26 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2028 | 2028 | 49 | 50 | 2028-12-08 | 18:00 | 2028-12-11 | 6:00 | 3 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 2. + TV. |  |  |  | 2026-04-29 10:07 |  | 1,5,6,7
0054 | V-007908/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2028 | 2028 | 42 | 51 | 2028-10-18 | 0:00 | 2028-12-23 | 23:59 | 67 days | continuous | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-007905/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2028 | 2028 | 35 | 35 | 2028-08-31 | 18:00 | 2028-09-03 | 6:00 | 3 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:07 |  | 4,5,6,7
0054 | V-007904/26 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2028 | 2028 | 35 | 42 | 2028-08-31 | 0:00 | 2028-10-18 | 23:59 | 49 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-007901/26 | Ostrava - Breclav | < > | Huštěnovice | Napajedla | 2028 | 2028 | 20 | 21 | 2028-05-21 | 18:00 | 2028-05-24 | 6:00 | 3 x 4 hours | periodical | Miscellaneous | T | LT | [5 empty] | ,X,X |  |  | 1. + TV. |  |  |  | 2026-04-29 10:07 |  | 1,2,3,7
0054 | V-007900/26 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2028 | 2028 | 20 | 23 | 2028-05-21 | 0:00 | 2028-06-06 | 23:59 | 17 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-007882/26 | Ostrava - Breclav | < > | Napajedla | Huštěnovice | 2028 | 2028 | 10 | 23 | 2028-03-11 | 0:00 | 2028-06-06 | 23:59 | 88 days | continuous | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-005235/26 | Detmarovice - Cadca | < > | Louky nad Olší | Odb Karviná-Darkov z | 2028 | 2028 | 38 | 52 | 2028-09-18 | 0:00 | 2028-12-31 | 23:59 | 105 days | continuous | Track & Rail |  | LT | [8 empty] | 2. bez TV. |  |  |  | 2026-04-29 10:07
0054 | V-005230/26 | Detmarovice - Cadca | < > | Louky nad Olší | Odb Karviná-Darkov z | 2028 | 2028 | 45 | 52 | 2028-11-07 | 0:00 | 2028-12-31 | 23:59 | 55 days | continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07
0054 | V-004437/26 | Wroclaw - Breclav | < > | Hrušovany u Brna | Modřice | 2028 | 2028 | 7 | 9 | 2028-02-16 | 18:00 | 2028-02-29 | 6:00 | 13 x 6 hours | periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  | 2026-04-29 10:07 |  | 1,2,3,4,5,6,7
Formulas:
Week = WEEKNUM([Period from])
To = WEEKNUM([Period to])
Note on T3: ST = Station Track LT = Line Track
Map
Show all
New
Changed/Modified
Deleted/ will not be implemented